Project Tracking - Late Finals Reason Codes

| CODE | DESCRIPTION | EXPLANATION |
| --- | --- | --- |
| CDLY | Contractor Delay | Use whenever there is a delay caused by the contractor – i.e. insufficient paperwork; not responding to inquiries (tentative final), etc. |
| CLMS | Claims. | Use when claims have been filed on a project. This could be a wage claim or when a contractor, municipality, etc. files a claim or when a lien is filed against a project. |
| CNQI | Construction Quality Issues / Repairs to be Addressed. | Use when projects need repair, warranty issues are pending or when additional work is needed on a project. |
| MTLS | Materials | Use when waiting on materials certification. |
| OTHR | Other | Use for any other reason not covered in the descriptions above. Some examples – overpayment to contractor not being paid promptly, environmental concerns, legal issues pending. Whenever this code is used describe the issue completely in the Finals Remarks field. |
| PLFC | Finals corrections needed / Project Leader Delay. | Use when finals have been reviewed and corrections are needed or missing documents have to be submitted by the project leader. Examples: Incomplete finals records, outstanding contract modifications, etc. |
| PLST | Punch List Items to be Completed. | Use when there is still minor punch list items that have not yet been completed. |
| QMPD | QMP Deductions. | Use for QMP issues such as deductions in dispute, deficient or rejected materials to be replaced, etc. |
| QTYD | Quantity Disputes. | Use for quantity disputes with the contractor after the tentative final has been sent and the 30 day period has expired. |
| SFST | Staff Shortages. | Use when regional office staff are not available due to vacant positions or workload assignments to perform reviews of finals, payrolls and materials. |
| WCLC | Wage Claim / Investigation Labor Compliance | Use whenever there has been a wage claim filed or there are delays in getting payrolls cleared to due contractor not responding to requests. |
| DLTE | Delete | Use when code is incorrectly entered and needs to be removed. |