## Nuclear Density Incentive
ITEM: | INCENTIVE DENSITY HMA PAVEMENT | [5 empty] | PROJECT I.D.
ROADWAY
ITEM #: | 460.2000 | [5 empty] | DESCRIPTION
CATEGORY: | 0010 | [5 empty] | COUNTY
ENTERED BY:
CHECKED BY:
** ENTER ALL INFO. IN RED COLUMNS.
DATE | DESCRIPTION | MIX | Computed | Density | Density |  | POTENTIAL | ACCEPTABLE | ACTUAL | PENALTY | REMARKS
PLACED | OF LOT | TYPE | LOT | LOT | REQ'D | DIFF. | INCENTIVE($) | AIR VOIDS? | INCENTIVE | % PAY | (LOT #)
|  |  | TONS | AVG. |  |  |  | See Note
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[6 empty] | 0 | 0 |  | 0 | 100
[8 empty] | TOTAL = | 0
Note: Regarding Air Voids - 460.5.2.3 (1) "If the lot density id greater than the minimum specified in table 460-3 and all individual air voids test results for that mixture placed during the same day are withing +1.0 percent and -0.5 percent of the design target in table 460-2, the department will adjust pay for that lot as follows:". Therefore, place a YES in the column if ALL air voids tests for that mixuture placed during that same day are within the acceptable limits (3.5% - 5%). If any single test for that mixture on that day is outside the acceptable limits, place a NO in the Column.

## Example
ITEM: | NUCLEAR DENSITY | [5 empty] | PROJECT I.D. | 2490-02-99
| INCENTIVE | [5 empty] | ROADWAY | STH 54 / 73
ITEM #: | 460.2000 |  |  | LOWER, INTERMEDIATE, UPPER LIFTS |  |  | DESCRIPTION | 2ND AVENUE SOUTH, WIS. RAPIDS
CATEGORY: | 0010 | [5 empty] | COUNTY | WOOD
ENTERED BY: | TRE
CHECKED BY:
** ENTER ALL INFO. IN RED COLUMNS.
DATE | DESCRIPTION | MIX | Computed | Density | Density |  | POTENTIAL | ACCEPTABLE | ACTUAL | PENALTY | REMARKS
PLACED | OF LOT | TYPE | LOT | LOT | REQ'D | DIFF. | INCENTIVE($) | AIR VOIDS? | INCENTIVE | % PAY | (LOT #)
|  |  | TONS | AVG. |  |  |  | See Note
9/03/04 | SENECA RD. LOWER | E-3 | 55.9 | 89 | 89.5 | -0.5 | PENALTY | YES | 0 | 98 | LOT 1
9/09/04 | SENECA RD. MID. | E-3 | 39.1 | 90.8 | 91.5 | -0.7 | PENALTY | No | 0 | 98 | LOT 2
9/13/04 | SENECA RD. UPPER | E-3 | 39.1 | 92.7 | 92 | 0.7 | 0 | YES | 0 | 100 | LOT 3
9/03/04 | 253+00 - 262+78 LOWER | E-3 | 750 | 89.8 | 89.5 | 0.3 | 0 | YES | 0 | 100 | LOT 4
9/03/04 | 262+78 - 273+00 LOWER | E-3 | 750 | 90.7 | 89.5 | 1.2 | 300 | YES | 300 | 100 | LOT 5
9/03/04 | 273+00 - 284+74 LOWER | E-3 | 750 | 91.4 | 89.5 | 1.9 | 600 | YES | 600 | 100 | LOT 6
9/07/04 | 284+74 - 296+25 LOWER | E-3 | 750 | 90.9 | 89.5 | 1.4 | 300 | YES | 300 | 100 | LOT 7
9/08/04 | 296+25 - 316+25 LOWER | E-3 | 750 | 91.6 | 91.5 | 0.1 | 0 | YES | 0 | 100 | LOT 8
9/08/04 | 296+25 - 316+25 LOWER | E-3 | 750 | 92 | 89.5 | 2.5 | 600 | YES | 600 | 100 | LOT 9
9/09/04 | 90+25 - 98+00, 202+00 - 208+00 LOWER | E-3 | 76 | 93.7 | 89.5 | 4.2 | 600 | No | 0 | 100 | LOT 10
9/09/04 | 98+00 - 202+00 LOWER | E-10 | 578 | 93.1 | 90 | 3.1 | 600 | No | 0 | 100 | LOT 11
9/07/04 | 335+55 - 350+27 LOWER | E-3 | 750 | 92.2 | 91.5 | 0.7 | 0 | YES | 0 | 100 | LOT 12
9/08/04 | 53+00 - 266+97 MID. | E-3 | 750 | 91.2 | 91.5 | -0.3 | 0 | YES | 0 | 100 | LOT 13
9/08/04 | 266+97 - 273+00 MID. | E-3 | 750 | 91.9 | 91.5 | 0.4 | 0 | YES | 0 | 100 | LOT 14
9/08/04 | 273+00 - 289+50 MID. | E-3 | 750 | 90.5 | 91.5 | -1 | PENALTY | YES | 0 | 98 | LOT 15
9/08/04 | 289+50 - 296+25 MID. | E-3 | 750 | 91.9 | 91.5 | 0.4 | 0 | YES | 0 | 100 | LOT 16
9/10/04 | 90+25 - 98+00, 202+00 - 208+00 MID. | E-3 | 64.9 | 91.9 | 91.5 | 0.4 | 0 | YES | 0 | 100 | LOT 17
9/10/04 | 98+00 - 202+00 MID. | E-10 | 429 | 91 | 92 | -1 | PENALTY | YES | 0 | 98 | LOT 18
9/13/04 | 253+00 - 266+97 UPPER | E-3 | 750 | 92.3 | 91.5 | 0.8 | 0 | YES | 0 | 100 | LOT 19
9/13/04 | 266+97 - 273+00 UPPER | E-3 | 750 | 92.1 | 91.5 | 0.6 | 0 | YES | 0 | 100 | LOT 20
9/13/04 | 273+00 - 294+00 UPPER | E-3 | 750 | 91.6 | 91.5 | 0.1 | 0 | YES | 0 | 100 | LOT 21
9/13/04 | 294+00 - 316+25 UPPER | E-3 | 750 | 91.4 | 91.5 | -0.1 | 0 | YES | 0 | 100 | LOT 22
9/11/04 | 90+25 - 98+00, 202+00 - 208+00 UPPER | E-10 | 614.9 | 93.5 | 92 | 1.5 | 300 | YES | 245.96 | 100 | LOT 23
9/11/04 | 98+00 - 202+00 UPPER | E-10 | 750 | 92.1 | 92 | 0.1 | 0 | YES | 0 | 100 | LOT 24
9/14/04 | 335+55 - 350+27 UPPER | E-3 | 564.3 | 93 | 91.5 | 1.5 | 300 | YES | 225.72 | 100 | LOT 25
[8 empty] | TOTAL = | 2271.68
Note: Regarding Air Voids - 460.5.2.3 (1) "If the lot density id greater than the minimum specified in table 460-3 and all individual air voids test results for that mixture placed during the same day are withing +1.0 percent and -0.5 percent of the design target in table 460-2, the department will adjust pay for that lot as follows:". Therefore, place a YES in the column if ALL air voids tests for that mixuture placed during that same day are within the acceptable limits (3.5% - 5%). If any single test for that mixture on that day is outside the acceptable limits, place a NO in the Column.