CORRESPONDENCE/MEMORANDUM	State of Wisconsin

Date:		January 2013

To:		2013 Construction Project Leaders

From:		Jennifer Oldenburg, Northwest Region-Eau Claire Contract Specialist

Subject:	Construction Project Information

Construction contract information for 2013 season. PLEASE READ THOROUGHLY!

- Before a Field Manager contract can be loaded on your computer, the following procedures must occur:

  - Contract must be fully executed and signed (Central Office – Madison).

  - Approved ECIP. Contractors should submit ECIP to WisDOT (David Larson) and DNR 14 days prior to preconstruction meeting. Once ECIP approved, send me an electronic pdf of the approved copy for our files.

  - Sublet requests approved. Contractors should submit to Elaine Ogilvie, for approval. Once they are approved, I will enter subcontractors into Field Manager and forward a copy to you.

  - Copy of Railroad Insurance Policy (if required by special provisions). Contractor should submit to Jennifer Oldenburg, Northwest Region-Eau Claire Contract Specialist. Copy will be sent to you electronically as pdf.

  - Copy of Warranty Bond (if required). Contractor should submit to Jennifer Oldenburg, Northwest Region-Eau Claire Contract Specialist. Copy will be sent to you electronically as pdf.

  - Once the above things have been completed, contact Adam Bleskacek to schedule time for installing new software.

  - Contact me to send FieldManager and FIT contract data. Contract cannot be released until above information is completed.

- Once project has started, check FIT and update Field Office / Contact information. Field Office report is run off of information entered into FIT. Please enter in a timely fashion.

- Merge and send FIT data every time you make any changes to your contract in Field Manager or FIT, i.e. estimates, diaries, etc. This information merges into the Project Tracking database, which is used for doing reports, labor compliance, etc. Project overview and problem solving works much better when we have the most current data to use. If you find yourself falling behind, just let me know and we’ll see if we can find a solution.

- Send Precon minutes to me for after they have been completed electronically. Form has been sent to you electronically prior to the precon & also a hard-copy is included in precon packet to use for minutes.

- Let me know when the start notice needs to go out. Without a start notice, the contractor cannot contractually start work. Enter those dates into Field Manager and merge and send in FIT. Let me know if there are any changes to the status of the project, i.e. suspension dates, etc.

- Let me know when project is completed. Email is fine. Enter those dates into Field Manager - there 3 dates that need to be entered into Field Manager – Date Opened to Traffic, All Contract Work Completed and Time Charges Stop Date.

- Notify me when the project final acceptance letter should be sent.

- Project final documents need to be sent into our office for review within 30 days of the project being final accepted. The project leader should submit for payment the tentative final estimate within 90 days of the project being substantially complete if the final documents have been reviewed.

- As-built plans are required for all projects. A cd is included with your precon packet with a copy of the as-let plan to use when completing the electronic as-built. Also a hard-copy stamped as-built plan is included with your precon packet. Complete electronic copy, burn to a cd & place in final records (see attached instructions with your as-built cd). Complete hard-copy as-built & mark all changed pages. Place in final records.

- Use the final records boxes we provide for you. Boxes can be requested through the Region’s front desk or records management staff.

- Complete contractor evaluation form in FieldManager for prime contractor and each 1st tier subcontractor on the project after project completed. Report is found in Field Manager. Print, sign and include it with final records.

- Complete DQI (Design Quality Index) in FIT when project completed.

- All diary information must be entered into FieldManager. This information is used by office staff and it is required. Print out & place in binder.

- Complete structure information in FIT if there is structure on project.

- If you have any problems with Field Manager or FIT working properly or if you have questions on where to find certain things that you need to enter in FIT or Field Manager, please let me know and I’ll help.

- Contact Elaine Ogilvie , 715.635.2048  or Elaine.Ogilvie@dot.wi.gov, with any labor compliance.

- Contact me, Jennifer Oldenburg, 715.225.9592  or Jennifer.Oldenburg@dot.wi.gov    with any contract administration questions or FieldManager / FIT questions.