1

_

| SUBJECT: | I.D. |  |
| --- | --- | --- |

This is to confirm arrangements made to hold a preconstruction conference to review construction operations and required utility coordination on the subject project.  By copy of this letter, interested parties, including utilities are being invited to this meeting.

The meeting will be at       , on ,     in Room  located at the Lee Sherman Dreyfus State Office Building, 141 N.W. Barstow Street, Waukesha, Wisconsin.  Please register with the receptionist on the 2nd level of the East Building.

Submit your proposed schedule of operations to the project manager at least 14 calendar days prior to the preconstruction conference.  Be prepared to discuss your schedule of operations at the preconstruction conference.  The format for the Schedule of Operations should be a horizontal bar chart or linear schedule, with room provided for future revisions.  Schedules should be reviewed at regular intervals and updated to reflect delays, etc. that will impact the schedule.

Also included are guidelines that are to be addressed at all preconstruction conferences.  These guidelines were a product of the Contract and Construction Improvement Committee and agreed by the DOT and the WTBA.  The guidelines include information on the following:  how to conduct construction meetings; the establishment of a chain of communication; and timeliness criteria for decision making, prior approvals, and processing paperwork.  You are encouraged to fill in the necessary information, such as chain of communication for yourselves as well as your subcontractors, before coming to the meeting.

Trans 401 requires an Erosion Control Implementation Plan to be submitted to the appropriate WisDOT Office and the WDNR at least (14) days prior to the preconstruction meeting.  An erosion control inspection sheet will be used for routine and emergency inspections.  This completed form will be given to the prime contractor if corrective action is necessary.  This is also a requirement of Trans 401.

You and your subcontractors should be prepared to discuss the pertinent requirements of the Special Provisions as related to your contract obligations.  Also required of you will be the name of the individual who will be your authorized representative on the project site and an alternate person who will have that same capacity in case the first person is not present.

If you have any questions regarding this project, please contact      , Project , at      .

Sincerely,

Project

/

Enclosures

| cc: | , Project Manager | J. Hosseini, Field Support Eng., CO Const. |
| --- | --- | --- |
|  | , Project Leader | C. Peterson, TSS Mgr. |
|  | , PD Supervisor | B. DuPont, Freeway Operations |
|  | , Group Manager | N. Vega, Equal Rights Officer |
|  |  | T. Peschke, Materials |
|  | L. Longley, Utilities/Railroads C. Hardy, SHR Utility Construction Engineer G. Berry, Mega Project Utility Const. Engineer M. Rojas, Mega Permits | P. Ambrose, Maintenance Engineer N. Martin, Maintenance Engineer |
|  | A. Lopez, Highway Maintenance Supervisor | T. Heydel, Traffic Operations |
|  | D. Jashinsky, Structures Maintenance | A. Zimmer, Supervisor TSS |
|  | D. Balog, Materials | M. Luty, Electrical Field Unit |
|  | J. Haug, Signal Operations Supervisor T. Kittson, Utilities Supervisor | S. Lee, Environmental Services H. Hallanger, Environmental Services |
|  |  | C. Wierzchowski, Soils Engineer |
|  | M. Pyritz, Public Information Office | J. Boggs, HMA |
|  | B. Blum, Construction Services B. Wondrachek, Work Zone Engineer | J. Washburn, SEWRPC J. Kutschenreuter, TSS Materials |
|  | Note: See Outlook distribution list: | DOT DL DTSD SE PDS PRE-CON |
|  | Note: Choose one of the following for DNR: |  |
|  | M. Thompson, WisDNR, General Mitchell BOA Projects Email address: michaelc.thompson@wisconsin.gov | K. Betzold, WisDNR, Zoo Interchange, Ozaukee Co., Milwaukee Co., Racine Co., Washington Co. Email address: Kristina.betzold@wisconsin.gov |
|  |  | C. Webster, WisDNR, Kenosha Co., Walworth Co., Waukesha Co. Email address: craig.webster@wisconsin.gov |
|  | Note: Other FHWA: |  |
|  | J. Berg, FHWA Email address: john.berg@dot.gov |  |