2.40 PROMPT PAYMENT

Prompt payment should be discussed at all pre-construction meetings.  Inform contractors that ASP 4 requires contractors to pay the subcontractors for satisfactorily completed work within 10 calendar days of receiving a progress payment.  If they will not be making payment to any of their subcontractors within the prescribed 10 calendar days they are required to provide a “good cause” explanation to the engineer prior to withholding payment.  ASP 4 can be found at the following extranet site.

https://trust.dot.state.wi.us/extntgtwy/hcci/bid-letting/related-info/asp-4.pdf

When a prompt payment is received, document your actions:

- Write a memo regarding the complaint received.

- Confirm WisDOT has paid on that particular estimate.

- Send letters to all subcontractors asking if they have been paid promptly.

- CC: the prime contractor, Central Office, Construction Administration Karen Roberts

- Request confirmation of payment from the prime contractor.

If the payment problem is not resolved;

- Inform (by registered mail) the prime contractor of default.

- CC: Bonding Company, Central Office, Construction Administration Karen Roberts.

- Refer matter to the Bureau of Highway Construction.

If the payment problem is resolved;

- Send a closure letter to the complainant.

- CC: Central Office, Construction Administration Karen Roberts

Refer to the procedures outlined in the Construction and Materials Manual, Chapter 2, Section 40.1.2

Important information:

Make sure that you have good documentation regarding the complaint and that all your estimates to the prime contractor are prompt and current.

A Sample Letter for you to use is available in the Pantry Software under the SE Region file.

__

Subject:  Prompt Payment to Sub-Contractors

Project ID

Section

Highway

County

It has come to our attention that you have not compensated your sub-contractor(s):  contractor name, for all of their work completed on the subject project.

Additional Special Provision 4 states, “Within 10 calendar days of receipt by a contractor of progress payment for work performed, materials furnished, or materials stockpiled by a subcontractor, the contractor shall pay that subcontractor for all work satisfactorily performed and for all materials furnished or stockpiled.”

Below are the pertinent details relating to this issue:

EXAMPLE PARAGRAPH --- DELETE & TYPE IN BELOW

Subcontractor BBB has a total of $8,000.00 yet to be paid on this contract.  $400,000 of this total is for the item High Strength Bar Steel.  High Strength Bar Steel was paid in full in estimates 1, 2, and 3 for a total of $7,000.00.  $4,000.00 is to be paid for additional accessories that were required through this contract due to a contract change order between Contractor AAA and Subcontractor BBB.

This letter serves to inform you that you have ten (10) calendar days to either pay for the satisfactory work performed by subcontractor name or provide the Department with “Good Cause” for non-payment.  Absent of “Good Cause”, when payment is made, please send a copy of the check to the District Office as verification that you followed through on your contract obligations.  If you fail to comply, the Department may proceed with “Terminating the Contract for Default” per subsection 108.12 of the Standard Specifications.

If you have any questions regarding this issue or would like more clarification, please contact me at     .

Sincerely,

cc: Javad Hosseini, BHC Regional Engineer for District

Bonding Company

subcontractor name

Karen Roberts, Construction Services Coordinator

Project File

Team Leader

Group Manager