MATERIALS HELPFUL HINTS 2014

CONTACT LIST

| NAME | OFFICE PHONE | CELL PHONE |
| --- | --- | --- |
| ANDY ZIMMER (MATERIALS SUPERVISOR) | 262-521-4406 | 414-750-1543 |
| CASEY WIERZCHOWSKI (SOILS ENGINEER) | 262-521-4427 | 414-588-0639 |
| JUSTIN KUTSCHENREUTER (MATERIALS ENG) | 262-548-6441 | 414-750-0923 |
| DEANN BALOG (MATERIALS SERVICES) | 262-548-5697 | 414-750-2676 |
| SHERYL SORBY (WEST ALLIS LAB.) | 414-266-1156 | 414-750-0880 |
| JON JOSLIN (IA) | 262-521-4423 | 414-750-1937 |
| TODD PESCHKE (PAVEMENT DESIGN) | 262-548-5696 |  |
| JIM BOGGS (HMA Scheduling) | 262-548-8758 |  |

PRE-CON MATERIALS LIST:

- Establish Department materials person (WDMP) and Contractor materials person (CDMP)

- WDMP provide materials guide to contractor, both WDMP and CDMP should review guide prior to construction. Highly recommended that WDMP and CDMP take HTCP materials training

- Contractor to submit 3 copies of Source of Materials (DT1349), to Project leader, forward copy to Justin Kutschenreuter.

- Should receive Base Aggregate QMP plan.

- Emphasize that payment will not be released until all materials are submitted, reviewed and approved.  Must be submitted in timely manner.

DURNING CONSTRUCTION

- Make sure materials documentation is received and APPROVED prior to material being incorporated into work (Section 106.1 of Standard Spec). Compare material documentation to contract requirements. WDMP initial and date once approved.

- Keep materials files organized and up to date.

- Notify Materials unit of change orders to assist with additional documentation

- Review all QMP plans, see checks list in materials region specific pantry software.

- Call Sheryl Sorby for bean guard testing

- Hold pre-pour and pre-pave meetings. Be sure to invite the following from TSS

  - Pre-Pave:  Justin Kutschenreuter, Jon Joslin, and Jim Boggs.

  - Pre-Pour: Justin Kutschenreuter, Jon Joslin, and Sheryl Sorby.

  - Pre-Pour/Pave agendas can be found in pantry software, statewide forms.

  - Notify IA prior to all pours, paves, base course placement, and QMP subgrade.

- Verify contractor follows QMP plan (i.e. make sure contractor is taking proper number of tests, verify QC field testers have proper certifications, verify proper mix)

- QV  testing: Verify QV sample frequency.  Deliver samples to labs in timely manner.  Call Signe Reichelt (Behnke Materials), 608-449-8427 to pick up concrete cylinders, verify cylinder picked in allotted time.

- Monitor QC data that it meets specifications.  Ensure data is being supplied in timely manner

- Notify Justin Kutschenreuter of all non-conformance/non-performance issues

POST CONSTRUCTION

      - See Materials Finals Check list in Pantry Software in SE regions specific folder.