## Sheet1
Project Label
SW REGION-LA CROSSE OFFICE CONSTRUCTION PROCESS
PRIOR TO PROJECT START:
Project Leader notify Survey to determine if any Section Corners will be disturbed with the project construction.
Wendy Braun, Project Manager & Project Leader review the ECIP and Prosecution and Progress Schedule
(Make sure DNR has ECIP and 2 weeks to review prior to precon)
Project Manager (with Wendy B approval letter) issue a ECIP Approval Letter to Contractor (confirm that materials sites are approved)
Project Leader set up Pre-construction Conference and send notices to contractor & utilities - Pantry - PCRequest Form to Sally
(Consultant Project Managers will do this for consultant run projects)
Project Leader sets up Lane Closure System (2 weeks prior to start) http://transportal.cee.wisc.edu/closures/
Project Leader enters staff in Field Manager and FITS Staff Info and Field Office location - see Project Leader packet handout
email Grace Bernu once field office information is entered in FITS - Send FITs
Project Manager confirms that Let contract has been executed & sublet request is approved
Project Manager informs Grace to issue the Project Start Notice - copy to Project Leader, Doak, and County Hwy Commissioner
Project Leader pays for any Stockpile Materials Requests submitted by Contractor (if it is reasonable)
Project Manager and/or Project Leader process any QMP according to the C & M Manual
Project Leader complete the Emergency Phone List and provide a copy to different sections including Grace as well as local gov't
(including Sheriff Dept., Cty Hwy Commis, School District, DNR, etc…) Place copy in N:\PDS\Construction\Emergency phone list
Project Manager provides Project Leader a copy of Envir. Commit, Corp Permit, Notes to Const, Real Estate Commitments and TMP
Project Leader forwards structure shop drawings to B.O.S. - Steel to Craig Wehrle, sign structures to Bill Oliva
retaining walls = Lee Schuchardt
DURING CONSTRUCTION WHILE CONTRACTOR STILL ON-SITE:
Project Leader completes the Bulletin Board sheet to verify that all wage documents are placed within public view (Grace supply sheet)
Project Leader confirms Sublet Request forms have been approved before Subcontractors work on the project
Project Leader notify La Crosse Office Bridge Section to make inspections and updates FITS as soon as structures are complete
Make sure vertical clearance is measured and in FITS as well as Pantry form to Bridge Section before opening to traffic
If Partial Acceptance is requested by contractor, Project Manager will issue the letter with input from the Project Leader
Project Leader updates Lane Closure System as traffic stages change or roadway is opened to traffic.
As project is winds down, Project Leader shall notify Project Manager for site walk through/ punch list -include all mat'l docs needed
(Project Leader shall also notify Locals if required)
Project Leader should send Estimates at least every two weeks or as warranted by amount of work completed
Project Leader verifys Environmental Commitments have been addressed
UPON COMPLETION OF PROJECT WORK:
If project impacted Section Corners, coordinate resetting those Section Corners with Survey
Project Leader stops time in Field Manager > dbl click contract # > Gen. Tab & Site Times Tab (controls LD's)>> FITS send
PL fills in "All Contract Work Complete" date in FM once the punchlist is completed & all mat'l documents rec'd.
If contract has a plant establishment period, do not fill in a date until the estab. Period is complete
Project Leader fills in punchlist complete date in FIT when punchlist and all mat'l doc received
Project Leader updates FITS once punchlist is complete and sends FITS
Project Manager notifies Grace to issue Conditional Final Acceptance Letter when all contract work complete date is entered
( cc: Region Maintenance Engineer, BHC, Project Leader, County Commish & City (if applicable) )
Project Leader review Retainage(Field Manager>>Inquiries>>Project Status) with Project Manager prior to creating an estimate
If the retainage should be reduced, notify Grace of the dollar amount to reduce to along with the contract ID. Once Grace reduces it in
CAS, the Project Leader will be notified - then do a contract refresh and create a new estimate.
Project Leader updates all quantities and submits an intermediate estimate as soon as possible.
Project Leader updates Lane Closure Sysytem
Project Leader/Staff enter Materials tests and certifications in MIT
Project Leader shall have all computations and Field Manager entries checked by Project Staff.
Project Leader shall prepare As Built Plans - See "Requirements for Asbuilts" -
Project Leader /Staff Backup Project Electronic Files>>(c:\fieldmgr\fieldmgr.db, pantry comps, e-mails and Caice if applicable)
Project Manager close out any Consultant Contracts.
Project Leader send any Uniform Hazardous Waste Manifests to the Region Environmental Unit (Currently Steve Vetsch) as
soon as project is completed (Completed by solid waste consultant). For small rehab work, place lead paint waste in approved
containers and deliver to D-5 Pav't and Marking Coord. WITH PROJECT ID.
Project Leader notify Survey Coordinator if new R/W was acquired so that Final R/W Monument Staking can be completed.
UPON COMPLETION OF PROJECT FINAL PAPERWORK (Project boxed up and put in cage):
Once the paperwork is complete and Final Estimate sent, Project Leader shall send the FieldManager contract to IT for archival.
Process is as follow:
1. Start FieldManager>> Process Mail>>FIT send
2. Select File / Export / Transfer Contracts... from the main menu. Say Yes to Use Fieldnet
3. Highlight one contracts and press the <Select> button.
4. Select Transfer the contract . This will send the working copy and leave a R/O on your PC.
Once the contract has been successfully received, it can be removed from your PC.
5. Sort either the FieldNet ID Description field or the FieldNet ID field to find SW LAX - Master Let FMGR050. Press <Select> and the export process
will begin. A message window will appear stating that "The contract(s) were successfully exported. Press <Enter> to continue
6. Press <OK> and the export process will begin. A message window will appear stating that "The contract(s) were successfully exported."
Then press <Enter> to continue.
7. Send Mail.
1
2
5
6
7
11
13
14
16
17
1
19
15
2
3
4
5
6
7
8
9
10
11
12
15
16
17
18
19
22
25
26