Field Manager Guides:

Pantry/Instructions

Region Specific

*Note:  All page numbers refer to the PC User guide found in Pantry – Region Specific.

AT PROJECT START-UP:

- In Field Manager – Double click contract or select <Docu> button

- Click on Administrators Tab

- Enter Project Staff – see PE packet and page 4 PC User Guide

- Click on General Tab

  - Enter Construction Start Date. – see page 4 PC User Guide

- Click on Site Times Tab

  - Enter Time charges start date – see page 4 PC User Guide

  - Send outbox Select <FM Mailbox> button; then select <send outbox> button

- In Field Manager- Select the <Contractor> button.

- Add subcontractors – see page 6 PC User Guide

  - Close Field manager

- In FITs – Merge data

- Click on Field Office/ Staff Info tab -  see page 40 PC User Guide

  - Enter Field Office Location, staff phone numbers,  traffic control contractor& emergency number and materials personnel

- Click On Acceptance Tab

  - Enter Erosion Control Implementation Information

- Perform a FITS send

DURING CONSTRUCTION:

- Enter IDR’s for each day the contractor is working – In Field Manager- page 7 PC User Guide

- Select <IDR> Button then <Add>

  - Include weather and Inspector comments(General Tab)

  - Men and Hours for each contractor working (Contractor Tab)

  - Time charges (on working day projects) (Site Times Tab)

  - Postings (used to pay contractor for work) (Posting Tab)

- Select <Save> or <Save/ Close>

- Select <Generate>

- Enter Daily Diary for each day of the week (including weekends)- In Field Manager page 9

- Select <Diaries> then <Add>

  - Import weather and Comments from IDR <General Tab>

    - Project leader adds to inspectors comments- any discussions with PM, contractor, property owners, CO, etc.

  - Import Site Data (Site Times)

- Create Weekly Report of Time Charges (on working day contracts) -In Field Manager –page 10

- Select <Misc Rpts>

  - Double click “Weekly Report of Time Charges”

  - Select <Add> button

  - Select Site from drop down menu

  - Enter Week ending date

  - Select <Print>

  - Sign and date and ask prime contractor to sign

  - Select <Save> or <Save/ Close>

- Create an Estimate  -In Field Manager– page 18 PC User Guide

Send an estimate twice per month if $1000 or more is due – Once a week if > $50,000 is due.

- Note:  All IDR’s and Diaries need to be generated to create an estimate.  Estimates pull the data from the “Postings” tab of the IDR

- Get Mail – Utilities>>FieldNet>>Get Mail from FieldNet

- Process all messages >> Double click each unprocessed message.

- Select <Estimates> button.

  - Select <Add> button

  - Select “estimate date” and “estimate type” <OK>

  - Review “General Tab” and “Item Usage Tab”

  - If there is an error in item usage – correct corresponding IDR

  - Select <Generate> button

  - Print “Construction Pay Estimate Report” and Balance Report for file.

  - Send Estimate.  Utilities >>FieldNet >>Send Outbox to FieldNet

  - Exit Field Manager

  - Merge and Send FIT data

  - Email Project Manager that an estimate was sent.  cc Kelly Addison (Madison)  or Lynn West (LaCrosse) if estimate is tentative final or final.

- Create a Contract Modification – In Field Manager – page 11 PC User Guide

- Select <Cont Mods> button

  - Select <Add> button- Follow remaining instructions on page 11 PC User Guide

  - Fill in Short description and Description of change (General Tab)

    - NOTE: Contract modifications are a contract document.  The description of change should be written as a special provision or reference the standard specifications if bid item exists.

    - NOTE: In the description of change place a note in regards to contract time.  (no additional time or additional time granted)

  - For increase/ decrease in quantities use the Inc/Dec Tab

    - Enter the 2 digit reason code + the description for each item

  - For new items use the New Item tab

    - Enter the 2 digit reason code + the description for each item.

    - Avoid using lump sum items if possible use an “each”.  If for some reason you do not want to pay the entire dollar amount of an item- it is not possible with a lump sum to only pay a portion.

  - Address contract time in every change order.

- In FITs – Enter structures data -see page 40 PC User Guide

- Select Structures Tab

  - Detail tab – enter: Feature Under, Replacing Structure, Road On, Date Structure completed, and Date opened to traffic.

  - Type of Work Tab – Select <Add>

  - Clearance Tab (If feature is under is a roadway or railroad vertical clearance is required BEFORE opening to traffic.

    - NOTE: Also complete the vertical clearance pantry form and send to Bridge Maintenance Engineer before opening to traffic.

  - Perform a Fits Send.

AT PROJECT CONCLUSION:

- Stop time In Field Manager – Double click contract or select <Docu> button – page 4

- Select “General” Tab

  - Enter “Open to Traffic” date

  - Enter “All Contract work Complete” after all contract work that requires labor is complete including the punchlist and plant establishment periods.

- Select “Site Times” Tab

  - Enter “Time Charges Stop Date” (Controls liquidated damages)

- Send Outbox & Close Field Manager

- Review Retainage with Project Manager prior to sending tentative final.

- See Common Field Manager Errors/ Questions for procedure (at the end of this document).

- Once quantities checked and final- Check each item as complete in Field Manager

- Required prior to sending final estimate

- In Field Manager select the contract you wish to final

- Select <Item> button

- Select the item and click on <Change> or double click item

- Select the Documentation tab and check <Yes> next to Item Completed.  For items that vary by > (5% major items or 10% minor item) of the original contract quantity us the Documentation field to explain why.

- Select Save and close

- Follow above procedure until all items complete.

- Alternate method – use above procedure to document items with (5% major items or 10% minor item)  variation for original quantity.  Then while in the <Item> screen go to “Edit”>> “Select All”>>Edit “Mark items Completed”.  This will mark all items completed.

- In FITs  -

  - Select Acceptance Tab –

    - Enter ‘Punch-List Complete” date and make sure all other items that are pertinent to the contract are filled out (if a claim has been filed make sure that date is filed in).

  - Select DQI Tab and enter DQI

  - Select Field Report Tab

    - Select Explanation of Variation from the drop down and select view then print.

    - Select IDR Summary and Index Report by Item and Category from the drop down and select view and print.

  - Perform a FITs send.

- Item History to Date

- In Field Manager select the contract you wish to final

- Select <Inquiries> button

- Double Click on the “Item History to Date” report

- Click “Select All”

- Print Report – Note the report is large

- IDR Summary and Index Report by Item and Category

- Close Field Manager

- Open FITs and Merge

- Select your contract to final

- Select the “Field Report” Tab

- Select the down arrow and select report IDR Summary and “Index Report by Item and Category”

- Select “Print”

- Transferring a Field Manager contract to another work station.

- Back up field manager & FITS on both work stations

- Send/ receive Field Manager Mail (Make sure last estimate is approved and CAS contract refresh has been processed)

- Merge and send FIT data

- See page 31 of PC User guide for additional instructions

- TROUBLESHOOTING: If the contract is accidentally send to the wrong Field Manager account, notify Kristen McDaniel immediately.

- Archive and remove finaled contracts – See page 25 of pc User Guide

- DO NOT archive your contract until your final estimate is approved and you receive and process an estimate approval, an estimate report and a CAS contract refresh.

Common Field Manager Errors/ Questions:

Issue:  Field Manager sometimes fails to process contract modification in CAS.

Problem: CAS will prevent any vouchers (pay estimates) from being processed due to a failed contract modification.

Cause:  When a contract modification is first created (not approved) header information is generated that includes a net total cost.  Many times project leaders create a contract modification and save it in draft form and send it to the project manager.  If there is a change in the contract modification net cost after a draft has been created, the following FieldNet message maybe received by the project leader:

--FieldNet_Boundary_!@#0^&*()

Contmod Failed Post CAS Edit

CONTID: 20111108003

CMOD: 002

REVISION: 1

- -FieldNet_Boundary_!@#0^&*()--

Solution:  The project leader is the only person that will receive this message.  If this message is received the project leader/ manager must notify Kristen McDaniel (608) 261-2561 and they needed to physically go into the system and fix the error in order for CAS to process any vouchers (pay estimates).  Note: do not delete contract modification.

Note to Project Managers: If you are aware or request a change that modifies the net cost of a contract modification, notify the project leader to pay close attention to FieldNet messages.

Reducing Retainer and Field Manager Steps:

- Discuss reducing retainer with Project Manager. ( PM’s see below)

- Project Manager emails contract specialist BEFORE estimate is generated.

- Contract Specialists reduces retainer and emails Project Manager

- Project Manager notifies project leader to perform a contract refresh

  - Utilities>>fieldNet>>Request Contract Refresh from FieldNet

  - Process Refresh.  Utilities>>FieldNet>>Get Mail from FieldNet>>double click unprocessed items.

  - Project engineer creates and sends estimate.

  - NOTE:  If estimate has a “zero” dollar value – make sure the prior estimate is not a zero dollar estimate.  If this is the case – the retainer will not be paid out (error in the system).  The only fix is creating a $0.01 payment on the estimate.

For Project Managers(Reducing Retainer con’t):

The following must be complete in order to reduce retainer:

- All Contract Work Complete Date is entered in Field Manager.

- Final Acceptance has been granted

- Materials certification complete. Note: if the Materials Engineer is reviewing the materials, you can reduce the retainer with supervisor approval.

- Check with Labor Compliance for potential wage claims and dollar value associated with claim (do not reduce retainer  below claim )

- Check liquidated damages (project leader with Field Manager contract may need to assist- If an estimate has not been generated since liquidated damages occurred, they will not show up anywhere.)

Deleting an estimate – See page 19 of PC User Guide

Transferring a Field Manager contract – See page 29-31 of PC User Guide

Archiving a Field Manager Contract – see page 25 of the PC User Guide