2014

# SW REGION

# CONSTRUCTION INSPECTION GUIDELINES

# Table of Contents

REMOVALS	2

TRAFFIC CONTROL	3

EROSION CONTROL	4

CONTRACTOR STAKING	5

EARTHWORK	6

BASE AGGREGATE	7

PIPE CULVERT	8

STORM SEWER	9

CONCRETE PAVEMENT	10

ASPHALT PAVEMENT	11

CONCRETE BRIDGES AND CONCRETE MASONRY	12

STEEL BRIDGES	13

PILING	14

STRUCTURES (GENERAL)	15

ANCILLARY STRUCTURES	16

BOX CULVERTS, RETAINING WALLS, AND ENDWALLS	17

ANCILLARY CONCRETE	18

PAVEMENT MARKING	19

LANDSCAPING	20

ELECTRICAL	21

MATERIALS	22

INCIDENTAL CONSTRUCTION	23

# REMOVALS

- CMM reference: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-03-15.pdf

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-02-04.pdf#ss204

- See Special Provisions for additional requirements.

- Clearly mark removal limits and contact adjacent property owner and contractor (discretion)

  - Measure removals according to standard specifications for that bid item and to the accuracy indicated in the CMM 2-32.5 http://roadwaystandards.dot.wi.gov/standards/cmm/cm-02-32.pdf.

  - Utilize Pantry documents to aid measurement and keep originals.

  - Indicate “measured by” date and “computed by” date.

  - Have computations checked – indicate “checked by” date.

- Photograph or video existing conditions with removal limits shown.

  - Document “tie-in” locations.

  - Document standing water after rain events.

- Assure environmental regulations are adhered to, especially in the removing of buildings and abandoning of wells.

- Document removal dates, weather conditions, labor and equipment hours.

- Verify disposal locations are in accordance with the Erosion Control Implementation Plan (ECIP).

# NOTES:

- Local Road Identification Signs are the responsibility of the local unit of government (both removal and reinstallation)

  - Contact  local unit(s) of government prior to construction to let them know that removal is their responsibility, invite them to weekly meetings when appropriate, and provide anticipated starting/completion dates and project limits

  - Temporary signs for EMS during construction are also their responsibility

- Mailboxes – See CMM 3-15.5 – contractor should notify owners and postmaster – confirm with postmaster notice has been provided and see if they are willing to provide the mailbox installation guide.

http://roadwaystandards.dot.wi.gov/standards/cmm/cm-03-15.pdf#cm3-15.5

# TRAFFIC CONTROL

- CMM reference: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-01-45.pdf

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-43.pdf#ss643

- MUTCD reference:  http://mutcd.fhwa.dot.gov/pdfs/2009r1r2/pdf_index.htm

- WI supplement to MUTCD:  http://www.dot.wisconsin.gov/business/engrserv/wmutcd.htm

- Work Zone Safety:  http://epdfiles.engr.wisc.edu/pdf_web_files/tic/handbooks/WorkZoneSafety.pdf

- Flaggers Handbook:  http://epdfiles.engr.wisc.edu/pdf_web_files/tic/handbooks/FlaggersHandbook.pdf

- See Special Provisions for additional requirements.

- Review TMP (from design) for commitments.  Be familiar with the document and have a copy at the field office.

- Enter Lane Closure System (LCS) information two weeks prior to start of closure and any stage changes.  http://transportal.cee.wisc.edu/closures/

- Make sure Emergency Contact List has a 24 hour traffic control contact and is posted and has been sent to all appropriate parties listed on the bottom of form.

- Inspect traffic control at initial set-up and stage changes prior to traffic control contractor leaving the project.  Then perform daily inspections with some nighttime inspections.  Use the “Traffic Control Inspection Checklist” found in the pantry statewide forms folder for documentation.

- If field changes are needed, reference the Work Zone Safety guide listed above and/or contact the engineer.

- Quality Guidelines:  Refer to pamphlet from ATSSA “Quality Guidelines for Temporary Traffic Control Devices.”  Contact regional Traffic section for guidance.

- Document traffic control conditions observed daily and note discussions with contractor and report any shortfalls to engineer.

- Review and file weekly traffic control diaries from contractor and ensure at least one weekly night inspection has been performed.  See section 643.3.2 of the Standard Specifications.

http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-43.pdf#ss643

- If any accidents occur see CMM: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-01-55.pdf

- Measure quantities at intervals directed by engineer.  Pantry has a spreadsheet for documentation.

# EROSION CONTROL

- CMM reference: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-06-45.pdf

- Standard Specifications references:  (also see bid item) §107.20http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-01-07.pdf#ss107 and http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-28.pdf#ss628

- Trans 401 reference: http://www.legis.state.wi.us/rsb/code/trans/trans401.pdf

- Erosion Control Product Acceptability Lists (PAL) for Multi-Modal Applications: http://www.dot.wisconsin.gov/business/engrserv/docs/pal.pdf

- See Special Provisions for additional requirements.

- Review the approved ECIP prior to layout and confirm stockpile locations with contractor.

- Layout erosion control items utilizing the plan and FIT TO FIELD CONDITIONS.

- Do not allow ground disturbing activities prior to initial inspection of erosion control.

  - Verify all products are on the PAL.

  - Inspect and document erosion control weekly, after every rainfall event greater than ½”, and at the beginning of each construction stage as required by Trans 401.

  - Notify PM and DNR if any discharges occur into waterways.

- If corrective action is needed, fill out the Erosion Control Order.

  - Note:  An erosion control mobilization is not to be paid for corrective action.

- Document the weather conditions, labor and equipment hours on a daily basis.

- Measure and document appropriate bid items.

# CONTRACTOR STAKING

- CMM reference: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-07-00toc.pdf

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-50.pdf#ss650

- FDM Reference: http://roadwaystandards.dot.wi.gov/standards/fdm/19-10.pdf§19-10-43

- See Special Provisions for additional requirements.

- Obtain contractor survey packet from design project leader. See CMM 7.10.3 and FDM 19-10-43 for requirements.

- Verify plan control is still in place and usable. If not, contact Regional Survey Coordinator.

- Note benchmarks set on fire hydrants or telephone poles.  Have they been moved/ reconstructed?

- Randomly check survey stakes.

  - The frequency of checks is not defined; early in the project, daily verification is expected.  Once confidence in the ability of the crews is obtained, less frequent checks are acceptable.  Provide results to the contractor per Sec. 105.6.3(4) of the Standard Specifications.

- Obtain copies of survey books/ notes daily and randomly check computations. Keep in project records.

- Document the weather conditions, labor and equipment hours on a daily basis.

- Measure and document appropriate bid items.

- Prior to final payment, obtain copy of completed contractor survey packet and verify all information from the table in CMM 7.10.3 is included.

# EARTHWORK

- CMM reference http://roadwaystandards.dot.wi.gov/standards/cmm/cm-03-00toc.pdf

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-02-00.pdf

- See Special Provisions for additional requirements.

- Ensure ECIP is approved and borrow/waste sites are cleared for archaeology.

- Coordinate with contractor on how borrow excavation is going to be measured.  Ensure original cross-sections are taken at borrow site and it is clearly defined where WisDOT material only is coming from.

- Monitor contractor’s placement procedures to ensure a stable subbase, and ensure proper materials of the correct gradation and moisture content are being used (depends on bid item).

- Verify the contractor is placing the material in approved lift thicknesses and is using the proper compaction equipment (depends on bid item).  General requirements are in Standard Specifications Section 207 Embankment.

- The frequency of inspection should be enough in the beginning of the operations so that the inspector is satisfied that the contractor’s equipment, materials and methods will produce a stable subbase.  Once the inspector is satisfied with the contractor’s operations, the frequency of inspection should follow:  \\dotnetdocsp\docs\dtsd\projdev\const\dtsd-critical-inspection-earthwork.pdf

- Ensure that all marsh excavation or excavation below sub-grade (EBS) has been inspected, accepted and measured prior to placing any fill material.  In cut sections, evaluate subgrade after rough grading has occurred.  EBS, prior to approval of the grade, is paid as common excavation and the appropriate bid item for the replacement material (from common or borrow)

  - Approve and document portions of the grade that are complete and ready for base course.  If there are any questionable areas Section 205.3.13 of the Standard Specifications allows the engineer to request a loaded truck to help spot yielding areas.

  - If EBS is required after rough grading and approved sub-grade, measure and pay as noted in Section 205.5.2(2) – (3X Common + 1X backfill)- Administrative Item

  - If EBS is required after placement of subbase or base, measure and pay according to Section 301.5(2) – (3X common + 3X backfill material and 3X base)

  - Do not pay for EBS in borrow.

- Document the weather conditions, labor and equipment hours on a daily basis.

# BASE AGGREGATE

- CMM references: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-08-60.pdf and http://roadwaystandards.dot.wi.gov/standards/cmm/cm-08-34.pdf

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-03-00.pdf

- See Special Provisions for additional requirements.

- Ensure quarry has current wear and soundness testing (check with Material Section).

- Check quarry scale.

- Check QMP plan for compliance to specifications (check with Materials section) and QC/QV testing required.

- Make sure grade has been inspected and accepted (see Earthwork Section).

- Monitor lift thickness, moisture content (see CMM 8-60), watering operations, and compaction.

- Collect and process the tickets for each load of material.

- After compacting, inspect for cracking or rutting, and replace any weak areas.

  - If EBS is required after placement of subbase or base, measure and pay according to Section 301.5(2) of the Standard Specifications – (3X common + 3X backfill material and 3X base)

  - Do not pay for EBS in borrow.

- Frequency of inspection:

\\dotnetdocsp\docs\dtsd\projdev\const\dtsd-critical-inspection-base-course.pdf

- Document the weather conditions, labor and equipment hours on a daily basis.

# PIPE CULVERT

- CMM reference: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-05-50.pdf

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-20.pdf#ss520

- See Special Provisions for additional requirements.

- Review staking and/or layout information with contractor and land owners as needed.

- Verify the lengths of culvert pipe required, and develop a pipe list to give to contractor.

- Obtain loading document from contractor and retain with project records.

- Obtain manufacturer’s certification of compliance from contractor and retain with project records.

- Verify that the manufacturer is on the approved list.

- Verify and record condition and markings on pipe.

  - For metal pipes include: Name of manufacturer, specified thickness, specified coating mass, identification symbols related to heat number and coating lot number, and AASHTO designation.

  - For concrete pipes include: Pipe class and designation, date of manufacture, name or trademark of the manufacturer, and identification of plant.

- Inspect the excavation of the foundation, backfilling and compaction to ensure it meets contract specifications.

- Inspect the placement of pipes, joint ties, gaskets, fabric, and anchors.

- Document the weather conditions, labor and equipment hours on a daily basis.

Frequency:

The length, grade and location of a pipe culvert should be verified prior to beginning its placement.  The frequency of inspection for this item should be once or twice per day.  The inspector should verify that the contractor properly places all joints, and properly backfills the pipe culvert.  If there are problems in these areas, the frequency of inspection should be increased.

# STORM SEWER

- CMM references: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-06-15.pdf#cm-6-15 and http://roadwaystandards.dot.wi.gov/standards/cmm/cm-06-20.pdf#cm6-20

- Standard Specifications references:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-07.pdf#ss607 and http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-11.pdf#ss611

- See Special Provisions for additional requirements.

- Review staking locations and make adjustments for any conflicts with utilities or traffic staging.

- Obtain loading document from contractor and retain with project records.

- Obtain manufacturer’s certification of compliance from contractor and retain with project records.

- Verify that the manufacturer is on the approved list.

- Verify and record condition and markings on pipe.

  - For metal pipes include: Name of manufacturer, specified thickness, specified coating mass, identification symbols related to heat number and coating lot number, and AASHTO designation.

  - For concrete pipes include: Pipe class and designation, date of manufacture, name or trademark of the manufacturer, and identification of plant.

- Inspect all connections to ensure system is watertight.

- Inspect the excavation of the foundation, backfilling and compaction to ensure it meets contract specifications.

- Inspect contractor’s operations to ensure safety and check work area at end of day to ensure there are no hazards to the public.

- Inspect the system upon completion to ensure it is cleaned out.

- Document the weather conditions, labor and equipment hours on a daily basis.

- Frequency:   As a milestone, the lines and grades of the storm sewer system should be verified prior to beginning placement.  The frequency of inspection for this item should be once or twice per day during pipe placement.  The inspector should be present when tying into any storm sewer structure to ensure the grades, alignment, and condition of the structure is satisfactory. The inspector should verify that the contractor properly places all joints and properly backfills the storm sewer pipe.  If there are problems in these areas, the frequency of inspection should be increased.  If any utility conflicts are anticipated, inspection should be continuous, and a good diary kept.  The inspector should document daily the labor and equipment used.  An inspection should be made at the end of each working day to ensure that proper drainage and safety will be maintained overnight.

# CONCRETE PAVEMENT

- CMM references: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-04-00toc.pdf#cm4, http://roadwaystandards.dot.wi.gov/standards/cmm/cm-08-70.pdf, and http://roadwaystandards.dot.wi.gov/standards/cmm/cm-08-35.pdf#cm8-35

- Standard Specifications references:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-04-15.pdf#ss415, http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-04-16.pdf#ss416, and http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-01.pdf#ss501

- See Special Provisions for additional requirements.

- Inspect the condition of the base the pavement is being placed upon to ensure it is stable and will not be the cause of premature failure of the pavement.

- Coordinate with the Materials section to ensure that the proper testing is scheduled.

- Verify that the mix design and source of materials has been properly approved.

- Review QMP quality control plan, if required.

- Verify the delivery time of each load meets contract specifications.

- Inspect the contractor’s probing method to ensure the depth of concrete meets contract specifications.

- Test concrete in accordance to QMP verification.

- Make cylinders for strength testing.

- Monitor QMP procedures as outlined in the contractor Q.C. plan

- Ensure contractor is performing probing depth checks and entering them into the MRS system. Department verification is required per Section 415.3.16.6 of the Standard Specifications.  Confirm that thickness meets specs.

- Reject concrete that does not meet the materials specifications.

- Inspect the contractor’s operations when constructing a header or joint.

- Inspect pavement for cracking twice according to Section 415.3.17 and document the findings.

- Crack repair in accordance with CMM 4-24.6.

- Document the weather conditions, labor and equipment hours on a daily basis.

Frequency:

As a milestone, the inspector should verify that the base was inspected and accepted prior to the placement of concrete pavement.  The inspection of concrete pavement should be continuous during concrete placement.  If any forms are used, the forms and steel should be inspected prior to the placement of concrete.  If QMP is a part of the contract, inspection is needed for materials testing assurance.  If the project is non-QMP, the inspector must take the tests at the intervals required by the C&M Manual.

- Additional Guidance:  \\dotnetdocsp\docs\dtsd\projdev\const\dtsd-critical-inspection-pavement-concrete.pdf

# ASPHALT PAVEMENT

- CMM references: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-04-50.pdf#cm4-50, http://roadwaystandards.dot.wi.gov/standards/cmm/cm-08-36.pdf, and http://roadwaystandards.dot.wi.gov/standards/cmm/cm-08-65.pdf#cm8-65

- Standard Specifications references:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-04-50.pdf#ss450, http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-04-55.pdf#ss455, and http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-04-60.pdf#ss460

- See Special Provisions for additional requirements.

- Monitor the operations of the contractor and also monitor the traffic control being utilized to ensure safety.  The inspector also must be aware of his presence around a paving operation and live traffic and ensure his own safety.

- Inspect the condition of the base the pavement is being placed upon to ensure it is stable and will not be the cause of premature failure of the pavement.

- Collect and process the tickets for each load of material.

- Coordinate the QMP testing procedures – Inform the materials lab of paving.

- Inspect and Document:

  - Temperature of the mix

  - Proper lift thickness to meet yield and compaction

  - Compute and track the yield based on weight tickets

  - Proper cross slope, transitions and superelevations

  - Placement of turn lanes, tapers, etc.

  - Matching into manholes, curb and gutter, water valves, etc.

  - No segregation or bleeding of the mix behind the paver

  - The compaction equipment and methods used for compaction to ensure the required density is achieved

- Coordinate with the density tester.

- Ensure that the contractor uses proper methods to construct joints to minimize the potential for bumps. See Standard Specifications Sec. 450.3.2.9 for guidance.

- Document the weather conditions, labor and equipment hours on a daily basis.

Frequency:

As a milestone, the inspector should verify that the base was inspected and accepted prior to the placement of asphaltic pavement.  The frequency of the inspection required is dependent on the complexity of the project.  If the project is placing miles of rural pavement, with nothing to match in the surface, the paving could be inspected periodically throughout the day.  A method must be established to collect weight tickets and monitor the yield of the placement.  The inspector should be present to ensure all tapers, turning lanes, bridge approaches, etc. are properly constructed.  If the project is urban paving or there are manholes, inlets, curb and gutter, complicated intersections, or other complexities, the inspection should be continuous.  The inspector should coordinate with the QMP testing and monitor the density and profilograph results.

# CONCRETE BRIDGES AND CONCRETE MASONRY

- CMM references: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-05-10.pdf#cm-5-10, http://roadwaystandards.dot.wi.gov/standards/cmm/cm-05-15.pdf#cm5-15, http://roadwaystandards.dot.wi.gov/standards/cmm/cm-08-35.pdf, and http://roadwaystandards.dot.wi.gov/standards/cmm/cm-05-25.pdf#cm5-25

- Standard Specifications references:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-01.pdf#ss501 and http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-02.pdf#ss502

- See Special Provisions for additional requirements.

- Obtain and review the signed and sealed falsework plan from the contractor and distribute it to the proper personnel for review.

- Coordinate and conduct the pre-pour meeting using the C&M Manual checklist found in Section 5-15.6.1 or “Pre-Pour Questions” document found in Panty.

- Inspect the dry run, verify steel reinforcement clearances and document.

- Inspect the forms, falsework, and reinforcement prior to the placement of any concrete.

- Ensure that the railings for the finishing machine are properly set up.

- Check expansion devise for proper installation and opening size. See structure plans for guidance.

- Complete “Elastomeric Expansion Device Installation Data” form, located in Pantry Statewide Forms folder, and distribute to Bureau of Structures, Regional Bridge Section, and obtain copy for project files.

- Verify that the mix design and source of materials has been properly approved.

- Check evaporation rates for deck pours shown in Figure 1 of the CMM Section 5-25.

- Ensure that the proper curing method is applied in accordance with the contract specifications.

- Verify the delivery time of each load meets contract specifications.

- Coordinate QMP testing.

- Test the air content of the concrete.

- Make cylinders for strength testing.

- Reject concrete that does not meet the materials specifications.

- Contact the region bridge engineer for final inspection prior to contractor leaving site.

- Complete applicable bridge vertical and horizontal clearance forms located in Pantry Statewide Forms folder and submit completed form to Regional Bridge Section.

- Document the weather conditions, labor and equipment hours on a daily basis.

Frequency:

The frequency of inspection of concrete bridges varies with the stage of construction of the bridge. While the contractors are forming and placing steel, the inspector should document the labor and equipment, continuous inspection of these activities is not required. As a milestone, all forms, falsework, and steel reinforcement should be inspected and approved prior to the placement of concrete. Inspection should be continuous any time concrete is being placed. After pouring concrete, the bridge should be inspected at least once per day to ensure the proper curing methods are used. Another milestone for concrete bridges should be that the substructure lines and grades should be verified before the placement of any superstructure members.

# STEEL BRIDGES

- CMM reference:  http://roadwaystandards.dot.wi.gov/standards/cmm/cm-05-20.pdf

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-06.pdf#ss506

- See Special Provisions for additional requirements.

- Verify that all requirements have been met for the shop inspection for steel members. Acceptance of structural steel members is on the basis of a shop inspection report (EB-20).

- Verify that all beam seats are at the correct elevation and alignment prior to beam placement.

- Inspect the beams upon delivery for correct camber, length, alignment, and coating.

- Inspect the contractor’s operations to ensure the members are correctly placed.

- Ensure that the diaphragms are correctly installed.

- Inspect all welds – certified welder and contractor inspector to fill out DT2320.

- Check all stud connection welds to verify their adequacy.

- Properly check the torque on all bolts.

- Complete the form “Rotational Capacity Test/Record” located in Panty and provide a copy of the completed form to the regional bridge section.

- Document the weather conditions, labor and equipment hours on a daily basis.

Frequency:

As a milestone, the inspector should verify the lines and grades of the substructure units prior to the placement of the members. The frequency of inspection of steel members should be inspected upon delivery, and inspected upon the completion of the placement of the members. The inspector also must obtain the required reports that verify the members were acceptably inspected during their fabrication and verify that the members delivered to the project correspond to the reports. The inspector needs to document the labor and equipment used to place the members. Welded studs and bolts should be inspected upon completion to verify the welds are acceptable and the bolts are properly tightened.

# PILING

- CMM reference:  http://roadwaystandards.dot.wi.gov/standards/cmm/cm-05-40.pdf

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-50.pdf#ss550

- See Special Provisions for additional requirements.

- Obtain the correct hammer bearing/blow count chart from the Pantry folder.

- Obtain completed form DT3550 “Pile Driving System” located in Pantry Statewide Forms folder from the contractor.

- Identify, measure, and document each original pile length.

- Inspect the layout and batter of the piling.

- Determine the bearing of piling by observing and documenting hammer fall, blow count, and

movement of the piling.  Document each pile in form DT1315 “Piling Record” and document 1st pile in each substructure unit in form DT1924 “Pile Driving Data.”  Forms are located in Panty Statewide Forms folder.  Submit copies of completed forms to Bureau of Structures, Regional Bridge Section and retain copy in the project file.

- Ensure the piling is driven to any minimum plan lengths.

- Inspect the splices – certified welder and contractor inspector to fill out DT2320.

- Obtain any samples required for testing.

- Measure cutoff lengths, determine pay length, and measure the area of sheet piling.

- Document the weather conditions, labor and equipment hours on a daily basis.

Frequency:

The frequency of inspection for piling should be a continuous inspection. It is critical to verify that the correct bearing and length are attained. Since it is uncertain when it will occur, continuous inspection and documentation is required.

# STRUCTURES (GENERAL)

- CMM reference: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-05-45.pdf#cm5-45

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-13.pdf#ss513 (Railing), http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-05.pdf#ss5-5 (Rebar), and http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-14.pdf#ss514 (Floor Drains)

- See Special Provisions for additional requirements.

- Verify that all requirements have been met for the shop inspection for steel members. Acceptance of structural steel members is on the basis of a shop inspection report (EB-20).

- Inspect the adequacy of all welds and ensure anchor bolts are the proper length.

- Verify the locations of all floor drains and down spouts.

- Document the weather conditions, labor and equipment hours on a daily basis.

- Rebar:

  - Record heat numbers of reinforcement delivered to project and verify they correlate to test reports and analysis.

  - Inspect the size, spacing, and clearance of all reinforcement to ensure they meet the plan requirements.

  - Inspect all splices to ensure they meet contract requirements.

  - Ensure any damaged coating is repaired.

Frequency:

As a milestone, it should be verified that all curing requirements have been met to allow any loading to install any of these items.  The drainage of the structure should also be checked to ensure the placement of any drainage items is correct.  The frequency of inspection of these items can then be inspected upon completion.  The frequency of inspection of steel reinforcement should be to verify, prior to placement, that the steel on the project corresponds to the test reports and analysis, then it should be inspected when its placement is completed.  If steel framework is put together, then covered by forms, the inspection needs to be done before the steel is covered.  The inspector needs to document the labor and equipment used daily in the placement of the steel.

# ANCILLARY STRUCTURES

- CMM reference:  http://roadwaystandards.dot.wi.gov/standards/cmm/cm-05-70.pdf#cm5-70

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-41.pdf#ss641, http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-60.pdf, http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-57.pdf, and http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-06.pdf#ss5-6 (bolts)

- See Special Provisions for additional requirements.

- Coordinate with sign inspection consultant to have initial inspection of sign structure completed prior to end of construction, but after completion of all sign structures.  Contact regional bridge section to obtain consultant’s contact information.

- Bolts (forms needed per lot per size):

  - Supplier Rotational Capacity Test/Record paperwok

  - DT2113 Rotational Capacity Test/Record

  - Send 2 bolts, 3 nuts, 3 washers to Tom Brokaw (608) 246-7934

- Installation (forms needed per base)

  - DT2321 High Strength Steel Anchor Rod Installation Tensioning Record After Installation

- Structure (forms needed per structure, if applicable) – Vertical clearance forms located in Pantry Statewide Forms.

  - Sign Bridge Vertical Clearance

  - Sign Structure Vertical Clearance

- Document the weather conditions, labor and equipment hours on a daily basis.

# Note: Please provide a copy of the completed forms to the regional bridge section.

Frequency: As a milestone, the inspector should verify the lines and grades of the substructure units prior to the placement of the members. The frequency of inspection of steel members should be inspected upon delivery, and inspected upon the completion of the placement of the members. The inspector also must obtain the required reports that verify the members were acceptably inspected during their fabrication and verify that the members delivered to the project correspond to the reports. The inspector needs to document the labor and equipment used to place the members. Welded studs and bolts should be inspected upon completion to verify the welds are acceptable and the bolts are properly tightened.

# BOX CULVERTS, RETAINING WALLS, AND ENDWALLS

- CMM reference: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-05-60.pdf#cm-5-60 and http://roadwaystandards.dot.wi.gov/standards/cmm/cm-05-10.pdf

- Standard Specifications reference:  (also see bid item)  http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-04.pdf#ss504, http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-05.pdf#ss505, and http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-01.pdf#ss501

- See Special Provisions for additional requirements.

- Review specifications, special provisions, plan and miscellaneous quantities for each item.

- Inspect the foundation and ensure it meets contract requirements.

- Inspect the forms, falsework, and reinforcement prior to any concrete pour.

- Verify that the mix design, source of materials, and QMP has been properly approved and is being followed.

- Ensure that the proper curing method is applied in accordance with the contract specifications.

- Verify the delivery time of each load meets contract specifications.

- Verification tests are taken in accordance with QMP provisions.

- Reject concrete that does not meet the materials specifications.

- Document the weather conditions, labor and equipment hours on a daily basis.

Frequency:

The frequency of inspection for box culverts, retaining walls, and endwalls is similar to concrete bridges.  The frequency of inspection varies with the stage of construction of the structure.  While the contractors are forming and placing steel, the inspector should document the labor and equipment, continuous inspection of these activities is not required.  As a milestone, all forms, falsework, and steel reinforcement should be inspected and approved prior to the placement of concrete.  Inspection should be continuous any time concrete is being placed.  After pouring concrete, the bridge should be inspected at least once per day to ensure the proper curing methods are used.

# ANCILLARY CONCRETE

- CMM reference: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-06-10.pdf (curb and gutter), http://roadwaystandards.dot.wi.gov/standards/cmm/cm-05-10.pdf#cm5-10 (concrete masonry), and http://roadwaystandards.dot.wi.gov/standards/cmm/cm-04-24.pdf#cm4-24.7 (ancillary concrete)

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-05-01.pdf#ss501

- See Special Provisions for additional requirements.

- Review specifications, special provisions, plan, and miscellaneous quantities for these items.

- Verify the alignment and drainage meet plan requirements.

- Verify that the mix design, source of materials, and QMP has been properly approved.

- Verify the delivery time of each load meets contract specifications.

- Test concrete according to QMP specifications.

- Reject concrete that does not meet the materials specifications.

- Inspect the placement of joints.

- Crack repair in accordance to CMM 4.24.7.

- Document the weather conditions, labor and equipment hours on a daily basis.

Frequency:

The frequency of inspection for incidental concrete should be continuous while concrete is being placed.

# PAVEMENT MARKING

- CMM reference: http://roadwaystandards.dot.wi.gov/standards/cmm/cm-06-50.pdf

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-46.pdf#ss646

- See Special Provisions for additional requirements.

- Verify that the no passing zones are properly located. Retain records for final documents.

- Inspect the surface to be marked to ensure it is clean and adequately prepared.

- Ensure the contractor uses appropriate traffic control for painting operations.

- Document the weather conditions, labor and equipment hours on a daily basis.

Frequency:

As a milestone for inspection for pavement marking, the surface to be painted should be inspected to ensure it is clean and the marking is correctly laid out.  After that, the most that can be done is an inspection upon completion.

# LANDSCAPING

- CMM reference : http://roadwaystandards.dot.wi.gov/standards/cmm/cm-06-40.pdf

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-25.pdf#ss625 (topsoil), http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-27.pdf#ss627 (mulching), http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-30.pdf#ss630 (seeding), http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-31.pdf#ss631 (sodding), and http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-28.pdf#ss628 (erosion control)

- See Special Provisions for additional requirements.

- Collect seed tickets, bags, or scale tickets and verify that seed and fertilizer meet contract requirements.

- If necessary, test the topsoil to determine if it is adequate.

- Verify layout and preparation prior to planting or seeding.

- Make inspections prior to proving period elapsing.

- Document the weather conditions, labor, and equipment hours on a daily basis.

Frequency:

The frequency of inspection for landscaping items should be once per day.  The inspector needs to document the labor and equipment used.  As a milestone to landscaping, the layout should be checked before doing any planting.  Also as a milestone, any topsoil should be inspected and accepted before seeding or placing sod.  After any planting, the inspector must ensure that the correct amount of watering is done.

# ELECTRICAL

- CMM reference:  http://roadwaystandards.dot.wi.gov/standards/cmm/cm-06-55.pdf#cm6-55

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-51.pdf#ss651

- Also see Sections 652-660.

- See Special Provisions for additional requirements.

- Document the weather conditions, labor and equipment hours on a daily basis.

- Coordinate with the regional electrical unit and submit materials for approval prior to use and to assist in inspection and to be present for final acceptance.

- Ensure that the electrical workers meet the contract requirements for journey classification or apprenticeship.

- Verify that all materials are from the approved list and/or are UL inspected.

- Inspect conduit and pull box placement in accordance to the checklist shown in Figure 1 in Section 6-55 of the C&M Manual.

- Inspect lighting installation, traffic signal installation, and loop detector installation using the checklists in Figures 2-4 in Section 6-55 of the C&M Manual.

Frequency:

The materials used in electrical installations need to be approved prior to incorporating them into the project.  Many applications are buried and need to be inspected as they are constructed.  All conduit runs should be inspected after completion to ensure they are open.  A member of the regional electrical unit should be present to perform a final acceptance inspection.

# MATERIALS

- CMM reference:  http://roadwaystandards.dot.wi.gov/standards/cmm/cm-08-00toc.pdf

- Standard Specifications reference:  (also see bid item)  http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-01-06.pdf#ss106

- See Special Provisions for additional requirements.

- Ensure the Source of Materials has been reviewed by the Materials section and has been approved.

- Obtain Materials Testing E-Guide from the MRS site and/or Materials section.

- Obtain samples and certifications and perform testing required per the Materials Testing Guideline and the Standard Specifications.

- Ensure prequalified items are on approved list or PAL. http://www.atwoodsystems.com/materials/default.htm

- Review the QMP plan(s) submitted by the contractor.

- Coordinate with the materials section to ensure that all assurance or verification testing is completed in accordance with the contract.

- Inform the Materials Section of the timelines that will be used for paving and bridge deck pours.

- Review QMP test results for compliance with the contract.

- Review material certifications for conformity to specifications prior to installation.  Initial each certification to verify it conforms to specifications.

- Keep materials diary, binder, and MIT up to date during construction.

- Notify PM and Materials Section of non conforming materials.  In some cases materials can remain in place per Section 106.5 of the Standard Specifications.  Also see CMM 8-10.6 for price reduction guidelines.

- Document the labor and equipment hours on a daily basis.

# INCIDENTAL CONSTRUCTION

- CMM reference:  http://roadwaystandards.dot.wi.gov/standards/cmm/cm-06-00toc.pdf

- Standard Specifications reference:  (also see bid item) http://roadwaystandards.dot.wi.gov/standards/stndspec/ss-06-00.pdf

- See Special Provisions for additional requirements.

- Ensure construction conforms to contract provisions.

- Document the weather conditions, labor and equipment hours on a daily basis.

- The frequency of inspection should be enough in the beginning of the operations so that the inspector is satisfied that the contractor’s equipment, materials. and methods.  Once the inspector is satisfied with the contractor’s operations, the frequency of inspection can be reduced.