Pre-Construction Conference Agenda

Project I.D.

Date, Time, & Location:

Contractor:  					 	Project Est. Cost:

Project Supervisor:

Project Manager:

Project Leader:

Contract Executed:	 	Let:			Completion Date:

Standard Specifications:

INTRODUCTIONS

Purpose –

Distribute attendance Roster

Have all parties introduce themselves

GENERAL PROJECT INFORMATION

- Work Involved –

- Project ID/ Federal ID :

- Contract Cost:

- Anticipated Start Date:

- Project Completion Date:

PROJECT PERSONNEL

- DOT –WDOT Supervisor

- DOT – WDOT Project Manager

- Project Leader –

- Contractor Representative –

- Proposed Subcontractors

- Proposed Suppliers

- Sublet Approved Date :

- Line of Communication: WDOT - Prime Contractor – Subcontractors

Progress Meetings

- Held Weekly

- Location and time:

- Expected Attendance is Prime contractor and all subcontractors that will be involved in the next week’s work.

- Contractor to update schedule and provide 2-week look ahead.

Public Relations

- The contractor shall arrange and conduct a meeting between the contractor, department, local officials and business people to discuss the project schedule of operations prior to the start of work under this contract and two meetings per month thereafter.

- Date of First Meeting:

Contract Administration

- RFI Process – email is best for exchanging the form

- Addenda –

- Field Office

Location:

Phone:

Fax:

- Claims Process

-If you feel a claim or change order is due:

- Discuss the item immediately with the Project Engineer, PRIOR TO DOING THE WORK

- Have supporting documents that show the need for a change order and a possible solution.

- CCO Policy

– If you feel a change order is due discuss the item immediately with the project engineer, prior to doing the work

– Have supporting documents that show the need for a change order and a possible solution.

– If the concept of a change order is agreed to have a price break down for the work included in the change order submittal

REQUIRED SUBMISSIONS

Required		Submitted

- Schedule of Operations

- Archaeological Clearances

- Source of Materials Report

- Erosion Control Plan

- Request to Sublet

- Railroad Insurance

- Shop Drawings

- Necessary arch survey

(borrow sites, waste sites, staging sites)

CONSTRUCTION WORK SCHEDULE

Notice to Proceed Procedures – all submittals must be submitted and reviewed or approved prior to the Start Notice being sent.

Estimated date when the start notice will be sent:

Coordination with other projects:

Railroad Coordination – Insurance submitted date:

Contractors Work Schedule

-Plan of work operations,

- Anticipated start date

-Hours of operation, local ordinances

UTILITIES – Project does come under the provisions of Trans 220

Railroad Requirements and Coordination,

TRAFFIC CONTROL

- Traffic Requirements

- Holiday work restrictions

- Lane Closures, notification for LCS system

- Traffic Control Responsibility

  - Name

  - Phone

  - 24 hour number

.

ENVIRONMENTAL CONSIDERATIONS

- Erosion Control Implementation Plan submitted__________      Approved___________

- Materials cannot be stored, and equipment cannot be operated within any wetlands found during the project.

- Sites beyond the right of way that are proposed for borrow sites, batch plant sites, waste sites, or staging areas for this project are required to have an evaluation for archaeological significance.

- Re-topsoil, seed, fertilize and mulch graded areas within 7 working days after grading is completed.

- Submit amendments to the ECIP

MATERIALS

- Sources and locations

- Base Course:

- Concrete Aggregates:

- Asphalt

- Concrete Masonry

- Material Certification Process – HTCP certified testers are required

- QMP plans will be submitted?

- The Department does not want non-conforming materials incorporated into the work

- Pre-pour meeting is required before concrete work begins

- Pre-pave meeting is required before HMA work begins

- Remaining Required Submittals –

- QC data is subject to L.A.B. audits, it is imperative that all QC testing and documentation are completed, as required.  Faulty documentation is equivalent to not testing.

DETOURS AND HAUL ROADS

- Haul Roads – Identification of routes in writing

- Log haul routes with the following present:

- Other Comments -

SURVEY –

LABOR COMPLIANCE -

- Project posters are to be in place when the job starts and be in a location at the job site where workers can readily see them. The prime contractor’s signed EEO policy statement must be posted.

- Make sure that payroll submittals are timely and correct.  Any apprentice hours should be highlighted.

- Other comments -

REAL ESTATE COMMITMENTS/ Right of Way Issues

PROJECT ACCEPTANCE AND FINALS PROCESS

SAFETY

Flaggers shall be in sight of each other or in direct communication at all times.

Contractor’s Safety Plan?

OTHER -

- Superintendent on Job –

- Any remaining comments/questions