REGIONAL OFFICE REVIEW OF CONSTRCUTION PROJECT RECORDS
INSTRUCTIONS (Used by WisDOT PM or Finals review team)

- The number of items to review is based on the following contract dollar amount:

| Original Contract Dollar Amount | Number of Items to check |
| --- | --- |
| <$500,000 | 3-4 items |
| $500,000 - $1,000,000 | 4-5 items |
| $1,000,000 - $2,000,000 | 5-6 items |
| $2,000,000 - $5,000,000 | 6-7 items |
| $5,000,000 - $10,000,000 | 7-8 items |
| >$10,000,000 | 8-9 items |

NOTE: IF MULTIPLE ERRORS ARE FOUND IN ITEMS- INCREASE THE NUMBER OF ITEMS TO BE CHECKED TO 9.  IF YOU STILL ARE NOT COMFORTABLE WITH THE ACCURACY, CONTACT YOUR SUPERVISOR.

- Basis of Selection (which items to choose)

  - DO NOT select Lump Sum type items i.e. mobilization

  - Choose at least 1 high dollar item (Basis B)  Use the contract type to choose, for example a bridge project choose concrete masonry,  a concrete paving project, choose concrete pavement, etc.

  - Use Explanation of Variation in Project Tracking to choose items with large quantity deviations (Basis D). If you don’t have a log in ID contact the help desk.

    - \\Mad31zp1\n3public\Region\Project Tracking\TRACKING.EXE

    - Select <Project Track> button

    - Select down arrow next to “Contract ID” to get project ID

    - Enter project ID with dashes

    - Highlight project

    - Select “Field Reports”

    - Select down arrow and select “Explanation of Variation”

    - Select <View> button

    - The far right column shows a percentage of over/ under run

  - If the contract has several similar items, select one to review (Basis F).

  - If you are familiar with  past recurrent problems –  choose Basis D

  - For the remaining items use Basis G – Random Selection.

- Depth of Review

  - At least two items should be checked under “R” Operations I thought Q.

  - On projects that have multiple categories with the same item in multiple categories, review one item under “Q” Correct Cost Distribution.

  - Use the outcome of “a.” to decide the remaining depth of review. If there was an issue with any of the reviews “I-Q” check additional items with the corresponding Depth of Review that was an issue.  You can randomly select the remaining depth of review

Pantry20XX\RegSpec\SWR\Mad\RegionalReviewInstructions.docx                                Contact:  Kelly Addison/Teri Schopp2/24/14ka