Wisconsin Department of Transportation

Construction Progress Meeting

Agenda for (Month Day, Year)

| Project ID |  |
| --- | --- |
| Project Name |  |
| Location |  |
| Project Leader |  |

Attendees:

# Review Previous Progress Meeting Notes

# Outstanding Issues

- Work in Progress

- Prime Contractor

- Work completed last week

- Work scheduled for next week

- Work scheduled for the following week

- Subcontractor

- Work completed last week

- Work scheduled for next week

- Work scheduled for the following week

- Progress Schedule

- Current Schedule Update

- Critical Path/Controlling Items of Work Activities

- Current Completion Date

- Next Schedule Update

- Critical Delays (work on critical path or controlling item)

- Delays since last meeting?

- Current Delays

- Excusable

- Non-Excusable

- Potential Delays

- Excusable

- Non-Excusable

- Non-Critical Delays (work NOT on critical path or a controlling item)

- Delays since last meeting?

- Current Delays

- Potential Delays

- Utilities

- Maintenance of Traffic

- Upcoming closures

- Modifications to traffic control

- Other

- Materials

- QMP Materials Testing

- Non-QMP Testing

- Deficient Materials

- Plan/Shop Inspections

- Environmental

- Regulatory Permits

- Erosion Control

- Other

- Submittals

- Under Review

- To Be Submitted

- Request for Information (RFI’s)

- Outstanding RFI’s

- Upcoming RFI’s

- Contract Modification Status

- Dispute Resolution

- Current Disputes

- Stage of dispute resolution process

- Potential Disputes

- Claims

- Current

- Potential

- Completed Items & Agreement on Final Quantities

- Progress Estimate

- Safety

A. Work site safety

B. Work Zone safety

C. Emergency Incidents

- Public Relations

- EEO/Prevailing Wage

- DBE Commitment Status/Update

- ASP 7 Requirements

  - Prime needs to enter payment into CRCS and sub need to confirm payment.

  - All DBE payment no matter the Tier of subcontractor needs to be entered in CRCS.

- ASP 4 Requirements

  - Have subcontractors been getting paid in a timely manner?

- Finals Process

- New Issues

- Next Meeting

- Date

- Time

- Location