## Slide 1: Real Estate Process
Utilities Conference 2018

## Slide 2: Timeline
Minimum of 10 to 12 months for smaller projects
< 24 parcels
Transitioning to 24/7 timeline
Assumes:
No relocations
No complex acquisitions
No billboards
No parks, cemeteries, LAWCON property
No design/plat or ownership changes

## Slide 3: Flow Chart

## Slide 4: Key Steps
Preparation Work:
Title reviews
Plat reviews
Project entered into READS
PCA prepared & approved
Project Data Book prepared & approved
Appraisers & Reviewers hired or assigned
Start up meeting(s) conducted

## Slide 5: Key Steps
Acquisition Starting Point:
DSR approved
TPP/Plat is recorded
Funds are encumbered (PCA)
Introduction/Staking/Appraisal letters to owners
Staking photos taken
Appraisals prepared/reviewed/approved
NPPR prepared/reviewed/approved

## Slide 6: Key Steps
Finally…the Initiation of Negotiation (ION):
Meet with each Owner/Parties of Interest.
Review project, Owner’s Rights, appraisal or nominal offer, plat and profile, possibly walk property and answer questions.
Owner has 60 days to obtain and deliver own appraisal at DOT cost.

## Slide 7: Key Steps
The Negotiation:
Review appraisals, make offer to owner.
Owner accepts or counters offer.
If revising DOT offer, prepare Administrative Revision and present new offer.
Continue this process until agreement or deadlocked
Process can take several weeks or months depending on issues and $$ differences.

## Slide 8: Key Steps
If Agreement…
Purchase Agreement and/or Warranty Deed is signed by all parties of interest.
If a mortgage, obtain Partial Release from bank. (Timeline and success varies.)
Submit payment request to CO.
Obtain compensation check and close transaction.
- Deliver payment and record deed

## Slide 9: Key Steps
If no Agreement by all Parties…
Update title report
Issue a JO with final offer
Owner(s) have 20 days to accept JO
If accept JO, follow Agreement process.
If JO not accepted,
Order Award of Damages check
Send Award to Clerk of Courts naming all Parties of Interest
Record Award to conclude acquisition

## Slide 10: Common Procedural Issues…
Unknown owner Unresponsive owner
Change in ownership Incorrect title info
Judgements/Liens Amended plat
Marriage/Divorce Death of owner
Partial Releases Property sale or lease
Refinancing Out of town/country
Incorrect signatures Not notarized
Attorney involved Incomplete appraisal
Overly protective family member

## Slide 11: Common Valuation Issues…
Land, Landscaping, and Improvement Values
TLE Rate
Severance Damage - parcel size, configuration, proximity, visibility, access, grade change
Cost to Cure
Billboards/On-Premise Signs
Parking/Internal Circuity
Encroachments
Site Contamination

## Slide 12: Commitments to Owners
Statement to Construction Engineer (STCE)
Describes commitments made to owners during negotiation period.
Signed by Owner, if possible, and Proj. Mgr. or RE Agent even if no commitments made.
Saved on DOT P:drive so available to others.
RE needs to reinforce this process to assure commitments are available to utilities.

## Slide 13: Case Study - Texas Road House
Background:
Parcel - 1.96 ac fully developed with building, parking, drainage area
Fee Taking - .084 ac
17 parking stalls
Critical for business
Parking compliance violation?
Replacement parking – where?

## Slide 14: Case Study - Texas Road House
Proposed Solution:
Construct new parking at drainage area
Convey R/W land to TRH for new drainage
Cost to cure - new parking and drainage
Benefit: Eliminates extensive damages of possible total taking

## Slide 15: Case Study – Texas Road House

## Slide 16: Case Study – Texas Road House

## Slide 17: Case Study – Texas Road House

## Slide 18: Case Study – Texas Road House
Issues we encountered:
Engineering analysis - parking and drainage
Does solution even work?
Cost to engineer & construct
Conveyance of R/W land
Unclear title. Who is the Owner?
Land donation
Vacation of Street Easement by C of J
Required PC & CC meeting

## Slide 19: Case Study – Texas Road House
Issues we encountered:
Can we JO if conveying land?
Timing of ATC work
Construction Permit from TRH to ATC
Bi-Lateral Easement Amendment
QC deeds
BMO to DOT
C of J to DOT
Corrective Deed from C of J to DOT
DOT to TRH

## Slide 20: Case Study – Texas Road House
Who was involved…
Owner:
Two Attorneys Engineers
Appraiser Title Company
DOT:
Proj Des Mgr KL Engineers
OGC Proj Atty Appraiser
3 RE Agents RE Supervisor

## Slide 21: Case Study – Texas Road House
Who was involved, continued…
City of Janesville:
City Administrator City Attorney
Public Works Director City Council
Plan Commission
Land Developer
BMO Harris Bank

## Slide 22: Conclusion
Texas Road House was just one of 32 parcel acquisitions for this project.
23 months from ION to closing to acquire this site. (1/11/16 to 12/21/17)

## Slide 23: Comments and Questions