## Slide 1: Railroad Coordination During Construction
Ryan Arnold
TSS Supervisor
North Central Region Construction Conference
Northcentral Technical College Auditorium
February 19, 2020

## Slide 2: Project Construction Leader (PCL) (or designated staff) Coordination
Meet with the RRC prior to pre-con to discuss status of railroad coordination and standards.
Keep RRC updated on railroad items, such as schedule, flagger, any contractor issues, utilities that affect the railroads work.
Weekly meetings may be necessary.
Railroad work is funded by the projects and is part of the project even though the work is being done by the railroad (similar to a subcontractor)

## Slide 3: Project Construction Leader Utility Coordination
Utilities should be relocated to ensure that they are not in conflict with the railroad signals, bungalow, etc.
Utility relocations may be concurrent with construction and may need to be coordinated with the railroad work.
Field coordinate with utility companies to ensure that there are no conflicts to the railroads work.

## Slide 4: Railroad Insurance (RPLI)
Railroad Protective Liability Insurance
Do NOT issue the Start Notice prior to the railroad insurance being approved by the railroad.
(Standard Provisions 107.17.3(6))
Ensure that if the construction project carries over to the following year that the railroad insurance is renewed before issuing the resume notice.
If the railroad insurance expires during the construction project it must be renewed.

## Slide 5: Schedule
Contractor’s Construction Schedule
Invite the railroad to the Pre-construction meeting. Give ample notice to the railroad (14 days preferred).
Contractor inform the railroad, RRC and PM/PL of current construction schedule and any changes to the schedule that affect the railroad work.
Contractor should be in contact with the railroad to ensure the contractor and railroad schedules coincide.

## Slide 6: Contractor Submittals
Contractor’s Construction Schedule
Submit required documents to the railroad allowing enough time for review, objections and changes.
  Shop Drawings
  Shoring Plans/Excavation Plan (Roadway/Pipes)
  Structure Plans/Erection Plan
  Debris Containment
  Communication Plan
Each railroad has their own timeline and requirements for submittals. It’s the contractors responsibility to contact the RR representative to ensure the contractor knows these requirements.

## Slide 7: Railroad Permits
Additional Information Needed
Contractor may be required to supply additional information to the railroad to complete the permit process prior to the railroad allowing the flagger to be scheduled and for the work to proceed.
  Permits to construct items such as culverts, storm sewer, sanitary sewer, water, electric, etc.

## Slide 8: Railroad Flaggers
PCL Responsibilities
Know the Railroad’s flagging requirements.
If the contractor doesn’t abide by the Railroad’s flagging requirements
  Remove the contractor from the Railroad’s property or completely shut the project down (CMM 2-25.3.3)
  Immediate communication with the RRC is necessary

## Slide 9: Railroad Flaggers
PCL Responsibilities
PCL keep record of railroad flagger(s) on site for billing purposes if STSP 107-034 is in the Special Provisions
  Dates
  Time
  Staff (number of & names)
  When requested and cancelled
    Date & Time
This documentation may be needed if there are any disputes regarding the flagging invoice.
PCL review flagging invoice with RRC before submitting payment.

## Slide 10: Railroad Flaggers
Know the Railroad’s
Flagging Requirements
Contractor communication is critical to understand when to clear the tracks, this allows the train to come through at timetable speed. The contractor will need to gain the flagman’s trust. (How long does it take that contractor to clear the track).
Some railroads contract out the flagging work, this may require the contractor to give a 45-day notice if a flagger is needed for more than 30 days. It’s important for contractor to know the railroads flagging guidelines.

## Slide 11: Railroad Flaggers
Know the Railroad’s
Flagging Requirements
Give minimum 24-hour notice if cancelling the railroad flagger otherwise will be charged for flagger.
Cranes require flagging when the boom length measured toward the track is closer than 25’.
(flagging see CMM 2-58.3.3)
Flagging is needed until the forms are stripped from the parapets .

## Slide 12: Railroad Flaggers
Know the Railroad’s
Flagging Requirements
Flaggers can’t extend the work block beyond what is requested by the contractor.
Ensure that enough time is requested or the flagger will be required to leave and construction near the railroad will halt.

## Slide 13: Call Before You Dig
Each RR has their own CBYD number
Railroads are NOT part of Digges Hotline. See the RR STSP for Railroad Call Before Your Dig number.

## Slide 14: Contractor Orientation/E-Rail Safe
If Required per RR STSP
Contractor Orientation/E-Rail Safe training and badges are required for all contractor staff and subcontractors that will be working on RR R/W.
WisDOT staff is not required, nor can WisDOT staff take the Contractor Orientation/E-Rail Safe training due to indemnification language in the training.
Consultants working for WisDOT are not required to take the training but can if they choose to.

## Slide 15: Personal Protective Equipment
PPE’s
Ensure that ALL PPE’s are worn when working on railroad right-of-way.
  Hard Hat
  Safety Vest
  Steel Toe Boots
  Safety Glasses
  Hearing Protection (train horns 120 decimals)
Railroad will remove you from their property if not worn.

## Slide 16: Construction Safety Near Railroad
Mistakes Can Be Deadly
Railroad may shut the project down if rules are not followed, if this happens PCL shall contact the RRC immediately.
    Anna Davey – 715-392-7960
    Jared Kinziger – 920-492-7713

## Slide 17: Survey and Inspection
During Construction
Staking and inspecting (by project staff) needed to ensure proper locations and elevations of railroad signal and crossing surface.
If the railroad installs the signals or crossing surface in the wrong location or elevation, it may require extending closures, delays and cost to the project.
It is better to ensure that it is done correctly the first time than trying to get the railroad to come back to reinstall it.

## Slide 18: Paving
Paving Up To Crossing Surface
Utilize the SDD(s) and plan .
Prior to paving, discuss specific paving requirements with the RRC.

## Slide 19: Plan Changes
Involving the Area Near the Railroad
Do not make changes in the field to the center median, sidewalk etc. at or near an at-grade railroad crossing without consulting with the RRC first.

## Slide 20: Access Issues
Involving the Area Near the Railroad
Ensure the railroad has access to the work area and room to work.
  Example, a paving contractor place stakes in the same location that the railroad needed to excavate to place railroad signals. This delayed the railroad about ½ a day which cost WisDOT approximately $4,000.

## Slide 21: Drainage and Restoration
Railroad Property
Leave it better than when you got there. Can’t negatively affect railroad property.
Keep the area near the railroad clear of debris and piles.
Ensure that NO fine graded material (sand/topsoil) get place on top of the ballast or railroad ditches. This include through erosion. Keep the railroad flangeways clean.

## Slide 22: Any Questions or Issues
During Construction
Contact the RRC
  If you can’t get in contact with the RRC responsible for railroad coordination on a project please leave a message and contact the other RRC if it cannot wait for a response back.
Anna Davey – 715-392-7960
Jared Kinziger – 920-492-7713