## Program
Wisconsin Department of Transportation |  |  |  |  | Today: | 2026-07-28 09:52
Conceptual Cost Estimate SUMMARY Version 2.0 | Project I.D. | 1130-31-00 |  |  |  |  | Insert
| Highway | US 41 |  |  |  |  | CY
| Project Title | US 41 Expansion (Winnebago, Outagamie, and Brown Counties) |  |  |  |  | EACH
| Project Limits | Segment 7: CTH U Interchange |  |  |  |  | LF
| Project Type |  | Topography |  |  |  | SF
| Project Duration | Multi | Soil Type |  |  |  | STA
| Current Year | 2013 | Start Construction | 2018 |  |  | SY
| Start Preliminary Design | 2015 | End Construction | 2023 |  |  | TON
Project Scope | Alternative #: | Planning Study
Project Assumptions
ITEM DESCRIPTION | UNIT | QUANTITY | UNIT PRICE | Total | NOTES
MAJOR ROADWAY ITEMS | Bid Express Inst. | Estimator Inst.
Removing Pavement (see PAVEMENT tab) | SY | 10100 | 4 | 40000
Barrier Wall (see PAVEMENT tab) | LF | 0 | 50 | 0
Curb & Gutter (see PAVEMENT tab) | LF | 2500 | 13 | 33000
Earthwork
Common | CY | 17533.3333 | 8 | 140000
Marsh | Insert | 0 | 0 | 0
Rock | Insert | 0 | 0 | 0
Borrow | Insert | 0 | 0 | 0
EBS | Insert | 0 | 0 | 0
Signalized Intersections | Insert | 0 | 0 | 0
Pavement (see PAVEMENT tab)
Mainline | SY | 0 | 38 | 0
System Ramps (Concrete) | SY | 0 | 38 | 0
Service Ramps | SY | 6600 | 38 | 251000
Cross Road | SY | 7000 | 38 | 266000
Frontage Roads (Concrete) | SY | 0 | 32 | 0
Local Roads | Insert | 0 | 0 | 0
Mainline Shoulders (Concrete) | SY | 0 | 38 | 0
Ramp Shoulders (Concrete) | SY | 3600 | 38 | 137000
Base (see PAVEMENT tab)
Mainline | SY | 0 | 4 | 0
System Ramps | SY | 0 | 4 | 0
Service Ramps | SY | 6600 | 4 | 26000
Cross Road | SY | 7000 | 4 | 28000
Frontage Roads (Concrete) | SY | 0 | 4 | 0
Local Roads | Insert | 0 | 0 | 0
Mainline Shoulders (Concrete) | SY | 0 | 4 | 0
Ramp Shoulders (Concrete) | SY | 3600 | 4 | 14000
Subbase (see PAVEMENT tab)
Mainline | SY | 0 | 8 | 0
System Ramps | SY | 0 | 8 | 0
Service Ramps | SY | 6600 | 8 | 53000
Cross Road | Insert | 0 | 0 | 0
Frontage Roads (Concrete) | SY | 0 | 6 | 0
Local Roads | Insert | 0 | 0 | 0
Mainline Shoulders (Concrete) | SY | 0 | 8 | 0
Ramp Shoulders (Concrete) | SY | 3600 | 8 | 29000
Major Roadway Subtotal (MRS) |  |  |  | 1017000
ALLOWANCE ITEMS
Certainty Factor
DRAINAGE |  | % of MRS | 11.41% | 116000
EROSION CONTROL & RESTORATION |  | % of MRS | 9.25% | 94000
LIGHTING |  | % of MRS | 1.412% | 14000
ROADWAY INCIDENTALS |  | % of MRS | 28.85% | 293000
SIGNING/MARKING |  | % of MRS | 3.029% | 31000
TRAFFIC CONTROL & STAGING |  | % of MRS | 4.815% | 49000
ITS/ FTMS |  | % of MRS | 1% | 10000
Allowance Subtotal |  |  |  | 607000
STRUCTURES (see STRUCTURE tab) | UNIT | QUANTITY | UNIT PRICE | Total | NOTES
Bridge Removal | EACH | 0 | 50000 | 0
New Bridge (Single Level Interchange) | SF | 0 | 110 | 0
New Bridge (Multi-level Interchange) | Insert | 0 | 0 | 0
Bridge Redecking | SF | 0 | 60 | 0
Bridge Widening | SF | 0 | 140 | 0
Retaining Wall Removal | Insert | 0 | 0 | 0
New Retaining Wall | SF | 0 | 60 | 0
Noise Wall Removal | EACH | 0 | 75000 | 0
New Noise Walls | SF | 0 | 45 | 0
New Box Culvert/Extension | LF | 0 | 2200 | 0
Sign Bridge - Cantilever | EACH | 0 | 30000 | 0
Sign Bridge - Single Span | EACH | 0 | 60000 | 0
MSE Walls | Insert | 0 | 0 | 0
Secant Walls | Insert | 0 | 0 | 0
Structure Incidentals |  | % of Structures | 10% | 0
Structure SubTotal |  |  |  | 0
SPECIAL CONSTRUCTION ELEMENTS | UNIT | QUANTITY | UNIT PRICE | Total | NOTES
Temporary Bridges | Insert | 0 | 0 | 0
Temporary Roadways | Insert | 0 | 0 | 0
Environment Mitigation | Insert | 0 | 0 | 0
Community Sensitive Design | Insert | 0 | 0 | 0
Hazardous Materials | Insert | 0 | 0 | 0
Bypass / Alternate Routes | Insert | 0 | 0 | 0
Other | Insert | 0 | 0 | 0
Other | Insert | 0 | 0 | 0
Other | Insert | 0 | 0 | 0
Other | Insert | 0 | 0 | 0
Special Construction Elements Subtotal |  |  |  | 0
Construction Costs Estimate (CCE) |  |  |  | 1624000
CONTEXT SENSITIVE SOLUTIONS (CSS)
CSS |  | % of Item CCE | 5% | 81000
Base Construction Costs Estimate (BCCE) |  |  |  | 1705000
SCOPE CHANGE ALLOWANCE ITEMS
PROJECT SCOPE INCREASE ALLOWANCE |  | % of Item BCCE | 24% | 409000
Estimated Const. Let Amount (ECLA) |  |  |  | 2114000
PROJECT DELIVERY ALLOWANCE ITEMS
PRELIMINARY ENGINEERING |  | % of Item BCCE | 7.2% | 152000
FINAL ENGINEERING |  | % of Item BCCE | 5.4% | 114000
CONSTRUCTION ENGINEERING |  | % of Item BCCE | 9.2% | 194000
CONST CHANGE ORDERS & CLAIMS |  | % of Item BCCE | 10.4% | 220000
TRAFFIC MITIGATION |  | % of Item BCCE | 1.5% | 32000
PUBLIC INVOLVEMENT |  | % of Item BCCE | 1% | 21000
Delivery Allowance Subtotal |  |  |  | 733000
EXTERNAL COSTS |  |  |  |  | NOTES
REAL ESTATE |  | 8% of Item BCCE | 136000 | 136000
COMPENSABLE UTILITIES |  | 3% of Item BCCE | 51000 | 51000
JURISDICTIONAL TRANSFERS |  |  | 0 | 0
Other |  |  | 0 | 0
Other |  |  | 0 | 0
Other |  |  | 0 | 0
Other |  |  | 0 | 0
Other |  |  | 0 | 0
External Costs Subtotal |  |  |  | 187000
Base Project Cost Estimate |  |  |  | 3034000
RISK ADJUSTMENTS |  |  |  |  | NOTES
Risk Item A |  |  | 0 | 0
Risk Item B |  |  | 0 | 0
Risk Item C |  |  | 0 | 0
Risk Adjustment Subtotal |  |  |  | 0
ESTIMATE UNCERTAINTY |  |  |  |  | NOTES
Uncertainty Item A |  |  | 0 | 0
Uncertainty Item B |  |  | 0 | 0
Uncertainty Item C |  |  | 0 | 0
Estimate Uncertainty Subtotal |  |  |  | 0
Current Year Total Project Cost Estimate |  |  |  | 3034000
INFLATION
Design | 2%
Real Estate | 7%
Construction | 4%
BASE YEAR DOLLARS | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Design | 0 | 0 | 50540 | 82460 | 77140 | 55860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Real Estate | 0 | 0 | 0 | 0 | 45333.3333 | 45333.3333 | 45333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 0 | 0 | 0 | 0 | 0 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 50540 | 82460 | 122473.3333 | 534526.6667 | 478666.6667 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INFLATED DOLLARS | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Design | 0 | 0 | 52581.816 | 87507.2117 | 83498.8168 | 61673.9537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Real Estate | 0 | 0 | 0 | 0 | 59422.7525 | 63582.3451 | 68033.1093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 0 | 0 | 0 | 0 | 0 | 527216.2577 | 548304.908 | 570237.1043 | 593046.5885 | 616768.452 | 641439.1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 52581.816 | 87507.2117 | 142921.5693 | 652472.5565 | 616338.0173 | 570237.1043 | 593046.5885 | 616768.452 | 641439.1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A13: Major Roadway Item: The Major Roadway Item Cost is produced by multiplying the calculated major roadway item quantities times estimated units costs obtained from various historical databases of WisDOT bid prices. Sources of historical unit price information include Trans*port Estimator, Bid Express, and Regional project databases.
Note on A24: Signalized Intersections Signalized intersections are totaled from the “Signals Worksheet” where each signalized intersection is listed and the total number of signalized intersections is multiplied times the average cost per intersection.
Note on A55: Allowance Items: Allowance factors are used to account for construction costs of many of the project items that are not yet sufficiently detailed at this point in the development process for cost estimating processes. Allowance factors are multiplied times the Major Roadway Costs to provide cost estimates for: drainage, erosion control, traffic control and staging, lighting, signing and marking, ITS/FTMS , and roadway incidentals. The size of the allowance factor is determined by the type of project, its duration, and the surrounding topography.
Note on A57: Drainage: Drainage costs are computed as a percentage of the Major Roadway Items Subtotal. Drainage includes all culvert pipe, storm sewer pipe, apron end walls, catch basins, inlets & inlet covers, manholes & manhole covers, adjusting inlet & manhole covers, underdrain, etc.
Note on A58: Erosion Control and Restoration: Erosion Control and Restoration costs are calculated as a percentage of the Major Roadway Items Subtotal. They include all items associated with erosion control and restoration. Included in these items are: erosion mat, erosion bales, silt fence, riprap, ditch checks, topsoil, seed, mulch, fertilizer, sod, plantings, inlet protection, cleaning sediment basins, soil stabilizers, restoration of waterways, etc..
Note on A59: Roadway Lighting: Lighting costs are calculated as a percentage of the Major Roadway Items Subtotal. It includes temporary and non-decorative permanent street lighting and components. Examples include: high mast towers and foundations, light poles, concrete bases, conduit, electrical wire, control cabinets, controllers, etc..
Note on A60: Roadway Incidentals: Incidental costs are calculated as a percentage of the Major Roadway Items Subtotal. It includes all remaining construction items not listed above such as removals (except pavement and bridges), mobilization, construction staking, field office, beamguard, sidewalk, finishing and other construction incidentals.
Note on A61: Signing/Marking: Includes all signing and pavement marking items; does not include sign bridges
Note on A62: Traffic Control and Staging: Traffic Control and Staging costs are calculated as a percentage of the Major Roadway Items Subtotal. They Include all temporary pavement, temporary barrier, temporary marking, all temporary traffic control devices; all permanent traffic control items such as signals, cabinets & controllers, crash cushions; temporary shoring away from bridges, but does not include temporary bridges or bridge widening if required.
Note on A67: STRUCTURES : Historical costs for various types of structures can be found in the LFRD Bridge Manual. (http://on.dot.wi.gov/dtid_bos/extranet/structures/LRFD/LRFDManualIndex.htm). Costs are tabulated by square foot of bridge deck and retaining wall face or length of culverts and multiplied times the historical average unit prices. Contact the Bureau of Structures for assistance in developing estimates or for questions regarding unique structures where no historical data exists.
Note on A82: Covers micellaneous structural items and unknowns such as special foundation requirements.
Note on A86: Specialized Construction Items: Special construction items may or may not be present on the project. These are unique items that are not typically found on WisDOT projects and these costs need to be estimated separately. There may be historical costs from past projects, but they will generally need to be estimated using cost based methods where contractor’s costs for labor, equipment, materials, profit and overhead are accounted for. Examples include temporary bridges and roadways, non-standard bridges, treatment of hazardous materials or archeological sites, community sensitive design components. Additional rows can be added as necessary.
Note on A103: Project Scope Increase Allowance: An amount reserved for additional costs related to potential increases in project scope resulting from more detailed data gathering or design refinements as the project moves through the various design phases. This CF is applied to the preliminary construction estimate to provide a total construction cost estimate (i.e. contract let amount).
Note on A107: Project Scope Increase Allowance: An amount reserved for additional costs related to potential increases in project scope resulting from more detailed data gathering or design refinements as the project moves through the various design phases. This CF is applied to the preliminary construction estimate to provide a total construction cost estimate (i.e. contract let amount).
Note on A111: Preliminary Engineering: The total of consultant and WisDOT costs for preliminary engineering activities. This CF is applied to the total construction cost estimate to develop the total project cost estimate.
Note on A112: Final Engineering: The total of all consultant and WisDOT costs for final design engineering. This CF is to be applied to the total construction cost to develop the total project cost estimate.
Note on A113: Construction Engineering: The total of all consultant and WisDOT costs for construction engineering. This CF is applied to the total construction cost to develop the total project cost estimate.
Note on A114: CONST CHANGE ORDERS & CLAIMS : The total amount reserved for contract modifications, quantity overruns and claims. This CF is applied to the total construction cost to develop the total project cost estimate.
Note on A121: Enter estimated compensable utility costs known to date.
Note on A122: Jurisdictional Transfers: Jurisdictional Transfers Costs are those costs associated with the transfer of jurisdiction of a highway as part of a Majors Project. They should include all roadway improvement costs needed to implement the transfer. NOTE: Pavement costs for JT items are to be accounted for in this item and NOT in the pavement section under Major Roadway Items.
Note on A132: Risk Adjustments A project risk evaluation and assessment is made to identify risks and quantify their impact on costs. Typically an interdisciplinary team of internal and external experts are brought together in a workshop format to assess and model the risks. A risk is any known or unknown event or condition that cannot be adequately defined or estimated at this stage of the project. Cost risks are identified and an assessment made as to the likelihood of the risk occurring and the impact of the risk should it occur. Additional adjustments are added to the base project estimate to account for the risks. Risk items are listed in the “Risk Worksheet” and additional lines may be inserted as needed.
Note on A138: Estimate Uncertainty Estimate Uncertainty Items are contingency amounts to account for costs the estimator is unsure of or not confident in at the time the estimate is being prepared. For example, if the cost estimate for borrow is based upon the availability of a certain parcel of land, the estimator might add an uncertainty item for borrow in this section to cover the added costs of going to an alternate site.
Note on A146: Inflation Inflation factors are used to adjust the different items of the cost estimate to the planned years of design and construction.
Note on B4: The project title should be consistent with that shown on the Project Summary Screen in FIIPS. If FIIPS does not reflect the desired titile, the region planning ssection can change it or requrest the Bureau of State Highway Programs in central office to do so.
Note on B6: Rural (R): A rural cross section is defined as a section in which no curb and gutter will be used on the typical cross section. If a median is required it will be a normal ditch section without curb and gutter. Suburban (S): A suburban cross section is defined as a section in which a median is required and curb & gutter will be used on it but not on the outside shoulder of the typical cross section Urban (U): An urban cross section is defined as a section in which curb and ill be used on the median areas, if required, and the outside shoulders of the typical cross section location. Rural/Suburban (R/S): A Rural/Suburban project is defined as a rural cross section that is used in a developed or developing urban or suburban type area.
Note on B7: Single Season (S): Project is constructed primarily in one construction season. Multi Season (M): Project is constructed over two or more construction seasons.
Note on C8: Enter the current calendar YEAR, i.e. 2012
Note on C9: Enter fiscal YEAR ONLY
Note on C14: This number is referenced from the total in the "Pavement" worksheet. Enter all pavement removal areas in the "Pavement" worksheet.
Note on C15: This number is referenced from the total in the "Pavement" worksheet. Enter the sum of all barrier lengths (combine all barrier types/heights) in the "Pavement" worksheet.
Note on C16: This number is referenced from the total in the "Pavement" worksheet. Enter the sum of all C&G lengths (combine all types/heights) in the "Pavement" worksheet.
Note on C24: Count the number of signalized intersections on the project.
Note on C26: This number is referenced from the total in the "Pavement" worksheet. Enter all pavement areas in the "Pavement" worksheet.
Note on C27: This number is referenced from the total in the "Pavement" worksheet. Enter all pavement areas in the "Pavement" worksheet.
Note on C28: This number is referenced from the total in the "Pavement" worksheet. Enter all pavement areas in the "Pavement" worksheet.
Note on C29: This number is referenced from the total in the "Pavement" worksheet. Enter all pavement areas in the "Pavement" worksheet.
Note on C30: This number is referenced from the total in the "Pavement" worksheet. Enter all pavement areas in the "Pavement" worksheet.
Note on C31: This number is referenced from the total in the "Pavement" worksheet. Enter all pavement areas in the "Pavement" worksheet.
Note on C33: This number is referenced from the total in the "Pavement" worksheet. Enter all pavement areas in the "Pavement" worksheet. Shoulder quantities are for all pavement types. Unit price for shoulders should be an average price for all shoulder types.
Note on C35: This number is referenced from the total in the "Pavement" worksheet. Enter all base areas in the "Pavement" worksheet.
Note on C36: This number is referenced from the total in the "Pavement" worksheet. Enter all base areas in the "Pavement" worksheet.
Note on C37: This number is referenced from the total in the "Pavement" worksheet. Enter all base areas in the "Pavement" worksheet.
Note on C38: This number is referenced from the total in the "Pavement" worksheet. Enter all base areas in the "Pavement" worksheet.
Note on C39: This number is referenced from the total in the "Pavement" worksheet. Enter all base areas in the "Pavement" worksheet.
Note on C40: This number is referenced from the total in the "Pavement" worksheet. Enter all base areas in the "Pavement" worksheet.
Note on C44: This number is referenced from the total in the "Pavement" worksheet. Enter all subbase areas in the "Pavement" worksheet.
Note on C45: This number is referenced from the total in the "Pavement" worksheet. Enter all subbase removal areas in the "Pavement" worksheet.
Note on C46: This number is referenced from the total in the "Pavement" worksheet. Enter all subbase areas in the "Pavement" worksheet.
Note on C47: This number is referenced from the total in the "Pavement" worksheet. Enter all subbase areas in the "Pavement" worksheet.
Note on C48: This number is referenced from the total in the "Pavement" worksheet. Enter all subbase areas in the "Pavement" worksheet.
Note on C49: This number is referenced from the total in the "Pavement" worksheet. Enter all subbase areas in the "Pavement" worksheet.
Note on C68: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on C69: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on C70: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on C73: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on C74: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on C75: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on C76: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on C77: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on C78: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on C79: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on C80: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on C81: This number is referenced from the total in the "Structures" worksheet. Enter all pavement areas in the "Structures" worksheet.
Note on D6: Gentle (G): The general terrain of the project is level, nearly level, or gently sloping. Moderate (M): The general terrain of the project is moderately sloping to moderately steep. Severe (S): The general terrain of the project is steep to very steep terrain.
Note on D7: Coarse-grained (C): The predominate soil type on the project is gravels, sands, or silty sands. Fine-grained (F): The predominate soil type on the project is silt, silty clays, or clay.
Note on E8: Enter fiscal YEAR ONLY
Note on E9: Enter fiscal YEAR ONLY

## Program.a (hidden)
123527125.99
1900-05-19
Note on B39: --> OLAP: Provider=MSOLAP.2; Data Source=C:\Program Files\AFIN.NET\Samples\Data\OLAP\SalesInCube.cub; Initial Catalog=OCWCube; -->WITH MEMBER [Measures].[wynik] AS '0 + SUM({[nazwa].[AREX]}*{[suma wart_zl]})' SELECT {[Measures].[wynik]} on 0 FROM [OCWCube] 2009.01.07 11:06, youssef, Civil Engineering
Note on M32: --> ODBC: Driver={Microsoft Access Driver (*.mdb)}; DBQ=C:\Program Files\AFIN.NET\Samples\Data\ODBC\FK2Access\AccessFinancials.mdb; -->SELECT SUM(kwotatr) AS Kwota FROM T1_TRANS WHERE kontotr LIKE '1%' 2009.01.07 11:06, youssef, Civil Engineering

## Scheduled Est.
SUGGESTED CONCEPTUAL ESTIMATE
| BASE YEAR DOLLARS | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| Design | 0 | 0 | 50540 | 82460 | 77140 | 55860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Real Estate | 0 | 0 | 0 | 0 | 45333.3333 | 45333.3333 | 45333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction | 0 | 0 | 0 | 0 | 0 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 0 | 0 | 50540 | 82460 | 122473.3333 | 534526.6667 | 478666.6667 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SCHEDULED ESTIMATE | 2013: - Please input YOUR estimates below for the BASE year dollars ONLY.
| BASE YEAR DOLLARS | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Real Estate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INFLATED DOLLARS | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
2% | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7% | Real Estate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4% | Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The Scheduled Estimate allows refinement to the Conceptual Estimate by modifying the Conceptual Estimate to fit the actual project schedule based upon updated information.
Another potential use of the Scheduled Estimate is to overlap Design and Construction costs for more than the estimated one year.
Note on C13: Add your base estimate for every year, and the table will inflate the numbers automatically.

## PAVEMENT
Wisconsin Department of Transportation
1130-31-00
US 41
US 41 Expansion (Winnebago, Outagamie, and Brown Counties)
Segment 7: CTH U Interchange
ITEM DESCRIPTION | DESCRIPTION | SEGMENT | PAVEMENT REMOVAL AREA |  | NEW PAV. AREA | SHOULDER AREA | AREA OF BASE | AREA OF SUBBASE | BARRIER WALL | CURB & GUTTER | Centerline Barrier Wall NB | Centerline Barrier Wall SB | NB outside barrier wall | SB outside barrier wall | Frontage roads barrier | TOTAL BARRIER WALL |  | NOISE WALLS | Centerline Length (ft) | Length of 3 lanes NB | Length of 3 lanes SB | Length of 4 lanes NB | Length of 4 lanes SB | Length of 5 lanes NB | Length of 5 lanes SB | Length of 6 lanes NB | Length of 6 lanes SB | Length of transition lanes NB (avg lane width 6') | Length of transition lanes SB (avg lane width 6') | Lane width | Mainline pavement depth | Inside Shoulder width | Length of 12' NB Outside shoulder width | Length of 12' SB Outside shoulder width | Length of 8' NB Outside shoulder width | Length of 8' SB Outside shoulder width | Shoulder pavement depth | Total Concrete pavement | Total Shoulder pavement | NOTES
MAINLINE |  |  | SY |  | SY | SY | SY | SY | LF | LF
0
0
0
0
0
0
0
0
MAINLINE TOTAL |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | LF: | 0
[17 empty] | SF: | 0
SYSTEM RAMPS | [16 empty] | SY: | 0 | Number of lanes | Lane 1 Length | lane 2 length | lane 1 width | lane 2 width (if different) | right shoulder length | right shoulder width | left shoulder length | left shoulder width | TOTAL PAVEMENT (SF) | TOTAL SHOULDER (SF)
2.01 | [6 empty] | 0 | 0 | 0 | 0 | [17 empty] | 0 | 0
SYSTEM RAMPS TOTAL |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
SERVICE RAMPS
2.01 |  | CTH U - NB off | 1250 |  | 1250 | 700 |  |  | 0 | 0
2.02 |  | CTH U - SB on | 1750 |  | 1750 | 950
2.03 |  | CTH U - NB on | 2000 |  | 2000 | 1100
2.04 |  | CTH U - SB off | 1600 |  | 1600 | 850
SERVICE RAMPS TOTAL |  |  | 6600 |  | 6600 | 3600 | 0 | 0 | 0 | 0
CROSSROAD
3.01 |  | CTH U | 2150 |  | 4300 | 1100 | 0 | 0 | 0 | 2100
3.02 |  | CTH U Local Share | 1350 |  | 2700 | 700 | 0 | 0 | 0 | 400
CROSSROAD TOTAL |  |  |  | 3500 | 7000 | 1800 | 0 | 0 | 0 | 2500
FRONTAGE ROADS | [19 empty] | Length 1 | Width 1 | Length 2 | Width 2 | pvmt depth | TOTAL PAVEMENT
[5 empty] | 0 |  | 0 | 0 | 0 | [15 empty] | 0
[5 empty] | 0 |  | 0 | 0 | 0 | [15 empty] | 0
[6 empty] | 0 | 0 | 0 | 0 | [15 empty] | 0
[6 empty] | 0 | 0 | 0 | 0 | [15 empty] | 0
[6 empty] | 0 | 0 | 0 | 0 | [15 empty] | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0
FRONTAGE ROADS TOTAL |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
LOCAL ROADS
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LOCAL ROADS TOTAL |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
GRAND TOTALS |  |  | 10100 |  | 13600 | 5400 | 0 | 0 | 0 | 2500
Note on D6: Includes removal of concrete pavment and the asphalt overlay(s) on the concrete pavement.
Note on M6: Unit prices include base and subbase to 2' back of barrier.
Note on N6: Unit prices include base and subbase to 2' back of curb.

## STRUCTURE
Wisconsin Department of Transportation
1130-31-00
US 41
US 41 Expansion (Winnebago, Outagamie, and Brown Counties)
Segment 7: CTH U Interchange
ITEM DESCRIPTION | Number | SEGMENT | BRIDGE REMOVAL | NEW BRIDGE (SINGLE LEVEL I/C) | NEW BRIDGE (MULTI LEVEL I/C) | BRIDGE REDECKING | BRIDGE WIDENING | RETAINING WALL REMOVAL | NEW RETAINING WALL | NOISE WALL REMOVAL | NEW NOISE WALL | NEW BOX CULVERT / EXTENSION | SIGN BRIDGE CANTELEVER | SIGN BRIDGE SPAN | MSE Walls | Secant Walls | EXISTING DECK WIDTH #1 | EXISTING TOTAL BRIDGE LENGTH | BRIDGE WIDEN WIDTH #1 | FINISHED BRIDGE WIDTH | BRIDGE RECONSTRUCT WIDTH | BRIDGE RECONSTRUCT LENGTH | REDECK | WIDEN | RECONSTRUCT
|  |  | EACH | SF | SF | SF | SF | LF | SF | EACH | LF | LF | EACH | EACH | SF | SF | FT | FT | FT | FT | FT | FT | SF | SF | SF
MAINLINE & SYSTEM RAMPS
MAINLINE & SYSTEM RAMPS TOTALS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SERVICE RAMPS
2.01
2.02
2.03
2.04
2.05
2.06
SERVICE RAMPS TOTALS |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CROSSROAD
3.01
3.02
3.03
3.04
3.05
3.06
CROSSROAD TOTALS |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FRONTAGE ROADS
4.01
4.02
4.03
4.04
4.05
4.06
FRONTAGE ROADS TOTALS |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LOCAL ROADS
5.01
5.02
5.03
5.04
5.05
5.06
LOCAL ROADS TOTALS |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GRAND TOTALS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on U6: Marquis Young: Widen from Bridge sections + 3' for splicing + 3' for parapet, see assumptions

## REMOVALS
Wisconsin Department of Transportation
1130-31-00
US 41
US 41 Expansion (Winnebago, Outagamie, and Brown Counties)
Segment 7: CTH U Interchange
|  | Centerline Length (ft) | NB Length 1 | NB Width 1 | NB Length 2 | NB Width 2 | SB Length 1 | SB Width 1 | SB Length 2 | SB Width 2 | TOTAL (SF) | TOTAL (SY) | NOTES:
MAINLINE (US 41) & SYSTEM RAMPS
MAINLINE (IH) & SYSTEM RAMPS TOTAL
RAMPS |  |  | NB Length 1 | NB Width 1 | NB Length 2 | NB Width 2 | SB Length 1 | SB Width 1 | SB Length 2 | SB Width 2 | TOTAL (SF) | TOTAL (SY)
| CTH U - NB off |  | 750 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 1250
| CTH U - SB on |  | 0 | 0 | 0 | 0 | 1050 | 15 | 0 | 0 | 15750 | 1750
| CTH U - NB on |  | 1200 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 2000
| CTH U - SB off |  | 0 | 0 | 0 | 0 | 950 | 15 | 0 | 0 | 14250 | 1583.3333
CROSSROADS |  |  | Length 1 | Width 1 | TOTAL (SF) | TOTAL (SY)
| County U |  | 800 | 24 | 19200 | 2150
| County U Local Share |  |  |  |  | 1350
[5 empty] | 19200 | 3500

## Earthwork
Earthwork
| Concrete pavement (SY) | Shoulders (SY) | Earthwork (CY)
Mainline |  |  | 0
Ramps | 6600 | 3600 | 10200
Frontage roads |  |  | 0
Crossoads | 7000 | 1800 | 7333.3333
TOTAL |  |  | 17533.3333
Mainline Earthwork is calculated using the SY of mainline and shoulders, multiplied by a depth of 3 feet. This includes 10" on 16" on 6" for a depth of 32".
We are using 3' depth to be conservative and account for any extra earthwork that would be needed in the fill slopes.
Ramp earthwork is calculated the same way as Mainline.
Frontage roads earthwork is calculated the same as mainline, except using a depth of 2.5'

## Scope
Project Scope
You may wish to use the Project Scoping Document as a guide: http://roadwaystandards.dot.wi.gov/standards/fdm/03-05-003att.pdf
Note on A1: Project Scope: The scope of a project identifies the purpose and need of the project and defines the project requirements. It is essential that the scope be documented so that all future changes can be compared to the estimate prepared based upon this scope. Typically it would define the limits of the project, locations of major interchanges, descriptions of the work to be done, identification of temporary bridges or roadways and other details on how the work will be accomplished. The project scope is entered in the "Project Scope" worksheet and this should be printed and attached to the Cost Estimate Report. (Note: The Project Scope Worksheet is not linked to the Program Worsheet and will not automatically appear in the Conceptual Cost Estimate.)

## Assumptions
Project Assumptions - Segment 7
# OF LANES | 3 per direction. Widen into median.
DETOUR/OPEN | Open - staged construction
ALIGNMENT | No change, except for minor shift at the St. Patrick Cemetary
RELOCATION ON ALIGN. | None
COMPLEXITY OF DRAINAGE | Minimal
CONCRETE BARRIER | Frontage roads within the segment do not meet the desirable offset from the mainline. The quantity of concrete barrier at the outside shoulders could be reduced by 50% if barrier was eliminated in tangent areas which have an offset greater than 65'. The cost estimate does not include this reduction, however the reductions are noted on the plan sheets.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
Note on A1: Project Assumptions: The major project assumptions need to be documented so that future changes can be evaluated against the project costs estimated at this time based upon these assumptions. Assumptions should be related to the overall project and could include such things as the alignment used, width of Right of Way assumed, number of lanes to be built or rehabilitated, environmental mitigation locations, numbers of new bridges, numbers of bridges to be widened, etc. This list needs to be inclusive and in sufficient detail to provide others guidance on the basis of which this estimate was prepared. Project assumptions are entered in the "Assumptions" worksheet and should be printed out and attached to the Cost Estimate Report. (Note: The Assumptions Worksheet is not linked to the Program Worsheet and will not automatically appear in the Conceptual Cost Estimate.) Additional assumptions related to specific items of work should be documented on specific item worksheets.

## JT Costs
Jurisdictional Transfers

## Comp. Utilities
Compensable Utilities

## BID Express Inst.
BID EXPRESS
Bid Express URL
| Enter your username and password - Then click Log in |  |  | Choose Wisconsin - Then click Go
Navigational Tabs
WIDOT - Home page for WISDOT and contains link to their website
Lettings - Link to where you can look up bid tabs for all past projects
Utilities - Downloadable programs (WinZip, Adobe Acrobat, Expedite Bid) not often used
Search - Porjects, Items, or Vendors by keywords
Bid Tab Analysis- Lets you search items by description or number to compare prices
| Search for individual projects - click on the Lettings tab |  |  | *Requires knowledge of the Letting Date or ID number
Each Project has a Letting ID # (a.k.a. Contract ID #) consisting of 11 digits - only the first 8 digits are shown
The Letting ID and Date correspond to the Date that the project went to the board for approval
Find the correct ID number to the corresponding project and click on that date
The last 3 digits of the Contract ID number is the Call Order number
From here, click on the project you want
| Every Item has its own Item Number |  | Units vary depending on the Item
Click Bid Tabulations to see the various bidders and amounts they bid
Select the bidder's bid tab that you would like to see by unchecking the boxes and leaving the desired box checked - Then click
You can see what each contractor bid on each individual item.
*If you wish to export this page to Excel for instance, you can use this links
If you desire the contractor's personal information ( address, phone number, ect…) you can click on their name.
Searching for a particular item or contractor…first go to the Search tab
Put in the item you are looking for, between what dates you want to look between, and what you want it to sort by, then hit search
If you search by a vendor, all their offices or branches with show up in the search with contact information for every location and their Bidder ID.
As you can see from below, it will show you all the bids for example: grubbing (or whatever you entered) during the time you selected among all the projects in the database
Clicking on the Contract ID will take you back to the individual bids under the Letting tab, and clicking on the Vendor ID will take you back to the contractor's personal information
Year
Month
Day

## Trnsport Estimator Inst.
Estimator
Admin should automatically appear in the User Name box
Log in by typing in "password" for your password - Then click
This password may change with versions of Estimator, if it changes, talk to David Castleberg at the WISDOT - david.castleberg@dot.state.wi.us
When you installed the program, a catalog was also installed
A catalog is your database of projects that Estimator will work from
Go to View, Current Catalog to see your catalog
You may need to load on a new catalog if a more current one is available.
The name of the current catalog as you can see is ENG2003
This bigger box on the left is called your tree view, if you click the little box with the + in it, it will show the branches.
Here you can see all the folders that comprise the catalog. You can further expand the tree view by again clicking the + boxes next to the desired item(s)
If there isn't a + box next to the item then that means there is not anything in the folder.
As an example, the SEASON code table has been expanded by clicking the + box next to it.
What do these folders contain?
Standard Item Catalog - lists every possible item by its item number (Item Code) in order numerically. For example, item 201.0105 is CLEARING as seen in the Description box
If you click the yellow arrow, it shows you the item name which each item number represents, then just click the item number to return to this screen
Bid History Catalog - gives you statistical values regarding the item you selected in the forms of percentiles. The 50th percentile is the average
Code Table PWRKTYP - This is were you specify what type of construction you are doing.
For example, code AC corresponds to GENERAL CONSTRUCTION AND PCC PAVEMENT
Code Table SEASON - Choose the season in which the project will be let.
Code Table URBRUR - Select what type of community setting you are working with
For Example, code U means Urban
Code Table COUNTY - Each county around the state has a numerical value that represents it's county. Select the project location
For example, code C005 corresponds with Brown county
Code Table UNITS - This is where you select the units that will be used
For example, code DOL is sort for DOLLAR
Code Table HWYTYPE - This is where you select what kind of road you are working with
For example, code EC means EXPRESSWAY, COLLECTOR (MAJOR)
Preparing an Estimate
First thing you do is go to File, New. A new estimate box will pop up
Then it's always good to save it right away. So, go to File, Save, and then saving procedure is identical to any microsoft document.
|  | Fill in your projects specification by either entering them in or clicking the drop down arrows to select the desired choice. |  | Estimate ID numbers can be an actual project ID numbers or for example HWY 23 or 43rd St.
Next, in your tree view, click on the little + box to the left of Estimate. A "branch" should show up that is labeled a group. Click on the group. Then Click under Line #
Item will apprear in you tree view, and a new line should have appeared in the bottom right box. Then click the little "Green GO" symbol
Select the item you want to estimate by clicking the down arrow and find the item. Then select the units or measure by clicking the arrow by Units to select the units.
Then enter the project quantity while keeping in mind what units you are working with. Then click in the Unit Price box, and it will update automatically.
Also, the item and corresponding item number you selected should now show up over in your tree view next to Item
Prices have also shown up next to the Estimate and Group Branches - because there is only one item, the item, group and estimate price are all the same price
If you click the + box next to Item, a Bid History Regression branch will form. Double click that and a regression model will show for you to compare quantity and prices
The green lines on the graph quantity and price you have entered. This graph allows you to see how sensitive the price distribution is if you want to raise or lower you quantity
Say you are done with that item and you are ready to bid another. Click on the Group, and repeat the ealier steps by clicking the line in the bottom right box, then the GO button, and then form for bid for another item
As you can see, I added another item under Group 1, then added Group 2 and bid an item under the new group. Notice the prices now, the group price is the total of the items
in their groups, and the Estimate price is the total project price at the time because it's adding both individual group's prices together.
Dividing items onto groups allows you categorize your items. For example, all the Lighting items will be group 1 and all the Earthwork items will be group 2
For printing, do a File, Print.
Then this window will apprear, choosing None will work fine, but you can make your printout more detailed by clicking Summary or Detailed if you wish. Then clcik OK, and Print

## Often Missed
Items to Check
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## TheBrains
| 60% | 70% | 75% | 85% | 90% | 95% | 99% |  |  | Urban | Suburban | Rural/Suburb | Rural |  | Insert | Insert | Insert | Insert |  | Insert | Insert | Insert
DRAINAGE | 8.522% | 8.798% | 9.073% | 9.486% | 9.899% | 10.45% | 11.41% |  | PRELIMINARY ENGINEERING | 7.2% | 7% | 7% | 6.8% |  | Rural | Gentle | Single Season | Coarse-grained |  | 2% | 99% | 1%
EROSION CONTROL & RESTORATION | 6.907% | 7.13% | 7.353% | 7.688% | 8.023% | 8.469% | 9.25% |  | FINAL ENGINEERING | 5.4% | 5.2% | 5.2% | 4.8% |  | Suburban | Moderate | Multi Season | Fine-grained |  | 3% | 95% | 2%
LIGHTING | 1.054% | 1.088% | 1.122% | 1.173% | 1.224% | 1.293% | 1.412% |  | CONSTRUCTION ENGINEERING | 9.2% | 8.8% | 8.8% | 7.8% |  | Urban | Severe | 1 | 2 |  | 4% | 90% | 3%
ROADWAY INCIDENTALS | 21.54% | 22.24% | 22.93% | 23.98% | 25.02% | 26.41% | 28.85% |  | CONST CHANGE ORDERS & CLAIMS | 10.4% | 10% | 10% | 9% |  | Rural/Suburban | 3 |  |  |  | 3 | 85% | 4%
SIGNING/MARKING | 2.262% | 2.335% | 2.408% | 2.518% | 2.627% | 2.774% | 3.029% |  | TRAFFIC MITIGATION | 1.5% | 1.15% | 1.15% | 0.15% |  | 4 |  |  |  |  | 3% | 75% | 5%
TRAFFIC CONTROL & STAGING | 3.595% | 3.711% | 3.827% | 4.001% | 4.176% | 4.408% | 4.815% |  | PUBLIC INVOLVEMENT | 1% | 1% | 1% | 1% | [7 empty] | 70% | 6%
ITS/ FTMS | 1% | 1% | 1% | 1% | 1% | 1% | 1% |  | CONTEXT SENSITIVE SOLUTIONS (CSS) | 5% | 3% | 2% | 1% | [7 empty] | 60% | 7%
[21 empty] | 1 | 8%
9%
[7 empty] | ONLY UPDATE THE CELLS HIGHLIGHTED IN YELLOW, IF NEEDED. | [14 empty] | 10%
11%
[7 empty] | DO NOT EDIT OTHER FIELDS IN THIS TAB | [14 empty] | 12%
13%
14%
15%
yearly percentages for the design costs
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | total %
1 | 100% | [11 empty] | 100%
2 | 49.5% | 50.5% | [10 empty] | 100%
3 | 24% | 50% | 26% | [9 empty] | 100%
4 | 19% | 31% | 29% | 21% | [8 empty] | 100%
5 | 11% | 24% | 30% | 26% | 9% | [7 empty] | 100%
6 | 9% | 14% | 24% | 26% | 16% | 11% | [6 empty] | 100%
7 | 6% | 10% | 18% | 25% | 21% | 11% | 9% | [5 empty] | 100%
8 | 4% | 9% | 14% | 20% | 21% | 16% | 11% | 5% |  |  |  |  | 100%
9 | 4% | 9% | 10% | 15% | 20% | 16% | 11% | 8% | 7% |  |  |  | 100%
10 | 4% | 7.5% | 9% | 12.5% | 16% | 15% | 13% | 10% | 8% | 5% |  |  | 100%
11 | 5% | 7% | 8% | 10% | 11% | 14% | 13% | 12% | 7.5% | 6.5% | 6% |  | 100%
12 | 3% | 5% | 7% | 9% | 11% | 12.5% | 13% | 11.5% | 10% | 8% | 6% | 4% | 100%
Conceptual estimate in base year dollars
| design cost | 266000 |  | n1= | 4
start prelim. design
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | 0
2 | 0 | 0
3 | 0 | 0 | 0
4 | 50540 | 82460 | 77140 | 55860
5 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 50540 | 82460 | 77140 | 55860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 50540 | 82460 | 77140 | 55860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| construction cost | 2600000 |  | n2= | 6
start construction
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | 0
2 | 0 | 0
3 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0
6 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 0 | 0 | 0 | 0 | 0 | 0
| real estate cost | 136000
|  | n2=0 | n2=1
| year before | start const. | year after
| 45333.3333 | 45333.3333 | 45333.3333
Conceptual estimate in inflated dollars
| inflated design costs |  |  | n3= | 3 |  |  |  | design inflation | 2%
start prelim. design
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | 0
2 | 0 | 0
3 | 0 | 0 | 0
4 | 52581.816 | 87507.2117 | 83498.8168 | 61673.9537
5 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 52581.816 | 87507.2117 | 83498.8168 | 61673.9537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 52581.816 | 87507.2117 | 83498.8168 | 61673.9537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| inflated constr. costs | [7 empty] | constr. inflation | 4%
start construction
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | 0
2 | 0 | 0
3 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0
6 | 527216.2577 | 548304.908 | 570237.1043 | 593046.5885 | 616768.452 | 641439.1901
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 527216.2577 | 548304.908 | 570237.1043 | 593046.5885 | 616768.452 | 641439.1901 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 527216.2577 | 548304.908 | 570237.1043 | 593046.5885 | 616768.452 | 641439.1901 | 0 | 0 | 0 | 0 | 0 | 0
inflated real estate cost
|  | n2=0 | n2=1 | [5 empty] | real estate inflation | 7%
| year before | start const. | year after
| 59422.7525 | 63582.3451 | 68033.1093
BASE YEAR DOLLARS | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| 0 | 0 | 50540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 82460 | 77140 | 55860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design | 0 | 0 | 50540 | 82460 | 77140 | 55860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Real Estate | 0 | 0 | 0 | 0 | 45333.3333 | 45333.3333 | 45333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 0 | 0 | 0 | 0 | 0 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 50540 | 82460 | 122473.3333 | 534526.6667 | 478666.6667 | 433333.3333 | 433333.3333 | 433333.3333 | 433333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INFLATED DOLLARS | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| 0 | 0 | 52581.816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 87507.2117 | 83498.8168 | 61673.9537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design | 0 | 0 | 52581.816 | 87507.2117 | 83498.8168 | 61673.9537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Real Estate | 0 | 0 | 0 | 0 | 59422.7525 | 63582.3451 | 68033.1093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 0 | 0 | 0 | 0 | 0 | 527216.2577 | 548304.908 | 570237.1043 | 593046.5885 | 616768.452 | 641439.1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 52581.816 | 87507.2117 | 142921.5693 | 652472.5565 | 616338.0173 | 570237.1043 | 593046.5885 | 616768.452 | 641439.1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A2: Includes all culvert pipe, storm sewer pipe, apron end walls, pipe underdrain, inlets, manholes, castings, etc.
Note on A3: Includes all erosion control and restoration items
Note on A4: Includes temporary and permanent street lighting; non-decorative
Note on A5: All remaining construction items not listed above such as removals (except pavement and bridges), mobilization, construction staking, QMP, field office, finishing and other construction incidentals.
Note on A6: Includes all signing and pavement marking items; does not include sign bridges
Note on A17: The rows 1-15 are hidden, and contain the percentages used behind the allowance factors logic.
Note on J2: Preliminary Engineering: The total of consultant and WisDOT costs for preliminary engineering activities. This CF is applied to the total construction cost estimate to develop the total project cost estimate.
Note on J3: Final Engineering: The total of all consultant and WisDOT costs for final design engineering. This CF is to be applied to the total construction cost to develop the total project cost estimate.
Note on J4: Construction Engineering: The total of all consultant and WisDOT costs for construction engineering. This CF is applied to the total construction cost to develop the total project cost estimate.
Note on J5: CONST CHANGE ORDERS & CLAIMS : The total amount reserved for contract modifications, quantity overruns and claims. This CF is applied to the total construction cost to develop the total project cost estimate.