Pre-DSR Review MEETING AGENDA

Date:

Project ID:		     				Supervisor:

Title:			     				Project Manager:

Highway:		     				Designer(s):

County:		     				(Firm and Names)

- Introductions

- Proposed FIIPs Improvement Concept Code

- Project Location and Need

- Design Summary

- Major Design Changes Between 30 and 60% Plans

Project Schedule/Estimate

- PS&E Date:

- Advanceable Date:

- LET Date:

- Env. Document Date:

- DSR Date:

- Slope Intercept Date:

- Plat Recorded Date:

- DT1078 Submittal Date*:

|  | Date | Estimate** Construction (w/o delivery) | Estimate Right of Way | Estimate Utilities |  | Estimate Railroad | Comments |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Scope Approved: |  |  |  |  |  |  |  |  |
| Design Kick-off Meeting: |  |  |  |  |  |  |  |  |
| 30% Meeting: |  |  |  |  |  |  |  |  |
| FIIPS Estimate: |  |  |  |  |  |  |  |  |
| Current Estimate: |  |  |  |  |  |  |  |  |

*     - The date DT1078’s are sent to the utility companies

**   - State 3R projects – Inflate construction estimate by 2.5% per year to the LET Date

- Backbone and HISP projects – All estimates will be in current dollars

Current estimate in current dollars:

- Change Management Discussion (See NE Region Change Management Policy & Procedure)

- Funding Participation and Local Agreements

  - SMA

  - SMFA (Financial)

  - SMMA (Maintenance and Traffic)

  - Lighting

- Traffic Management Plan (TMP)

  - TMP Type

  - Status/Approval Date

- Real Estate Requirements

  - Additional right of way needs since 30% Review

  - Number of Parcels: Fee        TLE

  - Adequate time scheduled for acquisition

- Plats

  - Plat Status

  - Plat Review Meeting date

- Access

  - Issues with driveways

- Encroachment

  - Encroachment actions

  - Roadside Hazard actions

- Environmental Process

  - Impacts (Noise, Historical, Archeological, HazMat, etc.)

  - Section 106 status

  - 404 permit status

  - Northern Long Ear Bat (NLEB) Coordination with Fish and Wildlife Service (FWS)

  - Agency Coordination (DNR, COE, Native Americans, etc)

    - Review Preliminary Comments from DNR

  - Environmental Document Status

- Stormwater/Erosion Control

  - Stormwater Requirements

  - Temporary and Permanent Erosion Control Concerns

  - Waterway Concerns

- Utility Coordination

  - DT1078 status

  - Anticipated utility conflicts

  - Potential high cost/high risk utilities identified

  - Utility Coordination Task List

- Railroad Coordination

  - Railroad within 1000’ of the project limits or an at-grade crossing on the detour.

- Maintenance Concerns

  - Additional structural or culvert improvements identified since 30% Review Meeting.

  - Additional Maintenance Concerns

- Public Involvement

  - Public Involvement Plan (PIP) signed by Region Communications Manager (RCM)

    - PIP updates with additional project work with appropriate PI since initial RCM review

  - Results from PIM and Hearings

  - Date of next PIM

  - Stakeholder concerns/issues

- Discuss Comments Made Prior to Meeting

  - Comments the Designer Disagrees With

  - Comments that Require Further Study

- Additional Comments/Concerns

- Constructability Review Date: [Delete if Consultant design]

Responses to Section Comments Due Date:

Action Items:

*Note:  Review agenda provides a guide for possible discussion topics.  Designer shall modify agenda and provide additional information based on the specific project needs.

Project Data

|  | Existing Conditions | Proposed | Remarks/Comments |
| --- | --- | --- | --- |
| Design Speed |  |  |  |
| Traffic Projections |  |  |  |
| Typical Sections and Clear Zone |  |  |  |
| Geometric Design Elements |  |  |  |
| Preliminary Drainage/Storm Sewer |  |  |  |
| Pavement Considerations |  |  |  |
| Soils Report |  |  |  |
| Culvert/Bridge Design Elements |  |  |  |
| Side Roads/Intersections (Geometry/Traffic control Review) |  |  |  |
| ICE Reviews |  |  |  |
| Roundabout Review |  |  |  |
| Verify Design Vehicle/OSOW |  |  |  |
| Recreation Considerations |  |  |  |
| Park and Ride |  |  |  |
| Bicycle/Pedestrian Accommodations |  |  |  |
| Unique Design Requirements |  |  |  |
| Exceptions to Standards/Substandard Features |  |  |  |
| Connecting Highway Changes and Status |  |  |  |
| Commitments |  |  |  |
| NHS Status |  |  |  |

How to fill out the Pre-DSR Review Agenda – Delete once Agenda is completed.

Delete topics that do not pertain to the project.

- Design Summary – Give overview and discuss project background

- Major Design Changes between 30% and 60% Plans – Discuss anything different from the 30% meeting.

- Preferred Alternative – Discuss selected alternative. If there are any unresolved issues with the project, it can be discussed here if they do not fit anywhere else. Discuss pavement design considerations.

- Project Schedule/Estimate –

- Change Management Discussion (See NE Region Change Management Policy & Procedure) If the cumulative cost of the project has increased by $200,000, need to follow the change management procedure or if project limits have changed or if a different type of improvement is now 50% of the project, for example moving the project from a resurface to a re-condition to a reconstruct.

- Funding Participation and Local Agreements

  - SMA – Discuss Financial, Maintenance and Traffic Agreements. If the project has SMA delete SMFA and SMMA Sections.

  - SMFA (Financial) – Discuss Financial Agreements. If project has SMFA delete SMA section.

  - SMMA (Maintenance and Traffic) – Discuss Maintenance and Traffic Agreements. If project has SMMA delete SMA section.

  - Lighting - Discuss lighting

- Traffic Management Plan (TMP) – Discuss anything interesting regarding how to handle the traffic. Will there be a detour, staged or flagging?

  - TMP Type

  - Documentation

- Plats – Discuss when is the plat review meeting to go over the final corrects needed to the plat. When will the plat be recorded? Are there any issues with the time frame the plats will be able to deliver in?

- Real Estate Requirements

  - Schedule

- Access Control - Are there any existing driveways that are substandard? Are there any unsafe driveways? Are there any driveways with potential political issues?

- Encroachments - Discuss the big ones that need a permit or are to be removed.

  - Existing and proposed actions

  - Roadside Hazards and proposed actions

- Environmental Process - Discuss the following:

  - Impacts (Noise, Historical, Archeological, HazMat, etc)

  - Section 106 status

  - 404 permit status

  - Northern Long Ear Bat (NLEB) Coordination with Fish and Wildlife Service (FWS) - NLEB effect determination is required on all projects.

  - Agency Coordination (DNR, COE, Native Americans, etc)

    - Review Preliminary Comments from DNR

  - Environmental Document Status

- Stormwater/Erosion Control – Discuss the following:

  - Stormwater Requirements

  - Temporary and Permanent Erosion Control Concerns - How is water to be handled during construction?

  - Waterway Concerns

- Utility Coordination - Discuss the following:

  - DT1078 status – Discuss when the DT1078 plan will be submitted to the utility department. If it’s already submitted discuss what needs to be done in order for the ST1078 plan to be submitted to the utility companies and wen it will be completed.

  - Anticipated utility conflicts

  - Potential high cost/high risk utilities identified - Do these need to be designed around?

  - Utility Coordination Task List - discuss responsibilities

- Railroad Coordination - Discuss the following:

  - Railroad within 1000’ of the project limits or an at-grade crossing on the detour.

  - Discuss the status of railroad coordination.

    - Date of Railroad Project Submittal Package (RPSP) submitted to the Railroads and Harbors Section (RHS)

    - Discuss if Office of the Commissioner of Railroads (OCR) Hearing or Determinations is required.

    - If Railroad real estate is needed.

- Maintenance Concerns - Discuss the following:

  - Additional structural or culvert improvements identified since 30% Review Meeting.

  - Additional Maintenance Concerns

- Public Involvement

  - Results from PIM - Any complaints? Any positive feedback?

Project Data: (Include and expand on those that apply to project) These do not have to be discussed during the meeting only for reference. The below are topics/questions to think about when filling out the table.

  - Design Speed – List current and proposed

  - Traffic Projections – List current and future, construction and design. Any turning movement counts if they were completed.

  - Typical Sections and Clear Zone – List existing and proposed for each segment with the stationing.

  - Vertical & Horizontal Alignment- Document current vertical & geometric alignment and preferred alternative.

  - Preliminary Drainage/Storm Sewer – Document existing drainage and storm sewer and proposed improvements. In the remarks, document any specific design considerations.

  - Pavement Considerations -Document existing structure, document preliminary pavement design. Unless changes are made at the meeting the preliminary pavement design will be considered the final pavement design.

  - Soils Report – Document existing soils based off the soil report, document if any proposed soil improvements are need. In the remarks, state any frost heaves, or any issues from recently constructed projects in the area.

  - Culvert/Bridge Design Elements -Document existing structures and proposed improvements.

  - Side Roads/Intersections (Geometry/Traffic Control Review) – Document any sub standards and any proposed modifications. In the remarks, document crash trends at the intersections.

  - ICE Reviews – Document the existing intersection control and the proposed alternatives in the ICE.

  - Roundabout Review – What design elements have been reviewed?

  - Verify Design Vehicle/OSOW – Document what vehicle can navigate the project now, and the proposed design vehicle. Review FDM 11-25-2 attachments 2.1 & 2.2. See if SPO has any known concerns with OSOW movements in your project.

  - Recreation Considerations -Document any big attractions that could possibly cause issues with staging/construction or if any of the attractions need special design considerations

  - Park & Ride - Document any Park & Rides in the area and work that needs to be done in coordination of the construction project.

  - Bicycle/Pedestrian Accommodations -Document existing bike/ped accommodations and the proposed.

  - Unique Design Requirements -Document any existing or proposed elements outside of the normal roadway criteria.

  - Exceptions to Standards/Substandard Features – Document any existing and proposed 13 Controlling criteria that will not be designed to an exception. Document in the remarks if a programmatic or formal exception to standards has been approved.

  - Connecting Highway Changes -Document existing and proposed connecting highway limits.

  - Commitments – Document any commitments made to the public, legislation, other agencies, exc.

  - NHS Status – Document if project is NHS or non NHS highway.