## Sheet1
Potential Utility Conflicts
2021-10-13
Project ID: 1470-30-00
Two Rivers - Kewaunee
34th Street - NCL
WIS 42
Manitowoc County
Utility Name | Potential Conflict | Plan Sheet # | Station | Location
AT&T WISCONSIN | Possible conflict with box culvert replacement work. | Plan Detail - PRE_20 Plan Sheet - PRE_43 | 179+19 - 179+45 | 44.5'RT
AT&T WISCONSIN | Possible conflict with cross culvert replacement. | Plan Detail - PRE_26 Plan Sheet - PRE_50 | 414+94 | 32'RT
AT&T WISCONSIN | Possible conflict with cross culvert replacement. | Plan Detail - PRE_26 Plan Sheet - PRE_51 | 433+57 - 433+64 | 28'RT
AT&T WISCONSIN | Possible conflict with cross culvert replacement. | Plan Detail - PRE_27 Plan Sheet - PRE_51 | 442+87 - 442+94 | 34'RT
AT&T WISCONSIN | Possible conflict with culvert replacement. | Plan Detail - PRE_28 Plan Sheet - PRE_51 | 451+20 - 451+39 | 39.5'RT
AT&T WISCONSIN | Possible conflict with slope/ditch grading. | Plan Detail - PRE_28 Plan Sheet - PRE_51 | 452+64 - 453+42 | 30.5'RT - 34.5'RT
AT&T WISCONSIN | Possible conflict with cross culvert replacement. | Plan Detail - PRE_29 Plan Sheet - PRE_52 | 472+27 - 472+56 | 37'RT - 40'RT
AT&T WISCONSIN | Possible conflict with cross culvert replacement. | Plan Detail - PRE_29 Plan Sheet - PRE_52 | 491+26 - 491+43 | 37.5'RT
AT&T WISCONSIN | Possible conflict with cross culvert replacement. | Plan Detail - PRE_30 Plan Sheet - PRE_53 | 496+34 - 496+50 | 40.5'RT
AT&T WISCONSIN | Possible conflict with cross culvert replacement. | Plan Detail - PRE_31 Plan Sheet - PRE_53 | 512+54 - 512+65 | 37'RT
AT&T WISCONSIN | Possible conflict with cross culvert replacement. | Plan Detail - PRE_32 Plan Sheet - PRE_54 | 524+60 - 524+72 | 36'RT
AT&T WISCONSIN | Possible conflict with cross culvert replacement. | Plan Detail - PRE_32 Plan Sheet - PRE_54 | 530+26 - 530+38 | 35.5'RT
AT&T WISCONSIN | Possible conflict with culvert replacement. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 543+11 - 543+49 | 42'RT - 44'RT
AT&T WISCONSIN | Possible conflict with slope/ditch grading. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 542+85 - 543+11 | 44'RT - 43'RT
AT&T WISCONSIN | Possible conflict with culvert replacement. | Plan Detail - PRE_35 Plan Sheet - PRE_55 | 560+71 - 560+76 | 37'RT
AT&T WISCONSIN | Possible conflict with culvert replacement. | Plan Detail - PRE_35 Plan Sheet - PRE_55 | 566+35 - 566+45 | 39'RT
AT&T WISCONSIN | Possible conflict with culvert replacement. | Plan Detail - PRE_37 Plan Sheet - PRE_55 | 576+76 - 576+83 | 39.5'RT
AT&T WISCONSIN | Possible conflict with culvert replacement. | Plan Detail - PRE_37 Plan Sheet - PRE_56 | 607+26 - 607+37 | 37.5'RT
CITY OF TWO RIVERS - SANITARY | Possible conflict with cross culvert replacement. | Plan Detail - PRE_17 Plan Sheet - PRE_38 | 26+21 | 34'RT
CITY OF TWO RIVERS - SANITARY | Possible conflict with cross culvert replacements. | Plan Detail - PRE_17 Plan Sheet - PRE_39 | 52+81 - 52+97 | 29.5'RT
CITY OF TWO RIVERS - SANITARY | Possible manhole adjustment needed due to pavement work. | Plan Detail - PRE_18 Plan Sheet - PRE_39 | 65+27 | 53.7'LT
CITY OF TWO RIVERS - SANITARY | Possible conflict with cross culvert replacements. | Plan Detail - PRE_18 Plan Sheet - PRE_39 | 65+95 - 66+06 | 53'LT
CITY OF TWO RIVERS - WATER | Possible conflict with cross culvert replacements. | Plan Detail - PRE_17 Plan Sheet - PRE_38 | 26+21 | 25'RT
CITY OF TWO RIVERS - WATER | Possible conflict with cross culvert replacements. | Plan Detail - PRE_17 Plan Sheet - PRE_39 | 52+80 - 52+96 | 34.5'LT
CITY OF TWO RIVERS - WATER | Possible conflict with cross culvert excavation and water valve. | Plan Detail - PRE_17 Plan Sheet - PRE_39 | 53+06 | 34.5'LT
CITY OF TWO RIVERS - WATER | Possible manhole adjustment needed due to pavement work. | Plan Detail - PRE_17 Plan Sheet - PRE_39 | 53+93 | 27'RT
CITY OF TWO RIVERS - WATER | Possible manhole adjustment needed due to pavement work. | Plan Detail - PRE_18 Plan Sheet - PRE_39 | 64+99 65+07 | 28.8'RT 37.5'RT
CITY OF TWO RIVERS - WATER | Possible conflict with cross culvert replacements. | Plan Detail - PRE_18 Plan Sheet - PRE_39 | 65+97 - 66+08 | 27.5'RT
FRONTIER NORTH | Possible conflict with cross culvert excavation. | Plan Detail - PRE_17 Plan Sheet - PRE_38 | 26+07 | 18'LT - 18'RT
FRONTIER NORTH | Possible conflict with box culvert replacement work. | Plan Detail - PRE_20 Plan Sheet - PRE_43 | 179+16 - 179+44 | 51.5'RT - 53'RT
FRONTIER NORTH | Possible conflict with cross culvert replacements. | Plan Detail - PRE_23 Plan Sheet - PRE_47 | 313+87 - 313+97 | 30.5'RT
FRONTIER NORTH | Possible conflict with driveway culvert replacement. | Plan Detail - PRE_24 Plan Sheet - PRE_48 | 340+71 - 341+08 | 26'RT - 26.5'RT
FRONTIER NORTH | Possible conflict with cold in place recycling work and beam guard replacement. | Plan Detail - PRE_24 Plan Sheet - PRE_48 | 343+40 - 343+41 | 23'LT - 33'RT
FRONTIER NORTH | Possible conflict with slope/ditch grading. | Plan Detail - PRE_24 Plan Sheet - PRE_48 | 343+41 - 343+46 | 29'LT - 47'LT
FRONTIER NORTH | Possible conflict with cross culvert replacement. | Plan Detail - PRE_29 Plan Sheet - PRE_52 | 472+27 - 472+56 | 37'RT - 40'RT
FRONTIER NORTH | Possible conflict with cross culvert replacement. | Plan Detail - PRE_32 Plan Sheet - PRE_54 | 530+26 - 530+38 | 22'RT
FRONTIER NORTH | Possible conflict with slope/ditch grading. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 542+80 - 543+11 543+50 - 544+09 | 39.5'RT - 47'RT 52'RT - 48'RT
FRONTIER NORTH | Possible conflict with slope/ditch grading and pedestial. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 542+80 | 39.5'RT
FRONTIER NORTH | Possible conflict with culvert replacement. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 543+11 - 543+50 | 47'RT - 52'RT
PAETEC | Possible conflict with driveway culvert replacement. | Plan Detail - PRE_20 Plan Sheet - PRE_42&43 | 177+74 - 178+19 | 34'LT - 35'LT
PAETEC | Possible conflict with box culvert replacement work. | Plan Detail - PRE_20 Plan Sheet - PRE_43 | 179+25 - 179+53 | 41'LT - 39'LT
Unknown underground- fiber optic | Possible conflict with driveway culvert replacement. | Plan Detail - PRE_24 Plan Sheet - PRE_48 | 340+53 - 341+49 | 29'LT - 27'LT
Unknown underground- fiber optic | Possible conflict with slope/ditch grading. | Plan Detail - PRE_24 Plan Sheet - PRE_48 | 343+72 - 343+99 | 51'LT - 37'LT
Unknown underground- fiber optic | Possible conflict with slope/ditch grading. | Plan Detail - PRE_28 Plan Sheet - PRE_51 | 451+82 - 454+23 | 50.5'LT - 30'LT
Unknown underground- fiber optic | Possible conflict with slope/ditch grading. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 541+97 - 543+03 543+28 - 544+20 | 40'LT 40'LT - 44'LT
Unknown underground- fiber optic | Possible conflict with slope/ditch grading. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 543+84 - 544+50 | 37'LT
Unknown underground- fiber optic | Possible conflict with culvert replacement. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 543+03 - 543+28 | 40'LT
Unknown underground- fiber optic | Possible conflict with culvert replacement. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 543+04 - 543+30 | 30'LT - 32'LT
Unknown underground- fiber optic | Possible conflict with culvert replacement. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 543+05 - 543+31 | 24'LT -24.5'LT
Unknown underground- telephone | Possible conflict with slope/ditch grading. | Plan Detail - PRE_28 Plan Sheet - PRE_51 | 452+11 - 452+61 | 34.5'RT - 30.5'RT
Unknown underground- telephone | Possible conflict with slope/ditch grading. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 541+67 - 542+58 | 31'LT - 50'LT
Unknown underground- telephone | Possible conflict with culvert replacement. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 542+89 - 543+23 | 71'LT - 77'LT
Unknown underground- telephone Ped | Possible conflict with slope/ditch grading and pedestial. | Plan Detail - PRE_28 Plan Sheet - PRE_51 | 452+31 | 39.5'RT
Unknown underground- telephone Ped | Possible conflict with slope/ditch grading and pedestial. | Plan Detail - PRE_28 Plan Sheet - PRE_51 | 453+06 | 37.5'LT
Unknown underground- telephone Ped | Possible conflict with slope/ditch grading. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 541+98 | 36.5'LT
WPS | Possible conflict with cross culvert excavation and pole. | Plan Detail - PRE_17 Plan Sheet - PRE_39 | 52+71 | 38'LT
WPS | Possible conflict with cross culvert excavation and pole. | Plan Detail - PRE_19 Plan Sheet - PRE_40 | 111+41 | 48.5'LT
WPS | Possible conflict with slope grading and pole. | Plan Detail - PRE_20 Plan Sheet - PRE_43 | 180+21 | 44'RT
WPS | Possible conflict with cross culvert excavation and pole. | Plan Detail - PRE_23 Plan Sheet - PRE_47 | 332+98 | 36'RT
WPS | Possible conflict with driveway culvert replacement and pole. | Plan Detail - PRE_24 Plan Sheet - PRE_48 | 340+57 | 38'LT
WPS | Possible conflict with slope grading and pole. | Plan Detail - PRE_24 Plan Sheet - PRE_48 | 342+80 343+61 | 37'RT 38'LT
WPS | Possible conflict with cross culvert excavation and pole. | Plan Detail - PRE_25 Plan Sheet - PRE_49 | 393+31 | 40'RT
WPS | Possible conflict with slope/ditch grading and pole. | Plan Detail - PRE_28 Plan Sheet - PRE_51 | 451+71 & 451+95 452+60 & 452+94 | 39'LT & 43'RT 41.5'RT & 38'LT
WPS | Possible conflict with slope/ditch grading. | Plan Detail - PRE_28 Plan Sheet - PRE_51 | 453+05 - 453+77 | 37'LT - 37.5'RT
WPS | Possible conflict with cross culvert excavation and pole. | Plan Detail - PRE_30 Plan Sheet - PRE_53 | 503+57 | 39'LT
WPS | Possible conflict with slope/ditch grading and pole. | Plan Detail - PRE_34 Plan Sheet - PRE_54 | 541+82 543+80 | 35'LT 48'LT