## 1640-03-02
| Station | - | Station | Offset/ Location | Design Conflict |  | C. of Westby (Elec) | C. of Westby (Water) | Mediacom (Fiber) | Midwest (Gas) | Vernon Communications Cooperative (Comm) | Xcel Energy (Elec) | Comments
Underground/ground disturbance locations:
1 | 43650 |  |  | 55' LT/ 90' RT | Culvert Lining w/ New Endwalls | 24-inch |  |  | X |  | X |  | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict likely: Construction excavation beyond endwalls may be required to install pipe liner
2 | 43750 |  |  | 40' RT | Grading/Shaping Culvert End (Shallow/minimal ground disturbance) | [7 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict unlikely: Surface/flowline restoration only
3 | 44550 |  |  | 45' LT/ 30' RT | Replace Culvert and Endwalls | 24-inch | [6 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict unlikely: Shallow culvert replacement within existing roadbed
4 | 45140 | - | 45220 | LT | Grading/Shaping Ditch (Shallow/minimal ground disturbance) | [7 empty] | Mediacom (FO): Facilities in the area, survey information shows FO on RT (south), work is on LT (north) ditch only Vernon Coop (Comm): Facilities in the area, survey information shows 65' LT (north), likely outside work area Conflict unlikely: Surface/flowline restoration only
5 | 45055.7 | - | 45607.95 | LT/RT | Reconstruct Beam Guard | [7 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict unlikely: Beam guard replacement in same/similar location, fill only
6 | 45342 |  |  | 120' LT | Extend Culvert Pipe w/ New Endwalls | 48-inch |  |  | X |  | X |  | Mediacom (FO): Facilities in the area, surveyed location near RT endwall, minimal grading expected Vernon Coop (Comm): Facilities in the area, culvert extension LT appears to cross surveyed location Conflict likely: Construction activity near/on/across utility locations, some excavation expected
7 | 46317 |  |  | 70' LT/ 50' RT | Culvert Lining w/ New Endwalls | 36-inch |  |  | X |  | X |  | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict likely: Construction excavation beyond endwalls may be required to install pipe liner
8 | 46897 |  |  | 130' LT | Extend Culvert Pipe w/ New Endwalls (Extend only to existing R/W) | 36-inch |  |  | X |  | X |  | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict likely: Construction activity to LT R/W, some excavation expected. Minimal grading expected at RT endwall
9 | 47680 |  |  | 45' RT | Repair Stone Endwall (Cattle Pass) | [7 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict unlikely: Surface/flowline restoration only
10 | 49550 |  |  | 100' LT/ 70' RT | Culvert Lining w/ New Endwalls | 48-inch |  |  | X |  | X |  | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict likely: Construction excavation beyond endwalls may be required to install pipe liner
11 | 49950 |  |  | 115' LT | Extend Culvert Pipe w/ New Endwalls | 36-inch |  |  | X |  | X | X | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Xcel Energy (Elec): Facilities in the area Conflict likely: Construction activity at LT end, some excavation expected. Minimal grading expected at RT endwall
12 | 50901.5 | - | 51357.75 | RT | Reconstruct Beam Guard | [7 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict unlikely: Beam guard replacement in same/similar location, fill only
13 | 51195 |  |  | 60' LT/ 70' RT | Culvert Lining w/ New Endwalls | 48-inch | [6 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict unlikely: Excavation to install pipe liner is limited - minimal backslopes, survey locations 15'+ away
14 | 52646 |  |  | 100' LT | Repair Culvert Pipe and Endwall (Replace 30' of pipe, same location) | 60-inch | [6 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict unlikely: Excavation limited to existing pipe/endwall location, survey locations 15'+ away
15 | 52244.5 | - | 53353.25 | LT/RT | Reconstruct Beam Guard | [7 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict unlikely: Beam guard replacement in same/similar location, fill only
16 | 54226 |  |  | 40' LT/ 60' RT | Replace Culvert and Endwalls | 24-inch | [6 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict unlikely: Shallow culvert replacement within existing roadbed
17 | 55860 |  |  | 35' LT/ 35'RT | Clean Out Culvert Debris | 24-inch | [6 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Xcel Energy (Elec): Facilities in the area Conflict Unlikely: Cleaning/flushing out pipe, minimal to no ground disturbance
18 | 56810 |  |  | 40' LT/ 60' RT | New Endwalls | 18-inch | [6 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Xcel Energy (Elec): Facilities in the area Conflict unlikely: Endwall replacement, shallow/minimal ground disturbance
19 | 63134 |  |  | 40' LT/ 40' RT | Replace Box (Cattle Pass) with Culvert | 24-inch | [6 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Xcel Energy (Elec): Facilities in the area Conflict unlikely: Culvert replacement within existing roadbed
20 | 63960 |  |  | 50' LT | New Endwall | 24-inch | [6 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Xcel Energy (Elec): Facilities in the area Conflict unlikely: Endwall replacement, shallow/minimal ground disturbance
21 | 64834 |  |  | 60' LT | Repair Culvert Pipe and Endwall (Replace 20' of pipe, same location) | 24-inch |  |  | X |  | X | X | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Xcel Energy (Elec): Facilities in the area Conflict likely: Excavation expected near utility pedestal
22 | 67580 |  |  | 30'LT/ 45' RT | New Endwalls | 24-inch | [6 empty] | Mediacom (FO): Facilities in the area Vernon Coop (Comm): Facilities in the area Xcel Energy (Elec): Facilities in the area Conflict unlikely: Endwall replacement, shallow/minimal ground disturbance
23 | 68959 |  |  | 35' RT | Clean and Reset/Tie Culvert | 24-inch | [6 empty] | City of Westby (Elec): Facilities not likely to extend to this location City of Westby (Water): Facilities not likely to extend to this location Mediacom (FO): Facilities in the area Midwest (Gas): Facilities in the area Vernon Coop (Comm): Facilities in the area Xcel Energy (Elec): Facilities in the area Conflict unlikely: Excavation to re-set culvert sections, possible replacement if necessary
24 | 70395 |  |  | 35' LT/ 40' RT | New Endwalls | 24-inch | [6 empty] | City of Westby (Elec): Facilities in the area City of Westby (Water): Facilities in the area Mediacom (FO): Facilities in the area Midwest (Gas): Facilities in the area Vernon Coop (Comm): Facilities in the area Conflict unlikely: Endwall replacement, shallow/minimal ground disturbance
Overhead Locations:
| 44150 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 44150 |  | 44250 | RT | Overhead, Vang Rd Intersection | [6 empty] | X | Mill and paving only
| 44200 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 44650 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 50050 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 50050 |  | 50200 | RT | Overhead, Volden Rd Intersection | [6 empty] | X | Mill and paving only
| 50150 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 55700 |  | 55850 | LT | Overhead, Allen Dr Intersection | [6 empty] | X | Mill and paving only
| 55730 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 56800 |  |  |  | Overhead location | [6 empty] | X | Culvert work and mill and paving
| 57580 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 60550 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 61820 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 61900 |  | 62050 | LT | Overhead, Allen Dr Intersection | [6 empty] | X | Mill and paving only
| 63485 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 64200 |  | 64350 | LT | Overhead, Spring Coulee Rd Int. | [6 empty] | X | Mill and paving only
| 64800 |  | 64900 | LT | Overhead, Lovaas Ridge Rd Int. | [6 empty] | X | Mill and paving only
| 65500 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 67550 |  | 67700 | LT | Overhead, Saugstad Rd Intersection | [6 empty] | X | Mill and paving only
| 67760 |  |  |  | Overhead location | [6 empty] | X | Mill and paving only
| 70745 |  |  |  | Overhead location |  | X | [5 empty] | Mill and paving only
General comments on DT1077 responses:
City of Westby (Elec & Water): Comment on DT1077 "Westby only has paper copy of our maps we will only have electric and water at High Echo going north approximately 300' north"
Mediacom (Fiber Optics): Comment on DT1077 "Mediacom fiber optic line along entire project route"
Midwest (Gas): Comment on DT1077 "3-inch MD PE gas main ~2000' will be involved with project" (east end/Westby)
Vernon Communications (Comm): DT1077 maps indicate facilities aling entire route. Maps appear to not line up with roadway accurately.
Xcel Energy (Elec): Overhead facilities only, no underground (no facility maps provided)