## Sheet1
Station | - | Station | Offset/ Location | Design Conflict | Alliant Energy (Gas) | Alliant Energy (Electrical) | AT&T (Comm) | ATC (Electrical) | C. of FDL (Sewer) | C. of FDL (Water) | Frontier (Comm) | Charter (Comm) | Guardian (Gas) | WE Energies (Electrical) | Comments
7666 |  |  | 28-ft LT/RT | 29x45-Inch Elliptical Culvert Pipe | X |  | X | [7 empty] | Gas: Conflict anticipated. Alliant Energy underground gas line located at culvert replacement STA 76+65 at 30-ft O/S LT from CL. Comm: Conflict anticipated with buried fiber. Buried fiber located at STA 76+65 at 28-ft O/S from CL RT located at culvert replacement. Additionally, no conflict anticipated with aerial AT&T copper/fiber located on LT side of the road. STA 76+65 at 28-ft O/S LT from CL. Electrical: No conflict anticipated with aerial WE Energies located on RT side of road.
12135 |  |  |  | 24-Inch Concrete Culvert Pipe | X |  | X | [7 empty] | Gas: Conflict anticipated. Alliant Energy underground gas line located at culvert replacement STA 121+35 at 28-ft O/S from CL LT. Comm: Conflict anticipated. Buried AT&T Copper and fibert at STA 121+35 at 30-ft O/S from CL RT. Electrical: No conflict anticipated. Overhead We Energies on RT. Pole is close, but shouldn't be in the way of culvert grading
20022 |  |  |  | 48-Inch Concrete Culvert Pipe | X |  | X | [7 empty] | Gas: Conflict anticipated. Alliant Energy underground gas line located at culvert replacement STA 200+22 at 29-ft O/S from CL LT. Electrical: No conflict anticipated. Overhead We Energies on RT. Pole is close, but shouldn't be in the way of grading. Comm: Conflict anticipated. Buried AT&T copper and fibert located at culvert replacment at STA 200+22 at 29-ft O/S from CL on RT.
24268 |  |  | LT | 15-Inch Corrugated Steel Pipe | [10 empty] | No conflicts anticipated
24270 | - | 25020 |  | Concrete Barrier |  |  | X | [7 empty] | Comm: Overhead AT&T copper/fiber at the intersection of STH 175 and CTH B, guy wires and pole are within the area behind the guardrail that should be free of fixed objects.
24965 | - | 26352 | RT | Concrete Barrier |  |  | X |  |  |  |  | X |  | X | Electrical: Overhead We Energies on RT full length of this barrier section. Pole at STA 262+97 O/S 26.0-ft from C/L will be near grading. Guy wires near culvert and driveway removal at STA 251+25. Comm: Buried AT&T copper; buried AT&T fiber; AT&T fiber handhole/vault near culvert removal and grading/ditching (STA 264+40 40-FT O/S from CL); Charter Communication fiber line into Buechel Stone Corp Other: Culvert pipe located at STA 250+57 to 251+15 at 20-ft O/S from CL RT.
26070 | - | 27037 | LT | Concrete Barrier |  |  | X | [7 empty] | Comm: AT&T buried copper near barrier section. Cannot specify exact station with system map. Approx. STA 270+20 LT there are Telephone and OH line at beam guard end treatment. Fixed object behind EAT.
31708 |  |  |  | 36-Inch Concrete Culvert Pipe |  |  | X | [7 empty] | Comm: Conflict anticipated. Buried AT&T copper and fiber. Both located at STA 317+08 at 27-ft O/S from C/L.
33325 | - | 33800 | LT | Beam Guard |  | X | X | [7 empty] | Electrical: No conflict anticipated. Overhead Alliant Energy 26-ft LT of CL. Pole is near grading for beam guard but should not be an issue. Comm: Conflict anticipated. Buried AT&T copper is in the area of some grading work.
33470 | - | 33755 | RT | Beam Guard |  |  | X | [7 empty] | Comm: Conflict anticipated. Buried AT&T copper; buried AT&T fiber. Both located 30-ft O/S from C/L. Within limits of beam guard installation and grading. Electrical: No conflict anticipated with Alliant Energy OH lines.
33489 | - | 33569 | LT | 18-Inch Corrugated Steel Driveway Pipe |  |  | X | [7 empty] | Comm: Conflict anticipated. Underground AT&T copper located 5-ft from end of culvert replacement.
34314 |  |  |  | 30-Inch Concrete Culvert Pipe | [10 empty] | No conflicts anticipated. Comm AT&T buried fiber and coppe located outside of ROW. Also WE Energies OH electrical is outside of ROW.
35985 | - | 36495 | RT | Beam Guard |  |  | X | [7 empty] | Comm: Conflict anticipated. AT&T buried copper crosses at approx STA 361-80 which may conflict with beamguard post installation and associated grading. There is buried AT&T copper and fiber running along the length of the RT side but both are outside of the ROW. Water: No conflict anticipated. Buried C. of FDL 16-inch PVC main outside of ROW. Sanitary: Buried C. of FDL sewer structure and line at STA 365+15 15-ft O/S from CL. Shoulder grading will be occuring in this area but will work around the structure. Electrical: No conflict anticipated. Buried and OH located at STA 365+30 at 31-ft O/S from C/L. Shoulder grading will not impact utilities here. Gas: No conflict anticipated. Buried Alliant gas
36180 | - | 36610 | LT | Beam Guard | X? |  | X | [5 empty] | X? |  | Comm: Conflict anticipated. AT&T buried copper crosses at approx STA 361-80 which may conflict with beamguard post installation and associated grading. Gas: Conflict anticipated at STA 365+75 at 18-ft O/S from C/L LT. Gas line appears to be a service line to a resident. Buried gas line located at beam guard post installation - see standard detail drawing for beam guard post spacing. Electrical: No conflict anticipated. OH Electrical lines running the length of the LT corridor but is located outside of the ROW. Electrical line shown on C3D but cannot find on a system map.