## Sheet1
Utility Conflict
Number | Location and Description
1 | TV Pedestal STA 444+78 Offset 36' RT located where new endwall on the eastside of C-20-0147 will be installed, will need to be relocated
2 | Underground TV Line crossing ceterline at STA 444+83
3 | Overhead lines on westside at off set of 63' along work zone for C-20-0147
4 | Underground telephone line on the east side of C-20-0148 would be in the way if a diversion channel is used in construction
5 | Overhead lines on the westside of USH 151 offset about 73' crosses the construction limits of the slope and pipe extension at pipe C-20-0148
6 | Overhead line power poles at STA 465+58 offset 63' Left, STA 467+66 offset 74' left, and STA 469+66 offset 80'
7 | Telephone line STA 466+45 offset 98' to STA 467+44 offset 91'