{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":64,"n_cols":6,"rows_kept":64,"cut":false,"hidden":false,"merged":[[5,0,5,5],[6,0,6,5],[7,0,7,5],[0,0,0,5],[1,0,1,5],[4,0,4,5],[3,0,3,5],[10,2,10,3],[11,2,11,3],[12,2,12,3],[13,2,13,3],[14,2,14,3],[15,2,15,3],[16,2,16,3],[23,2,23,3],[17,2,17,3],[18,2,18,3],[19,2,19,3],[20,2,20,3],[21,2,21,3],[22,2,22,3],[33,2,33,3],[39,2,39,3],[40,2,40,3],[24,2,24,3],[25,2,25,3],[26,2,26,3],[27,2,27,3],[28,2,28,3],[29,2,29,3],[31,2,31,3],[52,2,52,3],[53,2,53,3],[46,2,46,3],[47,2,47,3],[48,2,48,3],[49,2,49,3],[42,2,42,3],[35,2,35,3],[37,2,37,3],[50,2,50,3],[51,2,51,3],[43,2,43,3],[44,2,44,3],[45,2,45,3],[41,2,41,3],[54,0,54,5],[55,2,55,3],[56,2,56,3],[57,2,57,3],[58,2,58,3],[64,0,64,5],[62,0,62,5],[59,2,59,3],[60,0,60,5]]}
["Potential Utility Conflicts"]
["October 2022"]
[]
["Project ID 4075-40-00"]
["W. Wisconsin Ave, T. of Grand Chute"]
["Casaloma Dr. - N. Badger Ave"]
["STH 96"]
["Outagamie County"]
[]
["Utility Name","Utility Type","Potential Conflict",null,"Station","Location"]
["Town of Grand Chute","WATER","Hydrant/valve",null,"102+57","43.2' RT"]
["Town of Grand Chute","WATER","Hydrant/valve",null,"104+68","37.0' RT"]
["Town of Grand Chute","WATER","Hydrant/valve",null,"108+67","38.1' RT"]
["Town of Grand Chute","WATER","Valve",null,"121+03","87.4' LT"]
["Town of Grand Chute","WATER","Hydrant",null,"134+41","48.4' RT"]
["Town of Grand Chute","WATER","Hydrant/valve",null,"161+38","43.2' LT"]
["Town of Grand Chute","WATER","Hydrant/valve",null,"183+62","58.1' LT"]
[]
["Town of Grand Chute","SANITARY","Manhole/existing line will be under new sidewalk",null,"128+27","68.3' LT"]
["Town of Grand Chute","SANITARY","Possible conflict with manhole",null,"130+83","82.5' LT"]
["Town of Grand Chute","SANITARY","Manhole in base patching area/line may be under proposed sidewalk at intersection (mapping not clear on this)",null,"160+47","32.1' LT"]
["Town of Grand Chute","SANITARY","Manhole in proposed sidewalk/small portion of line runs under proposed sidewalk",null,"191+08","45.7' LT"]
["Town of Grand Chute","SANITARY","Manhole in concrete pavement repair area",null,"201+52","37.7' LT"]
["Town of Grand Chute","SANITARY","Manhole in concrete pavement repair area",null,"204+88","34.9' LT"]
[]
["ANR Pipeline","GAS","8\" and 16\" pipeline crossing STH 96 under new sidewalk - no conflict anticipated",null,"160+46/160+75","Crossing 96"]
[]
["AT&T WI","TELEPHONE","Line impacted by storm sewer/inlet removal/replacement",null,"103+98","8.3-100.7' LT"]
["AT&T WI","TELEPHONE","Line crosses under proposed sidewalk",null,"120+37-120+60","125.5 LT"]
["AT&T WI","TELEPHONE","Line runs under proposed sidewalk/manhole may be in conflict with proposed sidewalk",null,"120+76-121+89","89.5 LT"]
["AT&T WI","TELEPHONE","Line impacted by storm sewer/inlet removal/replacement",null,"126+13-126+45","15.3-57.0' LT"]
["AT&T WI","TELEPHONE","Line runs under proposed sidewalk",null,"134+00","77.7' LT"]
["AT&T WI","TELEPHONE","Line impacted by storm sewer removal/replacement",null,"138+94","1 LT-7' RT"]
["AT&T WI","TELEPHONE","Line impacted by storm sewer/inlet removal/replacement",null,"146+15-146+84","39.7 LT-17.3' RT"]
["AT&T WI","TELEPHONE","Line impacted by storm sewer removal/replacement",null,"151+43","1.5 LT-6.5' RT"]
["AT&T WI","TELEPHONE","Line impacted by storm sewer/inlet removal/replacement and intersection improvements",null,"154+39-155+62","0-13.5' LT"]
["AT&T WI","TELEPHONE","Line runs under proposed sidewalk",null,"166+33","46.5' RT"]
["AT&T WI","TELEPHONE","Line runs under proposed sidewalk",null,"181+39","59.0' LT"]
["AT&T WI","TELEPHONE","Line runs under proposed sidewalk/curb ramp improvements",null,"192+25-193+40","33.0' RT"]
[]
["Spectrum Charter","FIBER OPTIC","Line runs under proposed curb ramp/sidewalk",null,"111+18-111+38","67.8' RT"]
["Spectrum Charter","FIBER OPTIC","Line runs under proposed curb ramp/sidewalk",null,"112+16-112+42","69.3' RT"]
["Spectrum Charter","FIBER/COAX","Line runs under proposed sidewalk",null,"134+02","75.9' LT"]
["Spectrum Charter","FIBER/COAX","Line runs under proposed curb ramp/sidewalk",null,"134+33","40.8' RT"]
["Spectrum Charter","FIBER/COAX","Line runs under proposed sidewalk",null,"157+82-158+02","48.5' RT"]
["Spectrum Charter","FIBER/COAX","Line crosses STH 96 in five (5) locations between Rexford and N. Badger - crossings under proposed sidewalk",null,"Exact stations unknown"]
[]
["WE Energies","ELECTRIC (UNDERGROUND)","Line is in area of new sidewalk/curb ramp",null,"101+82-102+23","52.8' RT"]
["WE Energies","ELECTRIC (UNDERGROUND)","Line runs throught intersection of Greenville Dr. (GV) and mall entrance.  Lines run under curb ramp improvements",null,"110+69-112+42","90 LT-79' RT"]
["WE Energies","ELECTRIC (UNDERGROUND)","Lines run in all quadrants of I 41 ramps/STH 96.  Lines run under curb ramp improvements",null,"125+00-130+00","Varies"]
["WE Energies","ELECTRIC (UNDERGROUND)","Lines run in all quadrants of Bluemound/STH 96.  Lines run under curb ramp improvements",null,"153+25-154+75","Varies"]
["WE Energies","ELECTRIC (OVERHEAD)","4 guy wires in conflict with proposedsidewalk in this station range",null,"155+24-157+94","Varies - LT"]
["WE Energies","ELECTRIC (OVERHEAD)","4 poles, 2 guy wires in conflict with proposed sidewalk in this station range",null,"160+90+170+70","45' LT"]
["WE Energies","ELECTRIC (OVERHEAD)","Poles and guy wires in conflict with proposed sidewalk in this station range",null,"173+80-End project","47' LT"]
[]
["WE Energies","GAS","Line crosses under proposed sidewalk",null,"120+55","102' LT"]
["WE Energies","GAS","Line runs between existing curb and gutter and proposed sidewalk - within excavation limits",null,"126+34-134+44","79' LT"]
["WE Energies","GAS","Line runs under proposed sidewalk",null,"155+48-179+12","43' LT"]
["WE Energies","GAS","Line runs under proposed sidewalk",null,"186+57-188+50","60' LT"]
["WE Energies","GAS","Line runs under proposed sidewalk",null,"192+15-End project","44' LT"]
[]
["WIN",null,"Line crosses STH 96 just east of Casaloma Drive. Exact location unknown.  Line runs under proposed sidewalk on south side of STH 96."]
[]
["CenturyLink",null,"Aerial facilities at the intersection of Bluemound/STH 96.  Exact location unknown.  Curb ramps/sidewalk/intersection improvements may affect line."]