{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":14,"n_cols":7,"rows_kept":14,"cut":false,"hidden":false,"merged":[[2,0,2,6]]}
["ID 4085-67-00/71; STH 32; New Holstein - Chilton; Altona Ave - USH 151; Calumet County - Potential Utility Conflicts"]
[]
["Potential Direct Conflicts"]
["Conflict","STA","Offset","Utility Company","Utility","Description","WisDOT Construction Activity"]
[1,"203+72 - 204+37","32' - 52' RT","WPS","Gas","Buried gas line","Culvert replacement and associated grading"]
[2,"203+72 - 204+37","42' LT","NET LEC","Communications","Buried fiber optic line","Culvert replacement and associated grading"]
[3,"242+08 - 242+76","31' - 55' RT","WPS","Gas","Buried gas line","Culvert replacement and associated grading"]
[4,"242+08 - 242+76","42' LT","NET LEC","Communications","Buried fiber optic line","Culvert replacement and associated grading"]
[5,"243+93 - 245+77","25' - 56' RT","WPS","Gas","Buried gas line","Cattle pass removal and ditch re-grading"]
[6,"245+10 - 245+77","39' LT","NET LEC","Communications","Buried fiber optic line","Cattle pass removal"]
[7,"260+48 - 261+16","23' - 48' RT","WPS","Gas","Buried gas line","Culvert replacement and associated grading"]
[8,"260+48 - 261+16","41' LT","NET LEC","Communications","Buried fiber optic line","Culvert replacement and associated grading"]
[9,"269+76 - 270+44","20' RT","WPS","Gas","Buried gas line","Culvert replacement and associated grading"]
[10,"269+76 - 270+44","41' LT","NET LEC","Communications","Buried fiber optic line","Culvert replacement and associated grading"]