{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":15,"n_cols":6,"rows_kept":15,"cut":false,"hidden":false,"merged":[[6,0,6,5],[7,0,7,5],[0,0,0,5],[2,0,2,5],[3,0,3,5],[4,0,4,5],[5,0,5,5],[9,0,9,1]]}
["Potential Utility Conflicts\nAugust 23, 2021"]
[]
["Project ID: 4430-21-00/71"]
["Sturgeon Bay - Egg Harbor"]
["Egg Harbor Rd - Mid JCT 42/57"]
["STH 42"]
["Door County"]
["Prepared by Doug Kirst"]
[]
["Location",null,"Operation","Risk of Conflict","Utility","Comments"]
["STA.","General"]
["99-50 to 102+50 RT","Right side of STH 42","Grading and Guardrail","Moderate","WPS-Gas","Determine depthof gas  line to see if it is inconflict with grading. Should not be in conflict with guardrail posts."]
["101+10 LT & RT","Underground line that crosses STH 42","Grading and Guardrail","Moderate","Underground Utility (unknown)","Determine if Telephone line is within 18-inches  of grading depth. Guardrail post location should be able to work around line."]
["101+10 RT","Power pole RT side of STH 42","Grading and Guardrail","Low","WPS Pole","Work operations should be able to work around guy wire and pole."]
["144+00 - 2+00 LT & RT","STH 42 NB and SB at Mid JCT 42/57","Mill and overlay - C&G spot replacement","Low","Signal Loops, Electricity","Loops should be in pavement, not a conflict. C&G to be repalced in kind."]