{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Potential Utility Conflicts"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Potential Utility Conflicts","index":0,"n_rows":46,"n_cols":14,"rows_kept":46,"cut":false,"hidden":false,"merged":[]}
["Potential Utility Conflict #","General Location","Reference Alignment","Station","to","Station","Offset","Offset Distance","Offset Distance 2","Utility Type","Underground/Overhead/Powerpole/Pedestool/Hydrant/Valve","Utility Owner","Notes","In TLE, PLE, or FEE?"]
[1,"Castle Dr./STH 114 SE Curb Ramp","STH 114",39671,"-",39715,"RT",44,38,"TV","Underground","Spectrum","Check Depth","No"]
[2,"Castle Dr./STH 114 SE Curb Ramp","STH 114",39671,"-",39715,"RT",44,38,"TV","Underground","Spectrum","Check Depth","No"]
[3,"Castle Dr./STH 114 SE Curb Ramp","STH 114",39671,"-",39715,"RT",44,38,"TV","Underground","Spectrum","Check Depth","No"]
[4,"Castle Dr./STH 114 SE Curb Ramp","STH 114",39692,"-",39716,"RT",25,25,"Water","Underground","Village of Sherwood","Check Depth","No"]
[5,"Condon Rd./STH 114 SW Curb Ramp","STH 114",41065,"-",39715,"RT",27,27,"Water","Underground","Village of Sherwood","Check Depth","No"]
[6,"Condon Rd./STH 114 SW Curb Ramp","STH 114",41085,"-","-","RT",38,null,"OH-PP","Powerpole/light","We Engeries-Electric","In proposed SW","No"]
[7,"Condon Rd./STH 114 SE Curb Ramp","STH 114",41132,"-",41180,"RT",28,29,"Water","Underground","Village of Sherwood","Check Depth","No"]
[8,"condon Rd./STH 114 SE Curb Ramp","STH 114",41134,"-","-","RT",29,null,"Water","Water Valve","Village of Sherwood","In proposed C&G/Roadway","No"]
[9,"Stumpf Ave/STH 114 NW Curb Ramp","STH 114",41687,"-",41714,"LT",31,33,"G","Underground","We Engeries-Gas","Check Depth","No"]
[10,"Stumpf Ave/STH 114 NW Curb Ramp","STH 114",41688,"-",41695,"LT",34,35,"T","Underground","Unknown (TDS Telecom?)","Check Depth","No"]
[11,"Stumpf Ave/STH 114 NW Curb Ramp","STH 114",41691,"-",41709,"LT",26,25.5,"FO","Underground","Nsight/Net-Lec","Check Depth","No"]
[12,"Stumpf Ave/STH 114 NW Curb Ramp","STH 114",41702,"-","-","LT",27,null,"G","Gas Valve","We Energies-Gas","In proposed SW/DWF","No"]
[13,"Stumpf Ave/STH 114 NW Curb Ramp","STH 114",41711,"-","-","LT",47,null,"Water","Hydrant","Village of Sherwood","Edge of Grading","No"]
[14,"Stumpf Ave/STH 114 NE Curb Ramp","STH 114",41749,"-",41789,"LT",31,33,"G","Underground","We Energies-Gas","Check Depth","No"]
[15,"Stumpf Ave/STH 114 NE Curb Ramp","STH 114",41755,"-",41786,"LT",24,24,"FO","Underground","Nsight/Net-Lec","Check Depth","No"]
[16,"Stumpf Ave/STH 114 SE Curb Ramp","STH 114",41749,"-",41787,"LT",25,25,"Water","Underground","Village of Sherwood","Check Depth","No"]
[17,"Harrison St/STH 114 SW Curb Ramp","STH 114",41976,"-",41997,"RT",23,23,"Water","Underground","Village of Sherwood","Check Depth","No"]
[18,"Harrison St/STH 114 SW Curb Ramp","STH 114",41998,"-","-","RT",24,null,"San","Manhole","Village of Sherwood","In Roadway","No"]
[19,"Harrison St/STH 114 SW Curb Ramp","STH 114",41998,"-",42014,"RT",24,41,"San","Underground","Village of Sherwood","Check Depth","No"]
[20,"Harrison St/STH 114 SE Curb Ramp","STH 114",42066,"-",42065,"RT",22,38,"G","Underground","We Energies-Gas","Check Depth","No"]
[21,"Harrison St/STH 114 SE Curb Ramp","STH 114",42066,"-",42090,"RT",22,21,"Water","Underground","Village of Sherwood","Check Depth","No"]
[22,"Meehl St/STH 114 SW Curb Ramp","STH 114",42123,"-",42162,"RT",20,21,"Water","Underground","Village of Sherwood","Check Depth","No"]
[23,"Meehl St/STH 114 NW Curb Ramp","STH 114",42131,"-",42157,"LT",26,26,"FO","Underground","Nsight/Net-Lec","Check Depth","No"]
[24,"Meehl St/STH 114 NW Curb Ramp","STH 114",42137,"-",42162,"LT",33,36,"G","Underground","We Energies-Gas","Check Depth","No"]
[25,"Meehl St/STH 114 NE Curb Ramp","STH 114",42201,"-",42233,"LT",29,28,"G","Underground","We Energies-Gas","Check Depth","No"]
[26,"Meehl St/STH 114 NE Curb Ramp","STH 114",42204,"-",42233,"LT",25,26,"FO","Underground","Nsight/Net-Lec","Check Depth","No"]
[27,"Meehl St/STH 114 NE Curb Ramp","STH 114",42208,null,"-","LY",35,null,"OH-PP","Powerpole/light","We Energies-Electric","At Edge of Proposed Grading","Yes"]
[28,"CTH M/STH 114 NE Curb Ramp","STH 114",42402,"-",42414,"LT",25,26,"FO","Underground","Nsight/Net-Lec","Check Depth","No"]
[29,"CTH M/STH 114 NE Curb Ramp","STH 114",42414,"-",42428,"LT",53,44,"Water","Underground","Village of Sherwood","Check Depth","Yes"]
[30,"CTH M/STH 114 NE Curb Ramp","STH 114",42411,"-","-","LT",46,null,"MH","Utility Manhole","Unknown","In sidewalk to be removed","No - close"]
[31,"CTH M Intersection Island","STH 114",42455,"-",42491,"LT",31,43,"FO","Underground","Nsight/Net-Lec","Check Depth","No"]
[32,"CTH M Intersection Island","STH 114",42468,"-",42481,"LT",61,51,"San","Underground","Village of Sherwood","Check Depth","No"]
[33,"CTH M/STH 114 East Curb Ramp","STH 114",42474,"-",42480,"LT",78,72,"Water","Underground","Village of Sherwood","Check Depth","No"]
[34,"CTH M/STH 114 East Curb Ramp","STH 114",42478,"-",42495,"LT",84,70,"G","Underground","We Energies-Gas","Check Depth","No"]
[35,"CTH M/STH 114 SW Curb Ramp","STH 114",42467,"-",42481,"RT",37,37,"G","Underground","We Energies-Gas","Check Depth","No"]
[36,"Base Patching","STH 114",42760,null,42810,"RT",0,15,"Water","Underground","Village of Sherwood","Check Depth","No"]
[38,"Midblock Crossing East Curb Ramp","STH 114",43041,"-",43067,"LT",24,25,"G","Underground","We Energies-Gas","Check Depth","No"]
[39,"CTH B/STH 114 NE Curb Ramp","STH 114",43730,"-",43750,"LT",25,27,"G","Underground","We Energies-Gas","Check Depth","No"]
[40,"CTH B/STH 114 NE Curb Ramp","STH 114",43731,"-",43754,"LT",30,30,"FO","Underground","Nsight/Net-Lec","Check Depth","No"]
[41,"CTH B/STH 114 SE Curb Ramp","STH 114",43802,"-",43842,"LT",32,33,"FO","Underground","Nsight/Net-Lec","Check Depth","No"]
[42,"CTH B/STH 114 SE Curb Ramp","STH 114",43810,"-",43845,"LT",25,26,"G","Underground","We Energies-Gas","Check Depth","No"]
[43,"Forest Ave/STH 114 NW Curb Ramp","STH 114",45023,"-",45048,"RT",28,28,"San","Underground","Village of Sherwood","Check Depth","No"]
[44,"Forest Ave/STH 114 NW Curb Ramp","STH 114",45051,"-",45051,"RT",31,40,"G","Underground","We Energies-Gas","Check Depth","No"]
[45,"Forest Ave/STH 114 NW Curb Ramp","STH 114",45056,"-",45061,"RT",55,56,"T","Underground","Unknown (TDS Telecom?)","Check Depth","No"]
[46,"Frost Heave Repair","STH 114","466+91","-",46748,"LT",47,48,"FO","Underground",null,"Check Depth","No"]