**DT 1078 SUPPLEMENT TO UTILITIES**

**POTENTIAL CONFLICTS WITH PLAN**

9170-12-71

STH 32

Gillett – Mountain

Trinity Church Road – CTH AA

Oconto County

Generated by Ken Baierl, designer, for DT 1078 Submittal, 4.15.2020

**Potential Utility Conflicts**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **GENERAL LOCATION** | **STATION** | **OFFSET** | **PROJECT WORK** | **UTILITIES IMPACTED** |
| 0.4 miles west of CTH Z | 440+35 | RT | Culvert replacement. | Fiberoptic line and nearest gas line. |
| 0.5 miles west of CTH Z | 445+90 | RT | Culvert replacement. | Fiberoptic line and both gas lines. |
| 0.6 miles west of CTH Z | 452+15 | RT | Culvert replacement. | Fiberoptic line and nearest gas line. **\*\*\* NOTE:** The existing FO line was trenched into the existing culvert when it was installed **\*\*\*** |
| In front of water tower. | 461+64 | LT | None. | Water valve needs to be flush with the ground (existing is a hazard). |
| 1.0 mile west of CTH Z | 475+70 | RT | Culvert replacement. | Fiberoptic line. |
| 1.1 miles west of CTH Z | 479+80 | RT | Culvert end replacement. | Fiberoptic line. |
| 1.3 miles west of CTH Z | 487+45 | LT | Culvert replacement. | Both telephone lines. |
| **GENERAL LOCATION** | **STATION** | **OFFSET** | **PROJECT WORK** | **UTILITIES IMPACTED** |
| 1.3 miles west of CTH Z | 487+85 | RT | Culvert replacement. | Fiberoptic line and gas line. |
| 0.1 miles west of CTH V | 504+25 | LT | Culvert replacement. | Both telephone lines. |
| 0.1 miles west of CTH V | 504+25 | RT | Culvert replacement. | Both fiberoptic lines and gas line. |
| 0.5 miles west of CTH V | 524+90 | RT | Culvert replacement | TV line. |
| Krueger St – Northeast | 144+57 & 144+75 | RT | Curb ramp replacement | Two water valves. |
| Krueger St – Southwest | 145+21 | LT | Curb ramp replacement | Water valve. |
| Mill St – Southeast | 148+61 | LT | Curb ramp replacement | Water valve. |
| Mill St - Northeast | 148+54 | RT | Curb ramp replacement | Power pole. |
| Mill St – Northwest | 149+01 | RT | Curb ramp replacement | Fire hydrant. |
| Heasley St – Northwest | 154+80 & 155+00 | RT | Storm sewer replacement | Power pole. |
| Heasley St – Northwest | 154+89 & 154+92 | RT | Curb ramp replacement | Fire hydrant and water valve. |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **GENERAL LOCATION** | **STATION** | **OFFSET** | **PROJECT WORK** | **UTILITIES IMPACTED** |
| Burk St – Southeast | 159+02 | LT | Curb ramp replacement | Power pole. |
| Burk St – Northeast | 159+03 | RT | Curb ramp replacement | Fire hydrant. |
| Burk St – Northwest | 159+50 | RT | Curb ramp replacement | Power pole. |
| Railroad St – Northwest | 162+35 | RT | Curb ramp replacement | Fire hydrant. |
| Center St - Northeast | 165+64 & 165+73 | RT | Curb ramp replacement | Power pole and fire hydrant. |
| Jackson St – Southwest | 166+37 | LT | Curb ramp replacement | Power pole. |
| Bridge over Oconto River | 172+55 | RT | Concrete surface drain | Both fiberoptic lines and telephone line. |
| Bridge over Oconto River | 174+75 | RT | Concrete surface drain | Both fiberoptic lines and telephone line. |
| 0.4 miles west of CTH M | 272+90 – 273+30 | LT | Culvert pipe replacement | Fiberoptic line. |
| 0.3 miles north of Central Rd (S Junction) | 847+50 | LT | Culvert pipe repairs | Telephone line. |
| 0.8 miles north of Central Rd (S Junction) | 872+50 | LT | Culvert pipe replacement. | Telephone line. |
| 0.1 miles north of Central Rd (N Junction) | 933+15 | RT | Culvert pipe replacement | Fiberoptic & telephone lines. |

9190-28-71

STH 32

Suring - Breed

South Branch Oconto River Bridge, Oconto County

The only two potential conflict points:

* + The guardrail work gets within 5’ of the telephone line near 337+24 RT
  + The riprap works gets within 3’ of the telephone line near 340+52 RT

The project is a bridge overlay project. Primary excavation activities include:

* Guardrail replacement
* Storm sewer removal (north bridge abutment)
* Flume and riprap placement