CONSTRUCTION STAGE 2

+ OBJECTIVES

-CONSTRUCT WESTBOUND STH 23 FROM STA 250'WB'+00 TO STA 384'WB'+00.

-CONSTRUCT TAFT RD INTERSECTION

-CONSTRUCT TOWER RD INTERSECTION (NORTH)

-CONSTRUCT POPLAR RD INTERSECTION (NORTH)

-CONSTRUCT OLD PLANK TRAIL

-CONSTRUCT CULVERTS IN PROJECT STAGE 2.

+ STATUS OF PUBLIC USAGE

-EASTBOUND/WESTBOUND TRAFFIC TO REMAIN IN EXISTING LANES.

-TAFT RD, TOWER RD AND POPLAR ROAD ARE TO MAINTAIN PUBLIC CROSS-TRAFFIC WITH NO ACCESS TO THE PROJECT. CLOSURE OF THESE SIDE ROADS ARE RESTRICTED TO 14 CONSECUTIVE CALENDAR DAYS, AND NO CONSECUTIVE INTERSECTIONS TO STH 23 SHALL BE 	CLOSED SIMULTANEOUSLY.

+ REMOVAL/DEMOLITION THIS STAGE

-CULVERT, OLD STRUCTURE, AND PAVEMENT REMOVAL STAGE 2.

+ CONSTRUCTION CRITICAL FOR NEXT STAGE

-CONSTRUCT WESTBOUND STH 23 FROM STA 250'WB'+00 TO STA 384'WB'+00.

-CONSTRUCT TAFT RD INTERSECTION

-CONSTRUCT TOWER RD INTERSECTION (NORTH)

-CONSTRUCT POPLAR RD INTERSECTION (NORTH)

-CONSTRUCT CULVERTS IN PROJECT STAGE 2.

CONSTRUCTION STAGE 3B

+OBJECTIVES

-CONSTRUCT EASTBOUND STH 23 FROM STA 250'EB'+00 TO STA 388'EB'+66.

-CONSTRUCT RICHARD RD INTERSECTION

-CONSTRUCT TOWER RD INTERSECTION (SOUTH)

-CONSTRUCT POPLAR RD INTERSECTION (SOUTH)

-CONSTRUCT OLD PLANK TRAIL

-CONSTRUCT CULVERTS IN PROJECT STAGE 3B.

+STATUS OF PUBLIC USAGE

-EASTBOUND/WESTBOUND TRAFFIC TO BE ON RECENTLY CONSTRUCTED (STAGE 1) WESTBOUND LANES.

-RICHARD RD, TOWER RD AND POPLAR RD ARE TO MAINTAIN PUBLIC CROSS-TRAFFIC WITH NO ACCESS TO THE PROJECT. CLOSURE OF TOWER RD AND POPLAR ROAD IS RESTRICTED TO 14 CONSECUTIVE CALENDAR DAYS.  RICHARD RD IS NOT TO FULLY CLOSE. TOWER RD 	AND POPLAR RD INTERSECTIONS TO STH 23 SHALL NOT BE CLOSED SIMULTANEOUSLY.

+REMOVAL/DEMOLITION THIS STAGE

-CULVERT, OLD STRUCTURE, AND PAVEMENT REMOVAL STAGE 3B.

+CONSTRUCTION CRITICAL FOR NEXT STAGE

-CONSTRUCT EASTBOUND STH 23 FROM STA 250'EB'+00 TO STA 388'EB'+66.

-CONSTRUCT RICHARD RD INTERSECTION

-CONSTRUCT TOWER RD INTERSECTION (SOUTH)

-CONSTRUCT POPLAR RD INTERSECTION (SOUTH)

-CONSTRUCT OLD PLANK TRAIL

-CONSTRUCT CULVERTS IN PROJECT STAGE 3B

CONSTRUCTION STAGE 4

+OBJECTIVES

-CONSTRUCT EASTBOUND STH 23 FROM 388'EB'+66 TO 397'EB'+00

-CONSTRUCT RICHARD RD MEDIAN CROSSING

-CONSTRUCT TOWER RD MEDIAN CROSSING

-CONSTRUCT STORM SEWER IN PROJECT STAGE 4.

+STATUS OF PUBLIC USAGE

-EASTBOUND/WESTBOUND TRAFFIC TO BE ON FULLY CONSTRUCTED EASTBOUND/WESTBOUND LANES.  LANE CLOSURES WILL BE NEEDED TO COMPLETE MILL AND OVERLAY SECTION FROM 388'EB'+66 TO 397'EB'+00.

+REMOVAL/DEMOLITION THIS STAGE

-REMOVE ALL TEMPORARY MEDIAN CONNECTIONS CONSTRUCTED IN PREVIOUS STAGES.

-REMOVE EAST CROSSOVER.