## Instructions
Instructions for Contract Time for Completion Spreadsheet
See FDM 19-10-30 for general information on the Contract Time for Completion analysis.
1. The form is locked. Information can only be entered in the yellow shaded cells.
2. Enter project information at the top of the form.
3. Enter controlling items on left side of page under Item Analysis.
4. Enter item quantities for each stage (all stages do not need to be used).
5. Enter item units and production rates (see FDM 19-10 Attachment 30.3 for example rates).
6. Enter begin day for each item and stage (the end date will be calculated automatically). Tip: You can use a formula here, for instance to start Item 2 when Item 1 is done, you would enter =W30 in cell V31. That way if you add 2 days to Item 1, the start date for Item 2 will automatically adjust by 2 days.
7. If the default "Stage 1", "Stage 2", etc., doesn't work for your project, you can edit them in the yellow shaded cells. The legend and other column headings will update automatically.
8. Enter the construction year at the bottom of the page to automatically fill out all the Begin and End dates for each month. Then, delete Begin and End dates for months before the start date or after the completion date. Change the Begin date for the applicable month to the actual probable date of beginning and change the End date for the applicable month to the anticipated completion date. Under the Month column, delete names for unused months (those with no working days) to remove the labels from the Gantt Chart.
9. Enter number of holidays days each month.
10. Enter probable working day percentage based on the work type (see FDM 19-10 Attachment 30.2).
11. Enter remarks as necessary.
12. Enter number of calendar days, working days, and completion date based on the time of completion chart.
13. To get rid of extra days (blank space) on the right side of the Gantt Chart, right click on the top axis and select "Format Axis". Under "Axis Options", Change "Maximum" from "Auto" to "Fixed" and set the value to the total number of working days for the contract.
Contact David Layton (david.layton@dot.wi.gov) with any suggested revisions to this form.
Release Notes
10/2009 - Fixed Stage 3 formula error
01/2010 - Added ability to rename stages.
09/2010 - Updated FDM links to account for FDM file revisions.

## Blank Time Chart
CONTRACT TIME FOR COMPLETION
Wisconsin Department of Transportation DT1923 04/2011
Project ID | 6210-00-73/6210-01-60 |  |  | Highway | STH 49 |  |  |  | Project Title | Ripon - Auroraville | [12 empty] | Date of Letting | 2019-05-14
Work Type | HMA Overlay |  |  | County | Waushara |  |  |  | Project Limits | Green Lake County Line - STH 21 | [12 empty] | Probable Date of Beginning | 2019-06-17
ITEM ANALYSIS
Item |  | Contract Quantity per Stage |  |  |  |  | Total Quantity | Unit | Production Rate |  | Working Days (per Stage) | [5 empty] | Stage 1 |  | Stage 2 |  | Stage 3 |  | Stage 4 |  | Stage 5
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | [10 empty] | Begin | End | Begin | End | Begin | End | Begin | End | Begin | End | Gap 1 | Gap 2 | Gap 3 | Gap 4 | Gap 5
Traffic Control |  | 1 |  |  |  |  | 1 | Day | 1 |  | 1 | / |  | / | / | / | 0 | 1 | [8 empty] | 0 | 0 | 0 | 0 | 0
Culvert/AEW Replacements |  | 6 |  |  |  |  | 6 | Each | 0.6 |  | 10 | / |  | / | / | / | 1 | 11 | [8 empty] | 1 | 0 | 0 | 0 | 0
Riprap/Restoration |  | 16 |  |  |  |  | 16 | CY | 4 |  | 4 | / |  | / | / | / | 11 | 15 | [8 empty] | 11 | 0 | 0 | 0 | 0
Asphaltic Surface Milling |  |  | 81700 |  |  |  | 81700 | SY | 21000 |  |  | / | 4 | / | / | / |  |  | 15 | 19 | [6 empty] | 0 | 15 | 0 | 0 | 0
HMA |  |  | 7900 |  |  |  | 7900 | Ton | 2020 |  |  | / | 4 | / | / | / |  |  | 19 | 23 | [6 empty] | 0 | 19 | 0 | 0 | 0
Shoulders 3/4" BAD |  |  | 4350 |  |  |  | 4350 | Ton | 1000 |  |  | / | 5 | / | / | / |  |  | 23 | 28 | [6 empty] | 0 | 23 | 0 | 0 | 0
Centerline Rumble Strip |  |  | 16885 |  |  |  | 16885 | LF | 12000 |  |  | / | 2 | / | / | / |  |  | 28 | 30 | [6 empty] | 0 | 28 | 0 | 0 | 0
Pavment Marking |  |  | 76800 |  |  |  | 76800 | LF | 18000 |  |  | / | 5 | / | / | / |  |  | 30 | 35 | [6 empty] | 0 | 30 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [10 empty] | 0 | 0 | 0 | 0 | 0
| Date |  | Days |  |  | Possible | Probable Working Days | [12 empty] | REMARKS
Month | Begin | End | Month | Total | Holiday | Work Days | % | Month | Total
June | 2019-06-17 | 2019-06-30 | 14 | 14 |  | 10 | 95 | 10 | 10
July | 2019-07-01 | 2019-07-31 | 31 | 45 | 1 | 22 | 95 | 21 | 31
August | 2019-08-01 | 2019-08-31 | 31 | 76 |  | 22 | 85 | 19 | 50
[6 empty] | 0 |  | 0 | 50
[6 empty] | 0 |  | 0 | 50
[6 empty] | 0 |  | 0 | 50
[6 empty] | 0 |  | 0 | 50
[6 empty] | 0 |  | 0 | 50
[6 empty] | 0 |  | 0 | 50 | [10 empty] | Calendar Days |  |  |  | 0
[6 empty] | 0 |  | 0 | 50 | [10 empty] | Working Days |  |  |  | 35
[6 empty] | 0 |  | 0 | 50 | [10 empty] | Completion Date |  |  |  | 2019-08-29
[6 empty] | 0 |  | 0 | 50 | CONSTRUCTION YEAR: | [6 empty] | 2019 |  |  | Prepared By |  |  |  | GRB
Page 1 of 1
Formulas:
Possible = NETWORKDAYS([HMA Overlay],[Contract Quantity per Stage])-[STH 49]

## Example Time Chart
CONTRACT TIME FOR COMPLETION
Wisconsin Department of Transportation DT1923 09/2010
Project ID | 5992-05-88 |  |  | Highway | USH 151 |  |  |  | Project Title | East Washington Ave., City of Madison | [15 empty] | Date of Letting | 2004-12-14
Work Type | Reconstruction |  |  | County | Dane |  |  |  | Project Limits | Melvin Court to Thierer Road | [15 empty] | Probable Date of Beginning | 2005-03-14
ITEM ANALYSIS
Item |  | Contract Quantity per Stage |  |  |  |  | Total Quantity | Unit | Production Rate |  | Working Days (per Stage) | [8 empty] | Stage 1 |  | Stage 2 |  | Stage 3 |  | Stage 4 |  | Stage 5
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | [13 empty] | Begin | End | Begin | End | Begin | End | Begin | End | Begin | End | Gap 1 | Gap 2 | Gap 3 | Gap 4 | Gap 5
1. Traffic Control |  | 3 | 1 | 3 | 1 |  | 8 | Days | 1 |  | 3 | / | 1 | / | 3 | / | 1 | / |  | 0 | 3 | 11 | 12 | 68 | 71 | 88 | 89 |  |  | 0 | 8 | 56 | 17 | 0
2. Temporary Pavement |  | 7700 |  | 7250 |  |  | 14950 | S.Y. | 1000 |  | 8 | / |  | / | 8 | / |  | / |  | 3 | 11 |  |  | 80 | 88 |  |  |  |  | 3 | 0 | 69 | 0 | 0
3. Removing Pavement |  |  | 34000 | 2000 | 34000 |  | 70000 | S.Y. | 4000 |  |  | / | 9 | / | 1 | / | 9 | / |  |  |  | 12 | 21 | 70 | 71 | 89 | 98 |  |  | 0 | 12 | 49 | 18 | 0
4. Sanitary Sewer |  | 500 | 1550 | 150 | 500 |  | 2700 | L.F. | 400 |  | 2 | / | 4 | / | 1 | / | 2 | / |  | 3 | 5 | 14 | 18 | 71 | 72 | 91 | 93 |  |  | 3 | 9 | 53 | 19 | 0
5. Sanitary Manholes |  |  | 8 |  | 8 |  | 16 | Each | 7 |  |  | / | 2 | / |  | / | 2 | / |  |  |  | 18 | 20 |  |  | 93 | 95 |  |  | 0 | 18 | 0 | 73 | 0
6. Water Main (Inc. Laterals) |  |  | 6800 | 600 | 2900 |  | 10300 | L.F. | 200 |  |  | / | 34 | / | 3 | / | 15 | / |  |  |  | 13 | 47 | 72 | 75 | 93 | 108 |  |  | 0 | 13 | 25 | 18 | 0
7. Storm Sewer |  |  | 4000 | 650 | 4000 |  | 8650 | L.F. | 400 |  |  | / | 10 | / | 2 | / | 10 | / |  |  |  | 32 | 42 | 75 | 77 | 95 | 105 |  |  | 0 | 32 | 33 | 18 | 0
8. Storm Inlets and Manholes |  |  | 72 | 23 | 93 |  | 188 | Each | 10 |  |  | / | 8 | / | 3 | / | 10 | / |  |  |  | 42 | 50 | 77 | 80 | 105 | 115 |  |  | 0 | 42 | 27 | 25 | 0
9. Structure (Ped Tunnel) |  |  | 23 | 20 | 18 |  | 61 | Days | 1 |  |  | / | 23 | / | 20 | / | 18 | / |  |  |  | 45 | 68 | 68 | 88 | 88 | 106 |  |  | 0 | 45 | 0 | 0 | 0
10. Common Excavation (Urban) |  |  | 42000 |  | 41000 | 5000 | 88000 | C.Y. | 2000 |  |  | / | 21 | / |  | / | 21 | / | 3 |  |  | 29 | 50 |  |  | 105 | 126 | 136 | 139 | 0 | 29 | 0 | 55 | 10
11. Breaker Run (Urban) |  |  | 37500 |  | 35500 | 6100 | 79100 | Ton | 2000 |  |  | / | 19 | / |  | / | 18 | / | 4 |  |  | 38 | 57 |  |  | 110 | 128 | 137 | 141 | 0 | 38 | 0 | 53 | 9
12 CABC (Urban) |  |  | 21000 |  | 21000 | 3450 | 45450 | Ton | 2000 |  |  | / | 11 | / |  | / | 11 | / | 2 |  |  | 47 | 58 |  |  | 113 | 124 | 141 | 143 | 0 | 47 | 0 | 55 | 17
13. Concrete Pavement (Urban) |  |  | 33500 |  | 33500 | 6850 | 73850 | S.Y. | 3500 |  |  | / | 10 | / |  | / | 10 | / | 2 |  |  | 49 | 59 |  |  | 117 | 127 | 143 | 145 | 0 | 49 | 0 | 58 | 16
14. Concrete Curb and Gutter |  |  | 8400 |  | 8400 | 16000 | 32800 | L.F. | 2000 |  |  | / | 5 | / |  | / | 5 | / | 8 |  |  | 56 | 61 |  |  | 124 | 129 | 144 | 152 | 0 | 56 | 0 | 63 | 15
15. Concrete Sidewalk |  |  | 2000 |  | 2000 |  | 4000 | S.F. | 500 |  |  | / | 4 | / |  | / | 4 | / |  |  |  | 59 | 63 |  |  | 127 | 131 |  |  | 0 | 59 | 0 | 64 | 0
16. Concrete Driveway |  |  | 1100 |  | 500 |  | 1600 | S.Y. | 150 |  |  | / | 8 | / |  | / | 4 | / |  |  |  | 57 | 65 |  |  | 129 | 133 |  |  | 0 | 57 | 0 | 64 | 0
17. Seeding and Finishing |  |  | 6200 |  | 6200 |  | 12400 | S.Y. | 1500 |  |  | / | 5 | / |  | / | 5 | / |  |  |  | 63 | 68 |  |  | 131 | 136 |  |  | 0 | 63 | 0 | 63 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
| Date |  | Days |  |  | Possible | Probable Working Days | [15 empty] | REMARKS
Month | Begin | End | Month | Total | Holiday | Work Days | % | Month | Total
|  |  | 0 | 0 |  | 0 |  | 0 | 0
|  |  | 0 | 0 |  | 0 |  | 0 | 0
March | 2005-03-14 | 2005-03-31 | 18 | 18 | 0 | 14 | 75 | 11 | 11
April | 2005-04-01 | 2005-04-30 | 30 | 48 | 0 | 21 | 80 | 17 | 28
May | 2005-05-01 | 2005-05-31 | 31 | 79 | 1 | 21 | 85 | 18 | 46
June | 2005-06-01 | 2005-06-30 | 30 | 109 | 0 | 22 | 95 | 21 | 67
July | 2005-07-01 | 2005-07-31 | 31 | 140 | 1 | 20 | 95 | 19 | 86
August | 2005-08-01 | 2005-08-31 | 31 | 171 | 0 | 23 | 85 | 20 | 106
September | 2005-09-01 | 2005-09-30 | 30 | 201 | 1 | 21 | 80 | 17 | 123 | [13 empty] | Calendar Days |  |  |  | 262
October | 2005-10-01 | 2005-10-31 | 31 | 232 | 0 | 21 | 75 | 16 | 139 | [13 empty] | Working Days |  |  |  | 152
November | 2005-11-01 | 2005-11-30 | 30 | 262 | 1 | 21 | 60 | 13 | 152 | [13 empty] | Completion Date |  |  |  | 2005-12-01
|  |  | 0 | 262 |  | 0 |  | 0 | 152 | CONSTRUCTION YEAR: | [9 empty] | 2005 |  |  | Prepared By |  |  |  | D. Layton
Page 1 of 1
Formulas:
Possible = NETWORKDAYS([Reconstruction],[Contract Quantity per Stage])-[USH 151]