## Slide 1: 2017 Construction Conference
Electrical

## Slide 2: Electrical Focus
Monotube Problems – Grades?
Monotube Changes – OSOH
  20’ minimum clearance
  Hwy 151 – Manitowoc
  Hwy 42/57 – Sturgeon Bay (S of Bayview Br.)

## Slide 3: Monotube Problems?
Bases
  Soil Condition
  Water Table
  Bolts
  Elevation

## Slide 4: Monotube Problems?
Bases
  Soil Condition – Concern but hasn’t been a problem
  Water Table – Concern but hasn’t really been a problem
  Bolts – Hasn’t really been a problem
  Elevation – Lots of questions from the field. Can be a problem!

## Slide 5: Monotube Problems
Bases
  Elevation
    Top of base Elevation not provided
      Pavement grade changes
      Sidewalk slope changes
      Drainage changes that force curb changes
      Follow through.
    Compute after all is known
    Try not to install prematurely (i.e. early unless grades are final)
    Pay attention to clearance requirements (OSOH?)

## Slide 7
14.5’

## Slide 13: Electrical Services

## Slide 14: Electrical Services
Types
  Meter Breaker Pedestal – Common
  Meter Socket – Fairly Rare
  Main Lug Only – Line Voltages above 277

## Slide 15: Electrical Services
Types
  Meter Breaker Pedestal – Common
  Meter Socket – Fairly Rare
  Main Lug Only – Line Voltages above 277
Section 656
  Process to get a lateral from the utility

## Slide 16: Electrical Services
Types
  Meter Breaker Pedestal – Common
  Meter Socket – Fairly Rare
  Main Lug Only – Line Voltages above 277
Section 656
  Process
    656.5(7)Coordinate with the engineer to determine how to handle.. If the utility bills the contractor directly, pay the utility promptly. Department will reimburse for INVOICE costs under the Electrical Service Lateral Administrative item.

## Slide 17: Section 656 Elec Service Process
Special Provision would dictate responsibility. If none – Contractor
  Not a Project Manager Responsibility
    Make Application
    Obtain Estimate for Lateral Cost from Utility
    Pay for Estimate??
    Install Service Device and Provide Wiring Affidavit
    Utility Schedules Installation of Lateral
    Utility Provides Invoice
  Pay per Section 656
    What should you pay
      What if there is a credit?

## Slide 18
Make Application
  Who?
    Check SP’s
      IF NOT DEFINED SPECIFICALLY
        Contractor
Utility Needs Two Things
  Where to send bill for lateral installation
    Requestor/Applicant
  Where to send monthly energy bill
    Ultimate Owner
Section 656 Elec Service Process

## Slide 19
Utility Provides an Estimate for Lateral Install
  Utility performs a “design”
  Applicant gets an estimate
Utility Needs One Thing Now
  $$$
    Cash/Check or PO
      Contractors pay with Cash/Check
      State uses PO due to State Purchase Law Requirements
Section 656 Elec Service Process

## Slide 20
State Purchase Law
  Includes State Administered Projects
  Cannot pay for a service until that service is rendered
    Cannot pay an “estimate”
      How will you know?
Section 656 Elec Service Process

## Slide 24: Section 656 Process
State Purchase Law
  State Administered Projects
  Cannot pay for a service until that service is rendered
    Cannot pay an “estimate”
    Can we pay a contractor Invoice?
      Yes and No

## Slide 26
In this example the payment
Is the same as the “estimate”
From the utility

## Slide 27
You may have to contact the
Utility to confirm

## Slide 28: Section 656 Process
State Purchase Law
  State Administered Projects
  Cannot pay for a service until that service is rendered
    Cannot pay an “estimate”
    Can we pay a Contractor Invoice
Utility Accounting Policy
  Must have payment before work gets scheduled
    Cash/Check works – only for a contractor
    PO works for Gov’t Agencies. Promise to pay.

## Slide 29: Section 656 Process
Utility Schedules Lateral Installation
  Many times we are at their mercy
    Busy
    Mother Nature
  Project Staff, Contractor, NE Region Traffic – powerless
    Start process early
    Mention at Pre-Con if this is a controlling issue
      It can become one if missed
        Coordination of work
        LD’s

## Slide 30: Section 656 Process
Utility Provides Invoice for Lateral Installation
Contractor Submission
  Proof of payment to utility
  Copy of invoice from Utility
Now you can pay contractor per Section 656.5(7)
  656.5(7)Coordinate with the engineer to determine how to handle.. If the utility bills the contractor directly, pay the utility promptly. Department will reimburse for INVOICE costs under the Electrical Service Lateral Administrative item.

## Slide 31
Utility Invoice

## Slide 32: Section 656 Process
Utility Provides Invoice for Lateral Installation
  Credit or no credit? That is the question!
    Should show on the invoice as a refund to the contractor
      Who cares?
        Nobody if you haven’t paid for this yet

## Slide 33
Costs
Payments
Credit
Owed to
Applicant
$8500
$7312.89
$1187.11

## Slide 34
Costs
Payments
Credit
Owed to
Applicant
$8500
$7312.89
$1187.11

## Slide 35: Section 656 Process
Credit???
  Utility over-estimates
    Credit comes back on INVOICE
  If PM pays early the contractor gets overpaid
    If we don’t get an invoice we may never know
    Contractor may not reimburse
  If we pay early AND we find out there is a credit
    Document
    Inform all parties
    Withhold from estimate

## Slide 36: Section 656 Process
This Whole Thing Can Slip Through the Cracks
  Know it is in your plans
    Only way to really remember
  Contractor may forget to submit paperwork
    Utility may be really late in providing invoice
    Contractor forgets to submit real invoice from the utility

## Slide 37: Section 656 Process
Questions
  Contact NE Region Traffic Unit
    Help getting paperwork
    Contacting right people
    Working through problems
  Process not perfect
    Only way to keep responsibility for coordination in the contractors hands.