UTILITY STATUS REPORT	Wisconsin Department of Transportation

DT1080     7/2013

| Date 06/02/2017 | Title T Russell, Little Sand Bay Road | Design Project ID 8357-01-02 | PS&E Date 05/01/2017 |
| --- | --- | --- | --- |
| To: Bureau of Technical Services ATTN: Utility & Access Unit | Limits Old CTH K - Termini | Construction Project ID 8357-01-72 | Let Date 08/08/2017 |
| From: Director Region/Office: NW-Sup | Highway Loc Str | Right of Way Project ID Local Plat | Plat Date -- |
|  | County Bayfield | Right of Way Project ID -; - | Plat Date -; - |

| UTILITY |  | UTL OR UA |  |  |  |  | DATES |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OWNER | TYPE | UTL NO | UA NO | R/w Project ID | UTILITY Project ID | ESTIMATED COST | PROJECT PLAN SENT | UTL OR UA TO CO | CO APP OR LUG ACQ | WORK TO BE DONE |

| Bayfield Electric | ELCTY | --- | --- | Local Plat | --- | -- | 12/07/15 | --- | --- | PC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CenturyLink | COMLN | --- | --- | Local Plat | --- | -- | 12/07/15 | --- | --- | PC |

| UTL / UA | STATUS OF UTL’S OR UA’S NOT CLEAR |
| --- | --- |

| --- | --- |
| --- | --- |
| --- | --- |
| --- | --- |

COMMENTS

--

| Name of Utility Coordinator Erik Meyer | E-mail Address emeyer@westbrookeng.com | Area Code - Telephone Number (608) 588-7866 |
| --- | --- | --- |
| Name of Firm or Region/Office Westbrook Associated Engineers, Inc. |  | Date Prepared 06/02/2017 |
| Name of Region Project Manager Ryan McKane, NW Region Local Program Management Consultant, 608-519-1455 |  |  |

| - - For WisDOT Region Utility Representative Use Only - - Project Description (Check all applicable) This is a Trans 220 project This is NOT a Trans 220 project A copy of the Utilities Special Provision as described in FDM Procedures 18-10-40, 19-10-40, and 19-15-25 is attached. Utility(s) Clear for Letting (Check one if applicable) The above contains any utility(s) within the improvement project limits and all necessary coordination arrangements have been made. Within the improvement project limits, the project will not conflict with or impact every utility. Any utility(s) not in conflict or impacted by the project need not be listed in the table above. No known utility(s) within the improvement project limits. Utility(s) Not Clear for Letting (Exception request submitted. When utility(s) clear, resubmit USR.) (Check all applicable) Necessary coordination arrangements have not been made with utility(s). (See COMMENTS) UTL’s or UA’s not clear. (See STATUS OF UTL’S OR UA’S NOT CLEAR) I CERTIFY the above to be accurate to the best of my knowledge. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Jeffrey G. Olson |  |  |  | 6/22/2017 |
| Region Utility Representative Print Name |  | Region Utility Representative Signature |  | Date |

- Utilities.

This contract does not come under the provision of Administrative Rule Trans 220.

stp-107-065 (20080501)

Bayfield Electric has overhead facilities within the project limits along both sides of Little Sand Bay Road with crossings throughout the length of the project.  Conflicts are anticipated with existing anchors and guy wires at the following stations:

- Sta. 157+59

- Sta. 161+57

- Sta. 209+88

Conflicting anchors and guy wires will be temporarily disconnected prior to construction.

The contact for Bayfield Electric is Gary Tarasewicz – Office: (715) 372-4287.

CenturyLink has underground communication lines within the project limits on both sides of Little Sand Bay Road with crossings throughout the length of the project.

From Sta. 100+16.09 to Sta. 186+00 all existing CenturyLink facilities will remain in place.

From Sta.  186+00 to Sta. 187+80 the existing cable will be replaced and moved to within 3 feet of the south right-of-way line.  The new cable will be bored to a minimum of 8 feet deep.

From Sta. 187+80 to Sta. 190+30the existing facilities will remain in place.

From Sta. 190+30 to Sta. 194+00 the existing facilities will be replaced and moved to within 3 feet of the north right-of-way line.  The new cable will be bored at a minimum of 8 feet deep.

From Sta. 194+00 to Sta. 239+06.45 all existing facilities will remain in place.

Conflicting cables will be moved prior to construction.

The contact for CenturyLink is Alan Nickell – Office: (715) 378-2131.