NortHWEST Region

CUSTOMIZED Utility Coordination Task List

Tasks with Target Date of “If needed” or “If Plat” are not anticipated to be required for the project. “Surveyor” is the responsibility of the contracted surveyor for the project; may be different than Consultant. Any item noted as “If needed” or “If Plat” is understood to require a contract change order to account for the additional hours.

All tasks shall be done in accordance with the “WisDOT Guide to Utility Coordination”, unless otherwise noted.

| Project Description – Include Design Project ID, Title, Limits, Highway, County 1560-07-01(70); Drummond – USH 2; Drummond Lake Rd – East Junction CTH E; USH 63; Bayfield County |  |  |  |
| --- | --- | --- | --- |
| Construction ID 1560-07-70 |  | PS&E date 8/1/2022 (EPSE 05/01/2021) | LET date 12/13/2022 |
| WisDOT Project Manager Travis Jensen |  | Telephone number 715-395-3025 | Email address Travis.jensen@dot.wi.gov |
| Consultant Name MSA Pro Services | Contact Jason DiPiazza | Telephone number 218-499-3179 | Email address jdipiazza@msa-ps.com |

| This is a Trans 220 project |  | This is NOT a Trans 220 project |  | (i.e., connecting highway) |
| --- | --- | --- | --- | --- |
| Project Manager (PM): |  | Travis Jensen |  | 04-17-2019 |
|  |  | Signature |  | Date |
| Utility Coordinator (UC): |  | Mike Piller |  | 04-17-2019 |
|  |  | Signature |  | Date |
| Consultant: |  |  |  |  |
|  |  | Signature |  | Date |

|  |  | Responsible Person |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | TASK | PM | UC | CONSLT | TARGET DATE |

| 1 | Provide Concept Definition Report (CDR) and copies of any subsequent revisions to region utility coordinator. |  | X |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Create list of known utilities in the project area (UIN). |  |  |  | X |  |  |  |  |  |
| 3 | Verify all utility facilities located within the right of way of the proposed improvement, according to Trans. 220.04(1) and FDM Procedure 18-10-10. |  |  |  | X |  |  |  |  |  |
| 4 | Participate in project kick-off meeting. |  | X |  | X |  | X |  | If needed |  |
| 5 | Monthly: Send copies of all correspondence with utilities and utility-related documents to the PDS-Project Manager (and/or region utility coordinator), including the Trans 220 Log (DT1079). FDM Procedure 18-1-15 |  |  |  |  |  | X |  |  |  |
| 6 | Enter utility milestone dates in TUMS. |  |  |  | X |  |  |  |  |  |
| 7 | Prepare and send project notification (DT1077), along with cover letter and exhibits, to all utilities with a potential for facilities in the project area. Trans. 220.04; FDM Procedure 18-10-10. Note: Submit DT1079 to region utility coordinator and/or update TUMS. |  |  |  | X |  |  |  | Done |  |
| 8 |  | Obtain system maps from utilities. If completed by consultant, provide copies of the system maps to the region utility coordinator. Compare the system maps with the highway plan information to confirm that all utility facilities are shown properly. Trans. 220.05(1) FDM Procedure 18-10-10 |  |  |  | X |  |  |  | Done |
| 9 |  | Coordinate field locates of all utility facilities within project area. FDM Procedure 18-10-15 Remove manhole covers. Determine flow line elevations and pipe sizes. Expose existing utility facilities and obtain elevations (pothole) at the following locations. Note: Coordinate this with the utility facility owner. |  | Done |  |  |  |  |  | Prior to 30% |
| 10 |  | Show existing utility facilities on plat, plans, and cross-sections. Note: plot the horizontal locations of all underground and overhead utility facilities on mainline and side road cross sections. |  |  |  |  |  | X |  |  |
| 11 |  | Provide 30% plan to region utility coordinator for review prior to 30% Plan Review Meeting. |  |  |  |  |  | X |  |  |
| 12 |  | Invite utilities to all Public Information Meetings. |  |  |  |  |  | X |  |  |
| 13 |  | Provide information of hazardous material sites to the region utility coordinator, as it is associated with this project. With this information clearly state what hazardous material has been found, where it has been located, other potential sites, who will be responsible for the removal, handling of the removal, storage of material that has been removed, & the cost associated with remediation of the hazardous material on this project. |  |  |  |  |  | X |  | Include in 1078 |
| 14 |  | Provide information of environmental conditions to the region utility coordinator, as it is associated with this project. This includes wetlands, bedrock, historical and archaeological sites, endangered species, underground storage tanks, etc. |  |  |  |  |  | X |  | Include in 1078 |
| 15 |  | Provide a preliminary plat to the region utility coordinator for review after all existing utility information, including compensable and non-compensable utility facilities and easements have been identified. |  |  |  |  |  | X |  | If Plat |
| 16 |  | Provide a copy of the approved DSR to the region utility coordinator. |  | X |  |  |  |  |  |  |
| 17 |  | Provide a final recorded plat to the region utility coordinator, including compensable and non-compensable utility facilities and easements. |  |  |  |  |  | X |  | If Plat |
| 18 |  | Prepare DT1078 plans, plats, and cross-sections, which are all complete enough for use by utility companies in evaluating potential conflicts and developing a relocation design. Depending on utility preference, these can be in paper or electronic format (.dgn files). See related memos: Figure 1-7 and Figure 10-9. Provide to region utility coord. |  |  |  |  |  | X |  | No Plat 1 month prior to RPPMD If Plat 1 month prior to RPPMD |
| 19 |  | Provide DT1078 plans, plats, and cross-sections, which identify all “groundbreaking activities”, to the region utility coordinator for review prior to 60% Plan Review Meeting. |  |  |  |  |  | X |  |  |
| 20 |  | Identify potential utility conflicts. If completed by consultant, provide copy to region utility coordinator. FDM Procedure 18-10-20 |  |  |  |  |  | X |  | Include in 1078 |
| 21 |  | Hold utility coordination meeting before DT1078 packages are submitted to utility companies. |  | X |  | X |  | X |  | If needed |
| 22 |  | NO PLAT: Prepare and submit Project Plan Transmittal (DT1078) package, along with all DT1078 plans and related exhibits, to each utility within the project area. Include cover letter, potential utility conflict list, utility contact list, and Utility Worksheet (DT2236), according to Trans. 220.05; FDM Procedure 18-10-30. Note: Submit DT1079 to region utility coordinator and/or update TUMS. |  |  |  |  |  | X |  | RPPMD |
| 23 |  | PLAT: Prepare and submit Project Plan Transmittal (DT1078) package, along with all DT1078 plans, recorded plat, and related exhibits, to each utility within the project area. Include cover letter, potential utility conflict list, utility contact list, Utility Worksheet (DT2236), Buy America (DT2249), utility agreements, waivers, and release of rights. According to Trans. 220.05, FDM Procedure 18-10-30 and 18-15-15. Note: Submit DT1079 to region utility coordinator and/or update TUMS. |  |  |  | X |  | X |  | If Plat RPPMD |
| 24 |  | Provide to the region utility coordinator all plan changes from previous utility plans submittals, as required. Trans. 220.05(12); FDM Procedure 18-10-45. Note: repeat task 22 and/or task 23 as described above, if necessary. |  |  |  |  |  | X |  | ASAP |
| 25 |  | Hold utility coordination meetings after the DT1078 packets have been submitted to utilities, but before the Utility Work Sheets (DT2236) are due. Trans. 220.05(04); FDM Procedure 18-10-35 and 18-20-5 |  | X |  | X |  | X |  | If needed |
| 26 |  | Send notice to utilities of having received their Utility Worksheet (DT2236), utility relocation cost estimate, release of rights, waiver letter, and utility agreement. An email notice is acceptable. (cc: the region utility coordinator.) |  |  |  |  |  | X |  |  |
| 27 |  | Review utility work plans as they are received, include review by the region utility coordinator. Recommend corrective action if necessary. FDM Procedure 18-10-35 |  |  |  | X |  | X |  |  |
| 28 |  | Resolve with each utility any conflicts among the various utility work plans. Trans. 220.05(4) |  |  |  |  |  | X |  |  |
| 29 |  | Review utility relocation cost estimate, agreements/waiver, and release of rights, as they are received FDM Procedure18-15-20 and 18-20-1. Note: Only the Utility Coordinator is to negotiate utility compensation. |  |  |  | X |  |  |  | If Plat |
| 30 |  | Submit the utility relocation cost estimates, agreements/waiver, and release of rights, to the region utility coordinator as they are received. Note: Only the Utility Coordinator is to negotiate utility compensation. |  |  |  |  |  | X |  | If Plat |
| 31 |  | Submit utility relocation cost estimates, original agreements, and recorded release of rights to Central Office for review and approval. |  |  |  | X |  |  |  | If Plat |
| 32 |  | Record releases of rights. |  |  |  | X |  |  |  | If Plat |
| 33 |  | Consult with and recommend work plan approval from region utility coordinator. FDM Procedure 18-10-35; Trans. 220.05(7) |  |  |  |  |  | X |  |  |
| 34 |  | Submit work plan approval to utility. Trans. 220.05(7) |  |  |  |  |  | X |  |  |
| 35 |  | Provide monthly updates to the region utility coordinator regarding land acquisition, including early acquisition, as it is associated with this project. |  | X |  |  |  |  |  | If Plat |
| 36 |  | Provide Pre-PS&E plans and plat to region utility coordinator for review prior to Pre-PS&E Plan Review Meeting. |  |  |  |  |  | X |  | 2 months prior to E/PSE |
| 37 |  | Review Utility Permit (DT1553) applications for compatibility with PS&E plans and resolve corrective action if necessary. |  |  |  |  |  | X |  |  |
| 38 |  | Approve Utility Permit (DT1553) applications. |  |  |  | UPC |  |  |  |  |
| 39 |  | Conduct field meetings with utilities, as required. |  | X |  | X |  | X |  | If needed |
| 40 |  | Write the utility section of the highway contract special provisions, based upon approved work plans provided by the utility owners. |  |  |  |  |  | X |  |  |
| 41 |  | Submit the utility section of the highway contract special provisions to the region utility coordinator for review and approval. |  |  |  |  |  | X |  |  |
| 42 |  | Update utility notes and utility contacts on the General Notes sheet based upon information provided by utilities from work plans. |  |  |  |  |  | X |  |  |
| 43 |  | Prepare Utility Status Report (DT1080), obtain digital signature from region utility coordinator prior to PS&E e-submittal. FDM Procedure 18-10-40. |  |  |  |  |  | X |  | 1 month prior to E/PSE |
| 44 |  | Provide field staking for utilities, as needed. Right-of-way staking is needed only in the areas where utility facilities will be placed, not the entire project. Estimate this will be needed 1 times. |  |  |  |  |  | Surveyor |  |  |
| 45 |  | Send final plan set and copy of the utility portion of the highway contract special provisions to each utility with facilities in the project area just prior to or soon after the final PS&E. FDM Procedure 18-10-45 |  |  |  |  |  | X Link to FTP |  |  |
| 46 |  | Hold a utility coordination meeting after all work plans have been approved but before utility relocations begin. Chapter Trans. 220.05(04); FDM Procedure 18-10-35 and 18-10-45 |  | X |  | X |  | X |  | If needed |
| 47 |  | Monitor and report to the region utility coordinator regarding the status of all compensable and non-compensable utility relocations. X Including all utility relocations that will be started and completed prior to construction (i.e., Pre-Construction Meeting). X Including all utility relocations that will be started prior to construction and completed during construction. Including all utility relocations started and completed during construction. |  |  |  |  |  | X |  |  |
| 48 |  | Conduct a Pre-Construction Utility Meeting with the construction contractor and all affected utilities to discuss the status of utility relocations and utility coordination necessary during construction. |  | X |  | X |  | X |  | If needed |
| 49 |  | Prior to the Pre-Construction meeting, contact each utility to discuss status of relocation effort, and be prepared to discuss the status of the relocation effort at the Pre-Construction Meeting. |  |  |  | X |  | X |  |  |
| 50 |  | Process utility agreement change orders. |  |  |  | X |  |  |  | If Plat |
| 51 |  | Process utility second moves. |  |  |  | X |  |  |  |  |
| 52 |  | Process utility billings. |  |  |  | X |  |  |  |  |