## Instructions
Instructions for DT1923 - Contract Time for Completion Spreadsheet
See FDM 19-10-30 for general information on the Contract Time for Completion analysis.
1. The form is locked. Information can only be entered in the yellow shaded cells.
2. Provide a separate Time Chart worksheet for each calendar year of construction if there are multiple years. Put the overall working days, calendar days, or completion date on each sheet.
3. Do not create new worksheets by copying worksheet tabs. The formulas do not correctly carry over to the new sheets. Instead use one of the sheet tabs (Blank 2 - Blank 5) that have been created, or create a new worksheets by starting with a new DT1923 file.
4. Use the "Blank Time Chart (Utility-RR)" tab if the project timeline is affected by work done by a utility or railroad needing to be done prior to or during construction. Use the "Utility or Railroad Line Item" rows in the bar chart to show the work. Add (or remove unused) line items as necessary.
5. Enter project information at the top of the form.
6. Enter the construction year at the bottom of the page to automatically fill out all the Begin and End dates for each month. Then delete Begin and End dates for months before the anticipated start date, and after the anticipated completion date. Change the Begin date for the applicable month to the actual probable date of beginning and change the end date for the applicable month to the anticipated completion date. Under the Month column, enter the month names to have them show up on the top row of the Gantt Chart.
7. Check the box for the Contract Work Type to be used.
8. Enter number of holiday days for each month. See FDM 19-15-23 for how to enter for Independence Day.
9. If work is expected to take place on weekends or holidays during a month, fill in the number of these days under Adjusted Work Days Modifier. This will adjust the total possible work days before applying the probable work day percentage.
10. Enter probable working day percentage based on the work type (see FDM 19-10 Attachment 30.2).
11 Totals for Calendar Days Contract and Working Day Contract are autofilled based on the calculated totals from the bottom left table. These can be overwritten if necessary. Round to 5 day increments. Fill in the anticipated completion date if the contract will be a Completion Date Contract.
12. Enter controlling items on left side of page under Item Analysis. These items will autofill into the Gantt Chart.
13. Enter item quantities for each stage (all stages do not need to be used).
14. Enter item units and production rates (also see FDM 19-10-30.3).
15. Enter begin day for each item and stage (the end date will be calculated automatically). Tip: You can use a formula here, for instance to start Item 2 when Item 1 is done, you would enter =W30 in cell V31. That way if you add 2 days to Item 1, the start date for Item 2 will automatically adjust by 2 days.
16. If the default "Stage 1", "Stage 2", etc., doesn't work for your project, you can edit them in the yellow shaded cells. The legend and other column headings will update automatically.
17. Enter remarks as necessary to provide work restrictions, interim completions, etc.
18. To get rid of extra days (blank space) on the right side of the Gantt Chart, right click on the top axis and select "Format Axis". Under "Axis Options", Change "Maximum" from "Auto" to "Fixed" and set the value to the total number of working days for the contract.
19. If there are multiple Time Chart files, combine into a single _tim file for esubmit. It is recommended to first convert each file into a pdf, and then combine the files for the esubmit.
Contact Rielly O'Donnell (rielly.odonnell@dot.wi.gov) with any suggested revisions to this form.

## Blank Time Chart
CONTRACT TIME FOR COMPLETION
Wisconsin Department of Transportation DT1923 04/2022
Project ID | 8680-00-74 |  |  | Highway | USH 2 |  |  |  | Project Title | Superior - Wentworth | [15 empty] | Date of Letting | 2025-05-13
Work Type | Bridge - Perpetuation |  |  | County | Douglas |  |  |  | Project Limits | Bong Bridge B-16-0038-0013 | [15 empty] | Probable Date of Beginning | 2025-07-01
ITEM ANALYSIS
Item |  | Contract Quantity per Stage |  |  |  |  | Total Quantity | Unit | Production Rate |  | Working Days (per Stage) | [8 empty] | Stage 1A |  | Stage 1B |  | Stage 2A |  | Stage 2B |  | Stage 3
|  | Stage 1A | Stage 1B | Stage 2A | Stage 2B | Stage 3 | [13 empty] | Begin | End | Begin | End | Begin | End | Begin | End | Begin | End | Gap 1 | Gap 2 | Gap 3 | Gap 4 | Gap 5
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
Traffic Control |  | 1 | 1 | 1 | 1 |  | 4 | Each | 2 |  | 1 | / | 1 | / | 1 | / | 1 | / |  | 0 | 1 | 31 | 32 | 76 | 77 | 87 | 88 |  |  | 0 | 30 | 44 | 10 | 0
Lighting Replacement |  | 53 | 77 |  |  |  | 130 | Each | 1.8 |  | 30 | / | 43 | / |  | / |  | / |  | 1 | 31 | 32 | 75 | [6 empty] | 1 | 1 | 0 | 0 | 0
Median Parapet Wall |  | 105 | 180 |  |  |  | 285 | LF | 4.1 |  | 26 | / | 44 | / |  | / |  | / |  | 1 | 27 | 32 | 76 | [6 empty] | 1 | 5 | 0 | 0 | 0
Structure Spot Painting |  |  |  | 0.5 | 0.5 |  | 1 | Each | 0.1 |  |  | / |  | / | 5 | / | 5 | / | [5 empty] | 65 | 70 | 88 | 93 |  |  | 0 | 0 | 65 | 18 | 0
Pier Concrete Surface Repair |  |  |  |  | 1500 |  | 1500 | SF | 100 |  |  | / |  | / |  | / | 15 | / | [7 empty] | 88 | 103 |  |  | 0 | 0 | 0 | 88 | 0
MMA Flood Seal Bridge |  |  |  | 33360 | 33360 |  | 66720 | SY | 1700 |  |  | / |  | / | 20 | / | 20 | / | [5 empty] | 65 | 85 | 88 | 108 |  |  | 0 | 0 | 65 | 3 | 0
MMA Flood Seal Ramps |  |  |  |  | 11740 |  | 11740 | SY | 600 |  |  | / |  | / |  | / | 20 | / | [7 empty] | 88 | 108 |  |  | 0 | 0 | 0 | 88 | 0
Pavement Marking Bridge & Approach |  |  |  | 36200 | 36200 |  | 72400 | LF | 37000 |  |  | / |  | / | 1 | / | 1 | / | [5 empty] | 85 | 86 | 108 | 109 |  |  | 0 | 0 | 85 | 22 | 0
Pavement Marking Ramps |  |  |  |  | 9700 |  | 9700 | LF | 10000 |  |  | / |  | / |  | / | 1 | / | [7 empty] | 108 | 109 |  |  | 0 | 0 | 0 | 108 | 0
RAB Painting |  |  |  | 500 |  |  | 500 | LF | 250 |  |  | / |  | / | 2 | / |  | / | [5 empty] | 85 | 87 |  |  |  |  | 0 | 0 | 85 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
| Date |  | Days |  |  | Possible Work Days | Additional Work Days Modifier | Adjusted Possible Work Days |  | Probable Work Days | [8 empty] | Note: Chart is based on the assumption of work not occuring on weekends or holidays. If work is expected to occur on these days, adjust Possible Work Days by adding days to the Additional Work Days Modifier column. See FDM 19-10-30.
Month | Begin | End | Month | Total | Holiday |  |  |  |  | % | Month |  |  | Total
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | REMARKS
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Ramps can not be closed concurrently. If accessed from below, structure work can take place at any time. If accessed from above structure work to be done in Stage 2B. Sidewalk may only be closed for up to 3 weeks. MMA flood seal is bridge deck only between parapets (no sidewalk) and MN ramps (no sidewalk).
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
| 2025-07-01 | 2025-07-31 | 31 | 31 | 1 | 22 |  | 22 |  | 85 | 19 |  |  | 19
| 2025-08-01 | 2025-08-31 | 31 | 62 |  | 21 |  | 21 |  | 85 | 18 |  |  | 37
| 2025-09-01 | 2025-09-30 | 30 | 92 | 1 | 21 |  | 21 |  | 80 | 17 |  |  | 54 |  |  |  |  | Contract Work Type
| 2025-10-01 | 2025-10-31 | 31 | 123 |  | 23 |  | 23 |  | 73 | 17 |  |  | 71 | [5 empty] | Calendar Day |  |  | 184
| 2025-11-01 | 2025-11-30 | 30 | 153 | 1 | 19 |  | 19 |  | 70 | 13 |  |  | 84 | [5 empty] | Working Day |  |  | 84 |  |  |  | Prepared By
| 2025-12-01 | 2025-12-31 | 31 | 184 |  | 23 |  | 23 |  | 0 | 0 |  |  | 84 | [5 empty] | Completion Date |  |  | 2025-11-30 |  |  |  | Ayres Associates
[8 empty] | Page 1 of 1 |  | CONSTRUCTION YEAR: | [9 empty] | 2025
Formulas:
Possible Work Days = NETWORKDAYS([Bridge - Perpetuation],[Contract Quantity per Stage])-[USH 2]

## Example
CONTRACT TIME FOR COMPLETION
Wisconsin Department of Transportation DT1923 04/2022
Project ID | 5992-05-88 |  |  | Highway | USH 151 |  |  |  | Project Title | East Washington Ave., City of Madison | [15 empty] | Date of Letting | 2010-12-14
Work Type | Reconstruction |  |  | County | Dane |  |  |  | Project Limits | Melvin Court to Thierer Road | [15 empty] | Probable Date of Beginning | 2011-03-14
ITEM ANALYSIS
Item |  | Contract Quantity per Stage |  |  |  |  | Total Quantity | Unit | Production Rate |  | Working Days (per Stage) | [8 empty] | Stage 1 |  | Stage 2 |  | Stage 3 |  | Stage 4 |  | Stage 5
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | [13 empty] | Begin | End | Begin | End | Begin | End | Begin | End | Begin | End | Gap 1 | Gap 2 | Gap 3 | Gap 4 | Gap 5
1. Traffic Control |  | 3 | 1 | 3 | 1 |  | 8 | Days | 1 |  | 3 | / | 1 | / | 3 | / | 1 | / |  | 0 | 3 | 11 | 12 | 68 | 71 | 88 | 89 |  |  | 0 | 8 | 56 | 17 | 0
2. Temporary Pavement |  | 7700 |  | 7250 |  |  | 14950 | S.Y. | 1000 |  | 8 | / |  | / | 8 | / |  | / |  | 3 | 11 |  |  | 80 | 88 |  |  |  |  | 3 | 0 | 69 | 0 | 0
3. Removing Pavement |  |  | 34000 | 2000 | 34000 |  | 70000 | S.Y. | 4000 |  |  | / | 9 | / | 1 | / | 9 | / |  |  |  | 12 | 21 | 70 | 71 | 89 | 98 |  |  | 0 | 12 | 49 | 18 | 0
4. Sanitary Sewer |  | 500 | 1550 | 150 | 500 |  | 2700 | L.F. | 400 |  | 2 | / | 4 | / | 1 | / | 2 | / |  | 3 | 5 | 14 | 18 | 71 | 72 | 91 | 93 |  |  | 3 | 9 | 53 | 19 | 0
5. Sanitary Manholes |  |  | 8 |  | 8 |  | 16 | Each | 7 |  |  | / | 2 | / |  | / | 2 | / |  |  |  | 18 | 20 |  |  | 93 | 95 |  |  | 0 | 18 | 0 | 73 | 0
6. Water Main (Inc. Laterals) |  |  | 6800 | 600 | 2900 |  | 10300 | L.F. | 200 |  |  | / | 34 | / | 3 | / | 15 | / |  |  |  | 13 | 47 | 72 | 75 | 93 | 108 |  |  | 0 | 13 | 25 | 18 | 0
7. Storm Sewer |  |  | 4000 | 650 | 4000 |  | 8650 | L.F. | 400 |  |  | / | 10 | / | 2 | / | 10 | / |  |  |  | 32 | 42 | 75 | 77 | 95 | 105 |  |  | 0 | 32 | 33 | 18 | 0
8. Storm Inlets and Manholes |  |  | 72 | 23 | 93 |  | 188 | Each | 10 |  |  | / | 8 | / | 3 | / | 10 | / |  |  |  | 42 | 50 | 77 | 80 | 105 | 115 |  |  | 0 | 42 | 27 | 25 | 0
9. Structure (Ped Tunnel) |  |  | 23 | 20 | 18 |  | 61 | Days | 1 |  |  | / | 23 | / | 20 | / | 18 | / |  |  |  | 45 | 68 | 68 | 88 | 88 | 106 |  |  | 0 | 45 | 0 | 0 | 0
10. Common Excavation (Urban) |  |  | 42000 |  | 41000 | 5000 | 88000 | C.Y. | 2000 |  |  | / | 21 | / |  | / | 21 | / | 3 |  |  | 29 | 50 |  |  | 105 | 126 | 136 | 139 | 0 | 29 | 0 | 55 | 10
11. Breaker Run (Urban) |  |  | 37500 |  | 35500 | 6100 | 79100 | Ton | 2000 |  |  | / | 19 | / |  | / | 18 | / | 4 |  |  | 38 | 57 |  |  | 110 | 128 | 137 | 141 | 0 | 38 | 0 | 53 | 9
12 CABC (Urban) |  |  | 21000 |  | 21000 | 3450 | 45450 | Ton | 2000 |  |  | / | 11 | / |  | / | 11 | / | 2 |  |  | 47 | 58 |  |  | 113 | 124 | 141 | 143 | 0 | 47 | 0 | 55 | 17
13. Concrete Pavement (Urban) |  |  | 33500 |  | 33500 | 6850 | 73850 | S.Y. | 3500 |  |  | / | 10 | / |  | / | 10 | / | 2 |  |  | 49 | 59 |  |  | 117 | 127 | 143 | 145 | 0 | 49 | 0 | 58 | 16
14. Concrete Curb and Gutter |  |  | 8400 |  | 8400 | 16000 | 32800 | L.F. | 2000 |  |  | / | 5 | / |  | / | 5 | / | 8 |  |  | 56 | 61 |  |  | 124 | 129 | 144 | 152 | 0 | 56 | 0 | 63 | 15
15. Concrete Sidewalk |  |  | 2000 |  | 2000 |  | 4000 | S.F. | 500 |  |  | / | 4 | / |  | / | 4 | / |  |  |  | 59 | 63 |  |  | 127 | 131 |  |  | 0 | 59 | 0 | 64 | 0
16. Concrete Driveway |  |  | 1100 |  | 500 |  | 1600 | S.Y. | 150 |  |  | / | 8 | / |  | / | 4 | / |  |  |  | 57 | 65 |  |  | 129 | 133 |  |  | 0 | 57 | 0 | 64 | 0
17. Seeding and Finishing |  |  | 6200 |  | 6200 |  | 12400 | S.Y. | 1500 |  |  | / | 5 | / |  | / | 5 | / |  |  |  | 63 | 68 |  |  | 131 | 136 |  |  | 0 | 63 | 0 | 63 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / |  | / |  | / | [11 empty] | 0 | 0 | 0 | 0 | 0
| Date |  | Days |  |  | Possible Work Days | Additional Work Days Modifier | Adjusted Possible Work Days |  | Probable Work Days | [8 empty] | Note: Chart is based on the assumption of work not occuring on weekends or holidays. If work is expected to occur on these days, adjust Possible Work Days by adding days to the Additional Work Days Modifier column. See FDM 19-10-30.
Month | Begin | End | Month | Total | Holiday |  |  |  |  | % | Month |  |  | Total
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | REMARKS
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
March | 2023-03-10 | 2023-03-31 | 22 | 22 |  | 16 |  | 16 |  | 60 | 10 |  |  | 10
April | 2023-04-01 | 2023-04-30 | 30 | 52 |  | 20 |  | 20 |  | 65 | 13 |  |  | 23
May | 2023-05-01 | 2023-05-31 | 31 | 83 | 1 | 22 |  | 22 |  | 75 | 17 |  |  | 40
June | 2023-06-01 | 2023-06-30 | 30 | 113 |  | 22 |  | 22 |  | 80 | 18 |  |  | 58
July | 2023-07-01 | 2023-07-31 | 31 | 144 | 1 | 20 |  | 20 |  | 85 | 17 |  |  | 75
August | 2023-08-01 | 2023-08-31 | 31 | 175 |  | 23 |  | 23 |  | 85 | 20 |  |  | 95
September | 2022-09-01 | 2022-09-30 | 30 | 205 | 1 | 21 |  | 21 |  | 70 | 15 |  |  | 110 |  |  |  |  | Contract Work Type
October | 2022-10-01 | 2022-10-31 | 31 | 236 |  | 21 |  | 21 |  | 65 | 14 |  |  | 124 | [5 empty] | Calendar Day |  |  | 260
November | 2022-11-01 | 2022-11-24 | 24 | 260 |  | 18 |  | 18 |  | 50 | 9 |  |  | 133 | [5 empty] | Working Day |  |  | 133 |  |  |  | Prepared By
|  |  | 0 | 260 |  | 0 |  | 0 |  |  | 0 |  |  | 133 | [5 empty] | Completion Date |  |  | 2022-11-24 |  |  |  | Rielly O'Donnell
[8 empty] | Page 1 of 1 |  | CONSTRUCTION YEAR: | [9 empty] | 2023
Formulas:
Possible Work Days = NETWORKDAYS([Reconstruction],[Contract Quantity per Stage])-[USH 151]

## Blank Time Chart (Utility-RR)
CONTRACT TIME FOR COMPLETION
Wisconsin Department of Transportation DT1923 04/2022
Project ID |  |  |  | Highway |  |  |  |  | Project Title | [13 empty] | Date of Letting
Work Type |  |  |  | County |  |  |  |  | Project Limits | [13 empty] | Probable Date of Beginning
ITEM ANALYSIS
Item |  | Contract Quantity per Stage |  |  |  |  | Total Quantity | Unit | Production Rate |  | Working Days (per Stage) | [5 empty] | Stage 1 |  | Stage 2 |  | Stage 3 |  | Stage 4 |  | Stage 5
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | [10 empty] | Begin | End | Begin | End | Begin | End | Begin | End | Begin | End | Gap 1 | Gap 2 | Gap 3 | Gap 4 | Gap 5
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
Utility or Railroad Line Item #1 | [11 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
Utility or Railroad Line Item #2 | [11 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
Utility or Railroad Line Item #3 | [11 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
| Date |  | Days |  |  | Possible Work Days | Additional Work Days Modifier | Adjusted Possible Work Days |  | Probable Work Days | [5 empty] | Note: Chart is based on the assumption of work not occuring on weekends or holidays. If work is expected to occur on these days, adjust Possible Work Days by adding days to the Additional Work Days Modifier column. See FDM 19-10-30.
Month | Begin | End | Month | Total | Holiday |  |  |  |  | % | Month |  | Total
| 2022-01-01 | 2022-01-31 | 31 | 31 |  | 21 |  | 21 |  |  | 0 |  | 0 |  |  | REMARKS
| 2022-02-01 | 2022-02-28 | 28 | 59 |  | 20 |  | 20 |  |  | 0 |  | 0
| 2022-03-01 | 2022-03-31 | 31 | 90 |  | 23 |  | 23 |  |  | 0 |  | 0
| 2022-04-01 | 2022-04-30 | 30 | 120 |  | 21 |  | 21 |  |  | 0 |  | 0
| 2022-05-01 | 2022-05-31 | 31 | 151 |  | 22 |  | 22 |  |  | 0 |  | 0
| 2022-06-01 | 2022-06-30 | 30 | 181 |  | 22 |  | 22 |  |  | 0 |  | 0
| 2022-07-01 | 2022-07-31 | 31 | 212 |  | 21 |  | 21 |  |  | 0 |  | 0
| 2022-08-01 | 2022-08-31 | 31 | 243 |  | 23 |  | 23 |  |  | 0 |  | 0
| 2022-09-01 | 2022-09-30 | 30 | 273 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  | Contract Work Type
| 2022-10-01 | 2022-10-31 | 31 | 304 |  | 21 |  | 21 |  |  | 0 |  | 0 |  |  |  | Calendar Day |  |  | 365
| 2022-11-01 | 2022-11-30 | 30 | 334 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  |  | Working Day |  |  | 0 |  |  |  | Prepared By
| 2022-12-01 | 2022-12-31 | 31 | 365 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  |  | Completion Date
[8 empty] | Page 1 of 1 |  | CONSTRUCTION YEAR: | [6 empty] | 2022
Formulas:
Possible Work Days = NETWORKDAYS([Date],[Contract Quantity per Stage])-[Holiday]
Enter the Construction Year before completing this section (Then delete this note)

## Blank 2
CONTRACT TIME FOR COMPLETION
Wisconsin Department of Transportation DT1923 04/2022
Project ID |  |  |  | Highway |  |  |  |  | Project Title | [13 empty] | Date of Letting
Work Type |  |  |  | County |  |  |  |  | Project Limits | [13 empty] | Probable Date of Beginning
ITEM ANALYSIS
Item |  | Contract Quantity per Stage |  |  |  |  | Total Quantity | Unit | Production Rate |  | Working Days (per Stage) | [5 empty] | Stage 1 |  | Stage 2 |  | Stage 3 |  | Stage 4 |  | Stage 5
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | [10 empty] | Begin | End | Begin | End | Begin | End | Begin | End | Begin | End | Gap 1 | Gap 2 | Gap 3 | Gap 4 | Gap 5
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
| Date |  | Days |  |  | Possible Work Days | Additional Work Days Modifier | Adjusted Possible Work Days |  | Probable Work Days | [5 empty] | Note: Chart is based on the assumption of work not occuring on weekends or holidays. If work is expected to occur on these days, adjust Possible Work Days by adding days to the Additional Work Days Modifier column. See FDM 19-10-30.
Month | Begin | End | Month | Total | Holiday |  |  |  |  | % | Month |  | Total
| 2022-01-01 | 2022-01-31 | 31 | 31 |  | 21 |  | 21 |  |  | 0 |  | 0 |  |  | REMARKS
| 2022-02-01 | 2022-02-28 | 28 | 59 |  | 20 |  | 20 |  |  | 0 |  | 0
| 2022-03-01 | 2022-03-31 | 31 | 90 |  | 23 |  | 23 |  |  | 0 |  | 0
| 2022-04-01 | 2022-04-30 | 30 | 120 |  | 21 |  | 21 |  |  | 0 |  | 0
| 2022-05-01 | 2022-05-31 | 31 | 151 |  | 22 |  | 22 |  |  | 0 |  | 0
| 2022-06-01 | 2022-06-30 | 30 | 181 |  | 22 |  | 22 |  |  | 0 |  | 0
| 2022-07-01 | 2022-07-31 | 31 | 212 |  | 21 |  | 21 |  |  | 0 |  | 0
| 2022-08-01 | 2022-08-31 | 31 | 243 |  | 23 |  | 23 |  |  | 0 |  | 0
| 2022-09-01 | 2022-09-30 | 30 | 273 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  | Contract Work Type
| 2022-10-01 | 2022-10-31 | 31 | 304 |  | 21 |  | 21 |  |  | 0 |  | 0 |  |  |  | Calendar Day |  |  | 365
| 2022-11-01 | 2022-11-30 | 30 | 334 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  |  | Working Day |  |  | 0 |  |  |  | Prepared By
| 2022-12-01 | 2022-12-31 | 31 | 365 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  |  | Completion Date
[8 empty] | Page 1 of 1 |  | CONSTRUCTION YEAR: | [6 empty] | 2022
Formulas:
Possible Work Days = NETWORKDAYS([Date],[Contract Quantity per Stage])-[Holiday]
Enter the Construction Year before completing this section (Then delete this note)

## Blank 3
CONTRACT TIME FOR COMPLETION
Wisconsin Department of Transportation DT1923 04/2022
Project ID |  |  |  | Highway |  |  |  |  | Project Title | [13 empty] | Date of Letting
Work Type |  |  |  | County |  |  |  |  | Project Limits | [13 empty] | Probable Date of Beginning
ITEM ANALYSIS
Item |  | Contract Quantity per Stage |  |  |  |  | Total Quantity | Unit | Production Rate |  | Working Days (per Stage) | [5 empty] | Stage 1 |  | Stage 2 |  | Stage 3 |  | Stage 4 |  | Stage 5
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | [10 empty] | Begin | End | Begin | End | Begin | End | Begin | End | Begin | End | Gap 1 | Gap 2 | Gap 3 | Gap 4 | Gap 5
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
| Date |  | Days |  |  | Possible Work Days | Additional Work Days Modifier | Adjusted Possible Work Days |  | Probable Work Days | [5 empty] | Note: Chart is based on the assumption of work not occuring on weekends or holidays. If work is expected to occur on these days, adjust Possible Work Days by adding days to the Additional Work Days Modifier column. See FDM 19-10-30.
Month | Begin | End | Month | Total | Holiday |  |  |  |  | % | Month |  | Total
| 2022-01-01 | 2022-01-31 | 31 | 31 |  | 21 |  | 21 |  |  | 0 |  | 0 |  |  | REMARKS
| 2022-02-01 | 2022-02-28 | 28 | 59 |  | 20 |  | 20 |  |  | 0 |  | 0
| 2022-03-01 | 2022-03-31 | 31 | 90 |  | 23 |  | 23 |  |  | 0 |  | 0
| 2022-04-01 | 2022-04-30 | 30 | 120 |  | 21 |  | 21 |  |  | 0 |  | 0
| 2022-05-01 | 2022-05-31 | 31 | 151 |  | 22 |  | 22 |  |  | 0 |  | 0
| 2022-06-01 | 2022-06-30 | 30 | 181 |  | 22 |  | 22 |  |  | 0 |  | 0
| 2022-07-01 | 2022-07-31 | 31 | 212 |  | 21 |  | 21 |  |  | 0 |  | 0
| 2022-08-01 | 2022-08-31 | 31 | 243 |  | 23 |  | 23 |  |  | 0 |  | 0
| 2022-09-01 | 2022-09-30 | 30 | 273 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  | Contract Work Type
| 2022-10-01 | 2022-10-31 | 31 | 304 |  | 21 |  | 21 |  |  | 0 |  | 0 |  |  |  | Calendar Day |  |  | 365
| 2022-11-01 | 2022-11-30 | 30 | 334 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  |  | Working Day |  |  | 0 |  |  |  | Prepared By
| 2022-12-01 | 2022-12-31 | 31 | 365 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  |  | Completion Date
[8 empty] | Page 1 of 1 |  | CONSTRUCTION YEAR: | [6 empty] | 2022
Formulas:
Possible Work Days = NETWORKDAYS([Date],[Contract Quantity per Stage])-[Holiday]
Enter the Construction Year before completing this section (Then delete this note)

## Blank 4
CONTRACT TIME FOR COMPLETION
Wisconsin Department of Transportation DT1923 04/2022
Project ID |  |  |  | Highway |  |  |  |  | Project Title | [13 empty] | Date of Letting
Work Type |  |  |  | County |  |  |  |  | Project Limits | [13 empty] | Probable Date of Beginning
ITEM ANALYSIS
Item |  | Contract Quantity per Stage |  |  |  |  | Total Quantity | Unit | Production Rate |  | Working Days (per Stage) | [5 empty] | Stage 1 |  | Stage 2 |  | Stage 3 |  | Stage 4 |  | Stage 5
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | [10 empty] | Begin | End | Begin | End | Begin | End | Begin | End | Begin | End | Gap 1 | Gap 2 | Gap 3 | Gap 4 | Gap 5
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
| Date |  | Days |  |  | Possible Work Days | Additional Work Days Modifier | Adjusted Possible Work Days |  | Probable Work Days | [5 empty] | Note: Chart is based on the assumption of work not occuring on weekends or holidays. If work is expected to occur on these days, adjust Possible Work Days by adding days to the Additional Work Days Modifier column. See FDM 19-10-30.
Month | Begin | End | Month | Total | Holiday |  |  |  |  | % | Month |  | Total
| 2022-01-01 | 2022-01-31 | 31 | 31 |  | 21 |  | 21 |  |  | 0 |  | 0 |  |  | REMARKS
| 2022-02-01 | 2022-02-28 | 28 | 59 |  | 20 |  | 20 |  |  | 0 |  | 0
| 2022-03-01 | 2022-03-31 | 31 | 90 |  | 23 |  | 23 |  |  | 0 |  | 0
| 2022-04-01 | 2022-04-30 | 30 | 120 |  | 21 |  | 21 |  |  | 0 |  | 0
| 2022-05-01 | 2022-05-31 | 31 | 151 |  | 22 |  | 22 |  |  | 0 |  | 0
| 2022-06-01 | 2022-06-30 | 30 | 181 |  | 22 |  | 22 |  |  | 0 |  | 0
| 2022-07-01 | 2022-07-31 | 31 | 212 |  | 21 |  | 21 |  |  | 0 |  | 0
| 2022-08-01 | 2022-08-31 | 31 | 243 |  | 23 |  | 23 |  |  | 0 |  | 0
| 2022-09-01 | 2022-09-30 | 30 | 273 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  | Contract Work Type
| 2022-10-01 | 2022-10-31 | 31 | 304 |  | 21 |  | 21 |  |  | 0 |  | 0 |  |  |  | Calendar Day |  |  | 365
| 2022-11-01 | 2022-11-30 | 30 | 334 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  |  | Working Day |  |  | 0 |  |  |  | Prepared By
| 2022-12-01 | 2022-12-31 | 31 | 365 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  |  | Completion Date
[8 empty] | Page 1 of 1 |  | CONSTRUCTION YEAR: | [6 empty] | 2022
Formulas:
Possible Work Days = NETWORKDAYS([Date],[Contract Quantity per Stage])-[Holiday]
Enter the Construction Year before completing this section (Then delete this note)

## Blank 5
CONTRACT TIME FOR COMPLETION
Wisconsin Department of Transportation DT1923 04/2022
Project ID |  |  |  | Highway |  |  |  |  | Project Title | [13 empty] | Date of Letting
Work Type |  |  |  | County |  |  |  |  | Project Limits | [13 empty] | Probable Date of Beginning
ITEM ANALYSIS
Item |  | Contract Quantity per Stage |  |  |  |  | Total Quantity | Unit | Production Rate |  | Working Days (per Stage) | [5 empty] | Stage 1 |  | Stage 2 |  | Stage 3 |  | Stage 4 |  | Stage 5
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | [10 empty] | Begin | End | Begin | End | Begin | End | Begin | End | Begin | End | Gap 1 | Gap 2 | Gap 3 | Gap 4 | Gap 5
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
| Date |  | Days |  |  | Possible Work Days | Additional Work Days Modifier | Adjusted Possible Work Days |  | Probable Work Days | [5 empty] | Note: Chart is based on the assumption of work not occuring on weekends or holidays. If work is expected to occur on these days, adjust Possible Work Days by adding days to the Additional Work Days Modifier column. See FDM 19-10-30.
Month | Begin | End | Month | Total | Holiday |  |  |  |  | % | Month |  | Total
| 2022-01-01 | 2022-01-31 | 31 | 31 |  | 21 |  | 21 |  |  | 0 |  | 0 |  |  | REMARKS
| 2022-02-01 | 2022-02-28 | 28 | 59 |  | 20 |  | 20 |  |  | 0 |  | 0
| 2022-03-01 | 2022-03-31 | 31 | 90 |  | 23 |  | 23 |  |  | 0 |  | 0
| 2022-04-01 | 2022-04-30 | 30 | 120 |  | 21 |  | 21 |  |  | 0 |  | 0
| 2022-05-01 | 2022-05-31 | 31 | 151 |  | 22 |  | 22 |  |  | 0 |  | 0
| 2022-06-01 | 2022-06-30 | 30 | 181 |  | 22 |  | 22 |  |  | 0 |  | 0
| 2022-07-01 | 2022-07-31 | 31 | 212 |  | 21 |  | 21 |  |  | 0 |  | 0
| 2022-08-01 | 2022-08-31 | 31 | 243 |  | 23 |  | 23 |  |  | 0 |  | 0
| 2022-09-01 | 2022-09-30 | 30 | 273 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  | Contract Work Type
| 2022-10-01 | 2022-10-31 | 31 | 304 |  | 21 |  | 21 |  |  | 0 |  | 0 |  |  |  | Calendar Day |  |  | 365
| 2022-11-01 | 2022-11-30 | 30 | 334 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  |  | Working Day |  |  | 0 |  |  |  | Prepared By
| 2022-12-01 | 2022-12-31 | 31 | 365 |  | 22 |  | 22 |  |  | 0 |  | 0 |  |  |  | Completion Date
[8 empty] | Page 1 of 1 |  | CONSTRUCTION YEAR: | [6 empty] | 2022
Formulas:
Possible Work Days = NETWORKDAYS([Date],[Contract Quantity per Stage])-[Holiday]
Enter the Construction Year before completing this section (Then delete this note)