| REQUEST FOR INFORMATION (RFI) | Wisconsin Department of Transportation |
| --- | --- |
| DT2502 4/2013 |  |

| Project ID 1320-17-70 | RFI Number 2-REV |
| --- | --- |
| Roadway STH 11 | Date Submitted (m/d/yyyy) 6/30/2020 |
| Description USH 14/STH 89 to Turtle Creek Drive |  |
| County Walworth |  |
| To (responding party under standard spec 104.4) | From (requesting party under standard spec 104.4) |
| Dawn Marshall Project Engineer WisDOT (414)-750-1462 Dawn.Marshall@dot.wi.gov | Mike Jacobs Project Manager Rock Road (608)-931-2965 mjacobs@rockroads.com |
| Request Initiated by |  |
| Contractor Department |  |
| Short Description STH 11: Quantity adjustments/revisions REV |  |
| Detailed Description of Request Given the extensive nature of the revsions to the plan cross-sections, and lack of cohesion between the project plan set and provided modeling data are any quantity variations expected from the quantites contained in the plan set? The question pertains to both large and small quantitiy adjustments in the interest of accuracy and limiting disagreements over quantity discrepancies in the future. The questions also pertains to all contract items. ADDITION TO RFI #2 AFTER TRYING TO BUILD THE MODEL FOR THIS PROJECT, THERE ARE MULTIPLE CROSS SECTIONS THAT WILL NOT BE BUILDABLE AND DO NOT MATCH THE CROSS SECTIONS. ATTACHED IS A TYPICAL CROSS SECTION WE ARE ENCOUNTERING WHEN TRYING TO BUILD THE MODEL AT STA 65+50. ON THE LEFT SIDE THE SI IS ~ 31.5' LEFT. THERE IS ALSO TLE IN THIS AREA WHICH WOULD LEAD ONE TO BELIEVE THAT MORE WORK IS REQUIRED PAST THE SHOULDER PT. THE CROSS SECTIONS SHOW THE SI BEING 20.6' LEFT. ON THE RIGHT SIDE, THE SI IS CORRECT, BUT THIS IS NOT BUILDABLE. IS THE ROCK SUPPOSED TO GO TO THE 5:1 SLOPE OR IS THERE SUPPOSED TO BE JUST A SHOULDER CORE LEAVING A TRENCH ONLY. WE NEED REVISED CROSS SECTIONS AND QTYS TO BE ABLE TO START GRADING AS SOON AS POSSIBLE. |  |
| Are additional support documents attached? Yes No |  |
| Date Response is Due (m/d/yyyy) 7/6/2020 | Date Response is Sent (m/d/yyyy) |
| Detailed Response to Request Response to Original RFI #2 Attached are the revised Common Ex and Borrow raw quantities, not expanded. Original Division 1 (Reconstruct Area) Common Ex = 1,772 CY, Borrow = 9,774 CY Oriingal Division 2 (Resurfacing) Common Ex = 18,870 + 3,000 EBS, Borrow(Unexpanded Fill since borrow was reduced by cut) = 5489 CY Updated X-sections Division 1 (Reconstruct Area) Common Ex = 5047 CY, Borrow = 10023 CY. The difference is likely because the grading under the obliterated roadway was missed in the plan. Updated X-sections Division 2 (Resurfacing) Common Ex = 17963 CY + 3000 EBS, Borrow ( Unexpanded Fill) = 5494 CY. Note, the first run showed an increase in cut. That was caused when revising the files resulted in the datum surface extending under the mill and relay for roughly 1/3 of the projec. This has been corrected. As we discussed in emails prior to this response, the 0.5:1 shoulder slopes with final grading starting at the shoulder break point above the cross sections is where the shoulder should be cut in straight down. Other quantity changes expected (not ones that are already completed, or almost completed such as clearing, grubbing, sawcutting….): 305.0120 - 1.25 BAD is expected to increase by 220 Tons to account for the area above the backfill (top of subgrade equivalent) to the bottom of the mill and relay surface and the area where the shoulder is cut into the existing ground and is filled with agg in what would be the foreslope area. 204.0120 - Removing Asphaltic Surface Milling will increase by approximately 70 SY. The matchpoint on the western and middle Pleasant Streets will be moved back to remove some tire ruts and imprints created by this project. 504.0900 - Concrete Masonry will increase from 13 CY to 52 CY. The end of each endwall should extend 78" from the end of the pipe. A drawing and the calculation spreadsheet are included in the attachment. 204.0245 - Removing Storm Sewer 15-Inch will increase by approximately 220 FT because a pipe was found and will need to be removed for C&G placement between approximately Station 89+90 and 92+00 . |  |

| INSTRUCTIONS FOR REQUEST FOR INFORMATION (RFI) | Wisconsin Department of Transportation |
| --- | --- |
| DT2502 |  |

Project ID:  Enter controlling project ID for the contract. Usually the lowest.

RFI Number:  The project leader will assign the RFI number.

Roadway Date Submitted:  Enter date submitted. (m/d/yyyy – month, day, year).

Description:  Enter the description from the proposal cover sheet.

County:  Enter the county from the proposal cover sheet.

To (responding party under standard spec 104.4):  Enter the contact information for the responding party. This is either the project leader or the contractor's superintendant. Include phone numbers and email addresses.

From (requesting party under standard spec 104.4):  Enter the contact information for the requesting party. This is either the project leader or the contractor's superintendant. Include phone numbers and email addresses.

Request Initiated by:  Select either Contractor or Department.

Short Description:  Provide a brief description of the RFI issue. Maximum length is 255 characters.

Detailed Description of Request:  Provide a detailed description of the RFI issue. Include contact information for technical staff that can help provide additional details if necessary.

Are additional supporting documents attached?  Select either yes or no to indicate whether there are attachments.

Date Response is Due:  Enter the deadline for the response. Allow a minimum of 72 hours. (m/d/yyyy – month, day, year).

Date Response was Sent:  Enter the date the response was provided. (m/d/yyyy – month, day, year).

Detailed Response to Request:  Provide a detailed response to the RFI issue. Include contact information for technical staff that helped prepare the response.