East Waukesha Bypass						August 1, 2021

Sunset Drive to Arcadian Ave

STH 59	 							WisDOT Contact:

Waukesha County							Brett Matheny (414) 531-3079

Design ID 2773-10-01

Construction ID 2773-10-70

Note to utilities for the TRANS 220 Plans:

- It is the utilities responsibility to verify that their facilities are shown correctly on the plans.  Please contact WisDOT if there are new or missing facilities.

- The following is a brief flow chart of the TRANS 220 process.

  - WisDOT sends TRANS 220 package to all the utility companies (includes TRANS 220 Project Plan, contact list, work sheet, potential conflict list, etc).

  - The utility returns the DT1078 form acknowledging receipt of the package.

  - The utility company completes necessary paperwork and submits to WisDOT.

  - The utility company sends their work plan and work sheet to WisDOT for review.

  - WisDOT reviews the plans and informs the utility company of any deficiencies.  The utility revises their plan and resubmits if necessary.

  - WisDOT notifies the utility that the utility Work Plan has been approved.

- The below potential conflict list calls out any location that has a facility inside the grading limits that could be in conflict.  The utilities are to verify all conflicts and identify additional conflicts that are not noted.

- The utilities are responsible for coordinating their facilities with each other; see the utility contact list for names and phone numbers.

- AutoCAD Civil 3D electronic files are available at the request of the utility company.

- The utility special verbiage below can/will be changed based on each utilities Work Plans.  Coordination between the designer and utility will be needed.

- Utilities are shown on the cross sections for the TRANS 220 Plan only.  Utilities with facilities in the same trench are shown as a single tick in the cross sections.

- Construction will take place with STH 59 lane closures. One lane in each direction will be closed during peak hours and two lanes in each direction will be closed during non-peak hours.

- Excavation Below Subgrade (EBS) – anticipated EBS locations are noted in the cross sections.

- There are two identified locations for Hazardous Material within the project grading limits – anticipated HazMat locations are noted in the cross sections and plans.

- Utility conflicts shall be adjusted prior to construction unless noted otherwise. There may be a few utility adjustments that can only be completed during construction, and these adjustments must be clearly stated “to be completed during construction” in the special provisions.

- Municipal utilities wishing to include their utility adjustments in the WisDOT contract should contact the WisDOT Project Manager as soon as possible to coordinate the inclusion of the utility adjustments in the roadway plan.

1. Utilities – UTILITY POTENTIAL CONFLICT LIST

This project comes under the provisions of Administrative Rule TRANS 220.

Additional detailed information regarding the location of relocated utility facilities is available on the permits issued to the utility companies.  These permits can be viewed at the Region Office during normal working hours.  Contact the SE Region Utility Coordinator Rabi Bista at (262) 548-5690.

There are underground and overhead utility facilities located within the project limits.  There are known utility adjustments required for this construction project.  The contractor shall coordinate construction activities with a call to Digger’s Hotline or a direct call to the utilities that have facilities in the area as required per statutes.  The contractor shall use caution to ensure the integrity of underground and overhead facilities.

Bidders are advised to contact each utility company listed in the plans prior to preparing their bids, to obtain current information on the status of any utility within the project work limits.

Known utilities on the project are as follows:

AT&T Wisconsin has aerial facilities on WE Energies poles along the east side of STH 59 from the beginning of the project to Sunset Drive; buried facilities along the east side of STH 59 from the beginning of the project to Sunset Drive and then along the south side of Sunset Drive to the east of STH 59; buried facilities along the west side of STH 59 from 400’ north of Sunset Drive to 800’ north of Sunset Drive; buried facilities along the east side of STH 59 from 600’ north of Sunset Drive to Racine Avenue; buried facilities along the north side of Racine Avenue from the beginning of construction to the end of construction; buried facilities along the west side of STH 59 from Blackhawk Trail to Racine Avenue and then along the south side of Racine Avenue to the west of STH 59; aerial facilities on WE Energies poles along the north side of Racine Avenue from STH 59 to the east end of construction; aerial facilities on WE Energies poles along the west side of STH 59 from 900’ south of Broadway Street to Broadway Street; buried facilities along the south side of Broadway Street from beginning to end of construction; buried facilities along the east side of STH 59 from Broadway Street to Pearl Street; buried facilities along the east and west sides of STH 59 from Lincoln Avenue to the end of the project.

NOTE – For this TRANS 220 submittal the potential conflict list calls out any facility within our grading as a conflict because we do not know the facility depths.  The utility is to verify the depth of any buried facilities and height of any aerial facilities and determine if there is a conflict.

| Location and Conflict | Resolution |
| --- | --- |
| - STH 59 STA 151+50 to 152+50 RT. Buried facility goes through underpass removal. - Northeast and southeast corners of STH 59 and Blackhawk Trail. Buried facilities go through curb ramp replacement. - Racine Avenue STA 249+85 to 254+15 RT. Buried and aerial facilities go through turn lane extension, median work, and storm sewer work. - All four quadrants of STH 59 and Pearl Street. Buried facilities in the area of signal replacement. - Northwest corner of STH 59 and Lincoln Avenue. Buried facilities go through curb ramp replacement. | - AT&T Wisconsin to verify location/depth. If there is a conflict, AT&T Wisconsin to adjust facility prior to construction. - AT&T Wisconsin to verify location/depth. If there is a conflict, AT&T Wisconsin to adjust facility prior to construction. - AT&T Wisconsin to verify location/depth of buried facilities. If there is a conflict, AT&T Wisconsin to adjust facility prior to construction. Manhole will either need to be adjusted or moved out of the new pavement. Pedestals will need to be moved as well. WE Energies will have to verify pole locations. If there is a conflict, AT&T Wisconsin to coordinate pole relocations with WE Energies prior to construction. - AT&T Wisconsin to verify location/depth. If there is a conflict, AT&T Wisconsin to adjust facility prior to construction. - AT&T Wisconsin to verify location/depth. If there is a conflict, AT&T Wisconsin to adjust facility prior to construction. |

AT&T Wisconsin Contact: Tom Crowley

Phone: (262) 896-7427, E-mail: tc1657@att.com

ATC Management, Inc. has aerial facilities along the west side of STH 59 from the beginning of the project to 700’ north of Sunset Drive that then cross over to the east side of STH 59 and run along the east side of STH 59 to Blackhawk Trail and aerial facilities crossing STH 59 300’ south of Lincoln Avenue. No conflicts are anticipated.

ATC Management, Inc. Contact: Tony Marciniak

Phone: (262) 506-6814, E-mail: amarciniak@atcllc.com

Charter Communications has aerial facilities on WE Energies poles along the east side of STH 59 from the beginning of the project to Sunset Drive that then cross over to the west side of STH 59 on the south side of Sunset Drive and cross over Sunset Drive on the east side of STH 59; buried facilities along the west side of STH 59 from 400’ north of Sunset Drive to 800’ north of Sunset Drive; aerial facilities that cross over STH 59 on the south side of Blackhawk Trail; buried facilities on the east side of STH 59 from Blackhawk Trail to Racine Avenue; aerial facilities on WE Energies poles along the north side of Racine Avenue from the west end of construction to the east end of construction that also cross over Racine Avenue west of Guthrie Road; aerial facilities on WE Energies poles along the west side of STH 59 from 900’ south of Broadway Street to Pearl Street; aerial facilities along the south side of Broadway Street from beginning to end of construction; buried facilities that cross STH 59 at 500’ south of Pearl Street; buried facilities in all four quadrants of STH 59 and Pearl Street; buried facilities on the west side of STH 59 from old railroad crossing/New Berlin Trail crossing to the end of the project; aerial facilities on the west side of STH 59 from Lincoln Avenue to the end of the project.

NOTE – For this TRANS 220 submittal the potential conflict list calls out any facility within our grading as a conflict because we do not know the facility depths.  The utility is to verify the depth of any buried facilities and height of any aerial facilities and determine if there is a conflict.

| Location and Conflict | Resolution |
| --- | --- |
| - Northeast and southeast corners of STH 59 and Blackhawk Trail. Buried facilities go through curb ramp replacement. - Racine Avenue STA 249+85 to 254+15 RT. Buried and aerial facilities go through turn lane extension, median work, and storm sewer work. - Racine Avenue STA 246+90 LT. Aerial facility pole in grading area. - All four quadrants of STH 59 and Pearl Street. Buried and aerial facilities in the area of signal replacement. - Northwest corner of STH 59 and Lincoln Avenue. Buried facilities go through curb ramp replacement. | - Charter to verify location/depth. If there is a conflict, Charter to adjust facility prior to construction. - Charter to verify location/depth of buried facilities. If there is a conflict, Charter to adjust facility prior to construction. Manhole will either need to be adjusted or moved out of the new pavement. Pedestals will need to be moved as well. WE Energies will have to verify pole locations. If there is a conflict, Charter to coordinate pole relocations with WE Energies prior to construction. - WE Energies will have to verify pole location. If there is a conflict, Charter to coordinate pole relocation with WE Energies prior to construction. - Charter to verify location/depth. If there is a conflict, Charter to adjust facility prior to construction. WE Energies will have to verify pole location. If there is a conflict, Charter to coordinate pole relocation with WE Energies prior to construction. - Charter to verify location/depth. If there is a conflict, Charter to adjust facility prior to construction. |

Charter Communications Contact: Beau Abuya

Phone: (414) 908-1343, E-mail: wis.engineering@charter.com

City of Waukesha - Communications has buried facilities in all four quadrants of STH 59 and Pearl Street that run along the north side of Pearl Street to the west of STH 59 and along the south side of Pearl Street to the east of STH 59; aerial facilities along the north side of Pearl Street east of STH 59; aerial facilities along the west side of STH 59 from Pearl Street to the old railroad crossing/New Berlin Trail crossing.

NOTE – For this TRANS 220 submittal the potential conflict list calls out any facility within our grading as a conflict because we do not know the facility depths.  The utility is to verify the depth of any buried facilities and height of any aerial facilities and determine if there is a conflict.

| Location and Conflict | Resolution |
| --- | --- |
| - All four quadrants of STH 59 and Pearl Street. Buried and aerial facilities in the area of signal replacement. | - City of Waukesha to verify location/depth. If there is a conflict, City of Waukesha to adjust facility prior to construction. WE Energies will have to verify pole location. If there is a conflict, City of Waukesha to coordinate pole relocation with WE Energies prior to construction. |

City of Waukesha - Communications Contact: Jeffrey Hernke

Phone: (262) 524-3592, E-mail: jhernke@waukesha-wi.gov

City of Waukesha - Sanitary Sewer has buried facilities that cross STH 59 south of Sunset Avenue; buried facilities that cross STH 59 at 700’ south of Blackhawk Trail, then run along the west side of STH 59 to 800’ north of Blackhawk Trail, then cross under and run along the east side of STH 59 to Racine Avenue, then run along the south side of Racine Avenue to the east end of construction; buried facilities in the northwest corner of STH 59 and Racine Avenue; buried facilities down the center of Pearl Street from beginning to end of construction; buried facilities down the center of Lincoln Avenue from beginning to end of construction; buried facilities on the west side of STH 59 from Lincoln Avenue to the end of the project.

NOTE – For this TRANS 220 submittal the potential conflict list calls out any facility within our grading as a conflict because we do not know the facility depths.  The utility is to verify the depth of any buried facilities and determine if there is a conflict.

| Location and Conflict | Resolution |
| --- | --- |
| - Roadway - STH 59 STA 151+50 to 152+50 RT. Buried facility runs adjacent to underpass removal. - STA 239+30 to 248+30 LT. Buried facility runs through lane addition and storm sewer work. - Roadway at Pearl Street. Buried facilities in the area of signal loop replacement. - Northwest corner of STH 59 and Lincoln Avenue. Buried facilities go through curb ramp replacement. | - City of Waukesha to adjust sanitary manholes throughout the project. - City of Waukesha to verify location/depth. If there is a conflict, City of Waukesha to adjust facility prior to construction. - City of Waukesha to verify location/depth of buried facilities. If there is a conflict, City of Waukesha to adjust facility prior to construction. Manholes may need to be adjusted. - City of Waukesha to verify location/depth. If there is a conflict, City of Waukesha to adjust facility prior to construction. - City of Waukesha to verify location/depth of buried facilities. If there is a conflict, City of Waukesha to adjust facility prior to construction. Manholes may need to be adjusted. |

City of Waukesha - Sanitary Sewer Contact: Chris Langemak

Phone: (262) 524-3598, E-mail: CLangemak@waukesha-wi.gov

City of Waukesha - Water has buried facilities along the west side of STH 59 from the beginning of the project to Blackhawk Trail, then goes to the STH 59 median from Blackhawk Trail to Racine Avenue, then goes to the west side of STH 59 from Racine Avenue to 450’ north of Racine Avenue, then goes to the median from 450’ north of Racine Avenue to 1600’ north of Racine Avenue, then goes to the west side of STH 59 from 1600’ north of Racine Avenue to 300’ north of Pearl Street, then goes to the median from 300’ north of Pearl Street to the end of the project; buried facilities on the north side of Sunset Drive from the beginning to end of construction that also crosses under Sunset Drive at multiple locations; buried facilities down the center of Racine Avenue from beginning to end of construction with connections to the north and south of Racine Avenue at various locations; buried facilities on the east side of STH 59 from 1500’ south of Broadway Street to 1400’ south of Broadway Street; buried facilities cross under to the east side of STH 59 1100’ south of Broadway Street and then run along the east side of STH 59 to 1000’ south of Broadway Street; buried facilities cross under STH 59 at the south side of Broadway Street; buried facilities that cross under Broadway Street 80’ east of STH 59; buried facilities that cross under STH 59 350’ north of Broadway Street; buried facilities that cross under to the east side of STH 59 550’ south of Pearl Street and then runs along the east side of STH 59 up to Pearl Street; buried facilities down the center of Pearl Street from the beginning to end of construction that also crosses under Pearl Street at multiple locations; buried facilities down the center of Lincoln Avenue from the beginning to end of construction; buried facilities along the west side of STH 59 from 250’ south of Lincoln Avenue to the end of the project.

City of Waukesha - Water (Waukesha Water Utility) is planning to install watermain in the southeast corner of STH 59 and Sunset Drive; along the north side of Racine Avenue from STH 59 to the west end of construction; along the east side of STH 59 from Racine Avenue to Broadway Street.

NOTE – For this TRANS 220 submittal the potential conflict list calls out any facility within our grading as a conflict because we do not know the facility depths.  The utility is to verify the depth of any buried facilities and determine if there is a conflict. It does not call out any of the proposed work in bold above.

| Location and Conflict | Resolution |
| --- | --- |
| - Roadway - Pork Chop islands on the north side of the STH 59 and Sunset Drive intersection. Buried facilities go through curb ramp replacement. - STH 59 STA 151+50 to 152+50 RT. Buried facility is adjacent to underpass removal. - Racine Avenue STA 249+85 to 254+15 RT. Buried facilities go through turn lane extension and storm sewer work. - STH 59 STA 179+00 to 182+00 LT. Buried facilities through turn lane extension and grading. - STH 59 STA 182+00 to 186+25. Buried facilities through turn lane extension and storm sewer work. - STH 59 STA 190+00 to 191+00 RT. Buried facilities through auxiliary lane addition and driveway replacement. - STH 59 STA 195+75 to 196+70 RT. Buried facilities through auxiliary lane addition. - STH 59 STA 206+30. Buried facilities through turn lane extension. - All four quadrants of STH 59 and Pearl Street. Buried and aerial facilities in the area of signal replacement. | - City of Waukesha to adjust water valves throughout the project. - City of Waukesha to verify location/depth. If there is a conflict, City of Waukesha to adjust facility prior to construction. - City of Waukesha to verify location/depth. If there is a conflict, City of Waukesha to adjust facility prior to construction. - City of Waukesha to verify location/depth of buried facilities. If there is a conflict, City of Waukesha to adjust facility prior to construction. Hydrant at 252+00 RT will need to be moved out of the new pavement prior to construction. - City of Waukesha to verify location/depth of buried facilities. If there is a conflict, City of Waukesha to adjust facility prior to construction. - City of Waukesha to verify location/depth of buried facilities. If there is a conflict, City of Waukesha to adjust facility prior to construction. - City of Waukesha to verify location/depth of buried facilities. If there is a conflict, City of Waukesha to adjust facility prior to construction. - City of Waukesha to verify location/depth of buried facilities. If there is a conflict, City of Waukesha to adjust facility prior to construction. - City of Waukesha to verify location/depth of buried facilities. If there is a conflict, City of Waukesha to adjust facility prior to construction. - City of Waukesha to verify location/depth. If there is a conflict, City of Waukesha to adjust facility prior to construction. |

City of Waukesha - Water Contact: Chris Walter

Phone: (262) 521-5272, E-mail: cwalter@waukesha-water.com

Everstream does not have any existing facilities in the project footprint.

Everstream is planning to install fiber along the east side of STH 59 from the beginning of the project to Pearl Street and on the south side of the STH 59 and Broadway Street intersection.

NOTE – For this TRANS 220 submittal the utility is to verify the depth of any buried facilities and height of any aerial facilities and determine if there is a conflict. It does not call out any of the proposed work in bold above.

Everstream Contact: Shad Garcia

Phone: (414) 908-1009, E-mail: sgarcia@everstream.net

Level 3 Communications LLC has buried facilities that cross STH 59 at the old railroad crossing/New Berlin Trail crossing.

NOTE – For this TRANS 220 submittal the potential conflict list calls out any facility within our grading as a conflict because we do not know the facility depths.  The utility is to verify the depth of any buried facilities and determine if there is a conflict.

| Location and Conflict | Resolution |
| --- | --- |
| - STA 226+45. Buried facility in pavement replacement location. | - Level 3 to verify location/depth. If there is a conflict, Level 3 to adjust facility prior to construction. |

Level 3 Communications Contact: Network Relocations

E-mail: relocations@lumen.com

MCI Metro does not have any existing facilities in the project footprint.

MCI Metro is planning to install fiber in the northwest corner of STH 59 and Pearl Street, the crossing under to the east side of STH 59, then running along the east side of STH 59 to 500’ north of Pearl Street, then crossing under to the west side of STH 59, then running along the west side of STH 59 to the New Berlin Trail crossing; at the northwest corner of STH 59 and Lincoln Avenue, then crossing under to the east side of STH 59 and running along the east side of STH 59 to the end of the project.

NOTE – For this TRANS 220 submittal the utility is to verify the depth of any buried facilities and determine if there is a conflict. It does not call out any of the proposed work in bold above.

MCI Metro Contact: Steve Nemecek

Phone: (414) 763-0921, E-mail: snemecek@visiontelcom.com

Midwest Fiber Networks LLC has aerial facilities on WE Energies poles along the south side of Broadway Street from the beginning to end of construction. No conflicts are anticipated.

Midwest Fiber Networks LLC Contact: Richard Trgovec

Phone: (414) 459-3554, E-mail: rtrgovec@midwestfibernetworks.com

PaeTec Communications has underground facilities along the east side of STH 59 from the beginning of the project to the old railroad crossing/New Berlin Trail crossing.

NOTE – For this TRANS 220 submittal the potential conflict list calls out any facility within our grading as a conflict because we do not know the facility depths.  The utility is to verify the depth of any buried facilities and determine if there is a conflict.

| Location and Conflict | Resolution |
| --- | --- |
| - Northeast corner of STH 59 and Sunset Drive. Buried facilities go through curb ramp replacement. - Northeast and southeast corners of STH 59 and Blackhawk Trail. Buried facilities go through curb ramp replacement. - STH 59 STA 177+50 to 200+65 RT. Buried facilities go through auxiliary lane addition. - Northeast and southeast quadrants of STH 59 and Pearl Street. Buried facilities go through signal replacement area. | - PaeTec to verify location/depth. If there is a conflict, PaeTec to adjust facility prior to construction. - PaeTec to verify location/depth. If there is a conflict, PaeTec to adjust facility prior to construction. - PaeTec to verify location/depth. If there is a conflict, PaeTec to adjust facility prior to construction. - PaeTec to verify location/depth. If there is a conflict, PaeTec to adjust facility prior to construction. |

PaeTec Communications Contact: Lori Ketter

Phone: (414) 274-9215, E-mail: Lori.Ketter@windstream.com

Sprint Communications has buried facilities that cross STH 59 at the old railroad crossing/New Berlin Trail crossing.

NOTE – For this TRANS 220 submittal the potential conflict list calls out any facility within our grading as a conflict because we do not know the facility depths.  The utility is to verify the depth of any buried facilities and determine if there is a conflict.

| Location and Conflict | Resolution |
| --- | --- |
| - STA 226+45. Buried facility in pavement replacement location. | - Sprint to verify location/depth. If there is a conflict, Sprint to adjust facility prior to construction. |

Sprint Communications Contact: Dan Hilliard

Phone: (612) 217-3526, E-mail: dan.j.hilliard@t-mobile.com

TDS Metrocom LLC has buried facilities that run down the center of Broadway Street from beginning to end of construction. No conflicts are anticipated.

TDS Metrocom Contact: Matthew Schulte

Phone: (262) 754-3063, E-mail: matt.schulte@tdstelecom.com

WE Energies (Electric) has aerial facilities along the east side of STH 59 from the beginning of the project to Sunset Drive that then cross over to the west side of STH 59 on the south side of Sunset Drive and cross over Sunset Drive on the east side of STH 59; aerial facilities along the west side of STH 59 from 800’ south of Blackhawk Trail to Blackhawk Trail that crosses over to the east side at the southeast corner of STH 59 and Blackhawk Trail; buried facilities along the west side of STH 59 from 250’ south of Blackhawk Trail to Racine Avenue; buried facilities along the east side of STH 59 from 700’ south of Racine Avenue to Racine Avenue; aerial facilities along the north side of Racine Avenue from the west end of construction to the east end of construction that also cross over Racine Avenue west of Guthrie Road; buried facilities that cross Racine Avenue at Fleetfoot Drive; aerial facilities along the west side of STH 59 from Racine Avenue to the old railroad crossing/New Berlin Trail crossing that cross over to the east side of STH 59 and various locations; aerial facilities that cross STH 59 on the south side of Broadway Street; buried facilities along the west side of STH 59 from the old railroad crossing/New Berlin Trail crossing to Lincoln Avenue; aerial facilities along the west side of STH 59 from Lincoln Avenue to the end of the project; aerial facilities that cross STH 59 at the old railroad crossing/New Berlin Trail crossing.

NOTE – For this TRANS 220 submittal the potential conflict list calls out any facility within our grading as a conflict because we do not know the facility depths.  The utility is to verify the depth of any buried facilities and height of any aerial facilities and determine if there is a conflict. There are poles within the grading limits and the utility is to determine if the pole can be braced during construction, if the contractor can work around the pole during construction, or if the pole needs to be relocated.

| Location and Conflict | Resolution |
| --- | --- |
| - STH 59 STA 151+50 to 152+50 LT. Aerial facility runs through to underpass removal. - Southeast corner of STH 59 and Blackhawk Trail. Aerial facilities go through curb ramp replacement. - Racine Avenue STA 239+28 to 254+15 RT. Buried and aerial facilities go through turn lane extension, median work, and storm sewer work. - STH 59 STA 177+50 to 200+65 RT. Aerial facilities go through auxiliary lane addition. - All four quadrants of STH 59 and Pearl Street. Buried and aerial facilities in the area of signal replacement. - Northwest corner of STH 59 and Lincoln Avenue. Buried facilities go through curb ramp replacement. | - WE Energies to verify if poles can remain or need to be moved. - WE Energies to verify location/depth and all pole locations. If there is a conflict, WE Energies to adjust facility prior to construction. - WE Energies to verify location/depth and all pole locations. If there is a conflict, WE Energies to adjust facility prior to construction. WE Energies to verify if poles and pedestals can remain or need to be moved. - WE Energies to verify if poles can remain or need to be moved. - WE Energies to verify location/depth and all pole locations. If there is a conflict, WE Energies to adjust facility prior to construction. WE Energies to verify if poles can remain or need to be moved. - WE Energies to verify location/depth and all pole locations. If there is a conflict, WE Energies to adjust facility prior to construction. |

WE Energies (Electric) Contact: We Energies Utility Coordinator

Phone: (414) 221-2738, E-mail: WE-Utility-Relocations@we-energies.com

WE Energies (Gas) has buried main along the east side of STH 59 from the beginning of the project to the end of the project that crosses under STH 59 at various locations; buried main along the south side of Sunset Drive from Milky Way Road to the construction limits; buried main along the west side of STH 59 from 600’ south of Blackhawk Trail to the end of the project that crosses under STH 59 at various locations; buried main that crosses STH 59 on the south side of Blackhawk Trail; buried main along the south side of Racine Avenue from the beginning to end of construction that cross under to the north side of Racine Avenue at various locations; buried main along the south side of Broadway Street; buried main along the south side of Pearl Street; buried main that crosses under STH 59 just north of the New Berlin Trail Crossing; buried main along the south side of Lincoln Avenue.

NOTE – For this TRANS 220 submittal the potential conflict list calls out any facility within our grading as a conflict because we do not know the facility depths.  The utility is to verify the depth of any buried facilities and determine if there is a conflict. Determine if the gas facility needs to be adjusted/relocated or if the contractor can work around during construction.

| Location and Conflict | Resolution |
| --- | --- |
| - Northeast corner of STH 59 and Sunset Drive. Buried facilities go through curb ramp replacement. - STH 59 STA 151+50 to 152+50. Buried facilities runs through underpass removal. - Southeast corner of STH 59 and Blackhawk Trail. Buried facility go through curb ramp replacement. - Racine Avenue STA 239+28 to 254+15 RT. Buried facilities go through turn lane extension, median work, and storm sewer work. - Northwest corner of STH 59 and Racine Avenue. Buried facilities go through curb ramp replacement. - STH 59 STA 179+00 to 182+00 LT. Buried facilities through turn lane extension and grading. - STH 59 STA 177+50 to 200+65 RT. Buried facilities go through auxiliary lane addition. - STA 226+50. Buried facility in pavement replacement location. - All four quadrants of STH 59 and Pearl Street. Buried facilities in the area of signal replacement. - Northwest corner of STH 59 and Lincoln Avenue. Buried facilities go through curb ramp replacement. | - WE Energies to verify depth. If there is a depth conflict, WE Energies to lower facility prior to construction. - WE Energies to verify depth. If there is a depth conflict, WE Energies to lower facility prior to construction. - WE Energies to verify depth. If there is a depth conflict, WE Energies to lower facility prior to construction. - WE Energies to verify depth. If there is a depth conflict, WE Energies to lower facility prior to construction. - WE Energies to verify depth. If there is a depth conflict, WE Energies to lower facility prior to construction. - WE Energies to verify depth. If there is a depth conflict, WE Energies to lower facility prior to construction. - WE Energies to verify depth. If there is a depth conflict, WE Energies to lower facility prior to construction. - WE Energies to verify depth. If there is a depth conflict, WE Energies to lower facility prior to construction. - WE Energies to verify depth. If there is a depth conflict, WE Energies to lower facility prior to construction. - WE Energies to verify depth. If there is a depth conflict, WE Energies to lower facility prior to construction. |

WE Energies (Gas) Contact: We Energies Utility Coordinator

Phone: (414) 221-2738, E-mail: WE-Utility-Relocations@we-energies.com

WisDOT Lighting WisDOT has existing lighting at the intersections of STH 59 and Sunset Drive, Racine Avenue, Broadway Street, and Pearl Street. The lighting at STH 59 and Racine Avenue will be adjusted per the new intersection layout. The highway contractor shall complete this work as participating items.

WisDOT Signals Contact: Eric Perea

Phone: (262) 574-5422, E-mail: Eric.Perea@dot.wi.gov

WisDOT Signals WisDOT has existing signals at the intersections of STH 59 and Sunset Drive, Racine Avenue, Broadway Street, and Pearl Street. The signals at STH 59 and Pearl Street will be removed and replaced as part of this project. Monotube poles will be installed at this intersection. The signals at STH 59 and Racine Avenue will be adjusted per the new intersection layout. A right turn signal will be added to the southbound STH 59 to westbound Sunset Drive right turning movement. There is interconnect cable that runs along the west side of STH 59 from Racine Avenue to 500’ north of Racine Avenue, then crosses under to the east side of STH 59 and runs along the east side of STH 59 to Broadway Street. The highway contractor shall complete this work as participating items.

| Location and Conflict | Resolution |
| --- | --- |
| - STH 59 STA 179+00 to 182+00 LT. Buried facilities through turn lane extension and grading. - STH 59 STA 177+50 to 200+65 RT. Buried facilities go through auxiliary lane addition. | - WisDOT signals to verify depth. If there is a depth conflict, WisDOT signals to include in final plans. - WisDOT signals to verify depth. If there is a depth conflict, WisDOT signals to include in final plans. Pullbox will also need to be adjusted or moved. |

WisDOT Signals Contact: Derrin Wolford

Phone: (262) 521-4409, E-mail: derrin.wolford@dot.wi.gov