## Summary of Changes
N Port Washington Road
Bender Rd to W Daphne Rd
Project ID 1229-04-71
DT1078 REV 1
Summary of Plan Changes
(10/1/2021)
1. | Traffic Signals added at Port Washington Rd/Clovernook Ln intersection. ~ Refer to sheet 249-250 in Traffic Signal Plan.
2. | Temporary pavement and curb eliminated on Port Washington Rd, under UPRR bridge. Trunk line storm sewer under UPRR bridge moved from west curb line to east curb line. ~ Refer to sheets 174-175 in Storm Sewer Plan ~ Refer to sheet 346 in Plan and Profile ~ Refer to sheets 951-954 in Cross Sections
3. | Additional pavement replacement (base patching) for signal loop detectors at Port Washington Rd and Bender Rd/Devon St intersection. ~ Refer to sheets 246-248 in Traffic Signal Plan
4. | Modifications to the proposed storm sewer in the following locations: ~ Pipe went from 201P to 202. The pipe run was extended from 202 to existing structure west of I-43 near Jean Nicolet Rd. ~ Refer to sheets 174 in Storm Sewer Plan
5. | Landscape grading feature added at back of sidewalk along Port Washington Rd from 116+00 to 127+50 ~ Refer to sheets 955-962 in Cross Sections
6. | Port Washington Rd median between Coventry Ct and Cardinal Stritch University driveway reconstructed. Median will be removed and paved with temporary asphalt during construction and reconstructed at the same location and elevations at the end of the project. ~ Refer to sheet 227 in Lighting Plan ~ Refer to sheet 348 in Plan and Profile