## Summary of Changes
N Port Washington Road
Bender Rd to W Daphne Rd
Local Street
Milwaukee County, Wisconsin
Project ID 1229-04-71
DT1078 REV 2
Summary of Plan Changes
(12/15/2021)
1. | Storm Sewer Plans: The following Storm Sewer laterals along Port Washington Road were relocated: - Storm lateral at Station 105PN+75 shifted 10' to the north. Please note vertical elevations did not change. ~Replaces sheet 174-175 in Proposed Drainage Plan of original DT1078 plan set
2. | Storm Sewer Plans: Storm Sewer trunkline along Port Washington Road was relocated from the SB median shoulder to the NB median shoulder from Station 131PN+60 to Station 136PN+30. All trunkline elvations were raised approximately 1.5'-2.0' to better connect into existing storm sewer. ~Replaces sheets 178-180 in Proposed Drainage Plan of original DT1078 plan set
3. | Temporary Signal Plans: Add temporary traffic signal pole layout for the intersection of Bender Rd & Port Washington Rd. ~New sheet, insert after sheet 240 of original DT1078 plan set
4. | Traffic Control Crossovers: Crossovers for staged construction added at the Port Washington Road and Bender Road intersection (south leg). ~New sheet, insert after sheet 265 of original DT1078 plan set