## Summary of Changes
I-43 North South Freeway
Bender Road to Brown Deer Road
IH 43
Milwaukee County, Wisconsin
Project ID 1229-04-73
DT1078 REV 1
Summary of Plan Changes
(12/15/2021)
1. | Storm Sewer trunkline along mainline I-43 was relocated from the SB median shoulder to the NB median shoulder in the following areas. Please note the vertical elevations of the storm sewer in this area did not change. -Station 1080+50 to Station 1119+50 -Station 1124+50 to Station 1130+20 -Station 1133+00 to Station 1134+80 -Station 1138+00 to Station 1148+50 -Station 1152+00 to Station 1154+00 -Station 1159+00 to Station 1177+00 -Station 1179+00 to Station 1191+00 ~Replaces sheets 103-123 in Proposed Drainage Plan of original DT1078 plan set
2. | The following Storm Sewer laterals along mainline I-43 were relocated: - Storm lateral at Station 1109+50 shifted 15 feet south. Vertical elevations did not change. Refer to sheet 108 in Storm Sewer. - Storm lateral at Station 1130+50 crossing NB I-43 was removed. Refer to sheet 113 in Storm Sewer. - Storm inlet at Station 20GH+25 was shifted in NE Quadrant of Good Hope Road and Pheasant Lane. Refer to Sheet range 148-153 in Storm Sewer - Storm inlets at Station 29GH+90 were shifted in the NE Quadrant of Good Hope Road and Port Washington Road and an inlet was added in the SE Quadrant of Good Hope Road and Port Washington Road. Refer to Sheet range 148-153 in Storm Sewer. -Storm inlet at Station 1149GHA+75 was added in Good Hope Ramp A. Refer to Sheet range 148-153 in Storm Sewer.
3. | Storm Sewer trunkline along mainline I-43 was relocated from the SB median shoulder to the NB and SB outside shoulder in the following areas. Please note vertical elevations of the storm sewer in this area have changed. -Station 1217+00 to Station 1265+00 ~Refer to sheets 127-135 in Storm Sewer. ~ New sheets, insert after sheet 128 and 130 of original DT1078 plan set
4. | Adjusting Lighting poles spacing in IH 43 median to avoid conflict with the butterfly sign structure between Bender Rd. and Green Tree Rd. and provide better uniformity. ~Replaces sheets 205-209 in Lighting Plan of original DT1078 plan set
5. | Light pole at STA. 1143+64.29 moved to STA 1146+50.00 to provide 50-FT clearance for the sign structure at STA 1144+00.00 Light pole at STA 1147+18.41 moved to STA 1147+00.00 to provide better uniformity. ~Replaces sheets 210 in Lighting Plan of original DT1078 plan set
6. | All light poles at off-ramps and on-ramps with Good Hope interchange were moved close to the roadway to provide better uniformity. ~Replaces sheets 209-211 in Lighting Plan of original DT1078 plan set
7. | Revised light Poles location and spacing on all Brown Deer On and Off ramps, and Brown Deer Rd. due to newly updated WisDOT Luminaires Data files, and to provide better uniformity. ~Replaces sheets 216-221 in Lighting Plan of original DT1078 plan set
8. | Traffic Signal updates to Good Hope & I-43 Ramps: - Move traffic signal cabinets to SE quadrant at both ramp terminals - Added conduit connection across bridge, between ramp terminals - Increase size of Loops 81, 82, 61, 62, 63, 64, S2 and S3 at SB ramp terminal ~ Replaces sheets 228-231 in Traffic Signal Plan of original DT1078 plan set
9. | Traffic Signal updates to Brown Deer & Port Washington Rd: - Change SB3 to 20-ft monotube - Add 50-ft monotube to SB9 - Remove monotube from SB11 - Increase size of SB15 - Add 20-ft monotube to SB19 and relocate - Change SB20 to a 45-ft monotube - Remove/replace PB16, PB19, PB20 - Install new concrete bases for SB8, SB9, SB13, SB14, and SB16 ~ Replaces sheets 238-240 in Traffic Signal Plan of original DT1078 plan set
10. | Add temporary traffic signal pole layout for the intersections of Good Hope Rd & Port Washington Rd and Brown Deer Rd & Port Washington Rd. ~ New sheets, insert after sheet 240 of original DT1078 plan set
11. | Traffic Signal Updates to Good Hope Rd interconnect: - Connect into existing interconnect conduit at NE quadrant of Good Hope Rd & Port Washington Rd - Conduit run between ICPB1 and ICPB2 crosses Good Hope Rd and connects into signal cabinet in SE quadrant ~ Replaces sheets 242 in Traffic Signal Plan of original DT1078 plan set
12. | Crossovers for staged construction added at the west limits of Good Hope Road and Good Hope Road and Port Washington Road (north and south legs). ~ New sheet, insert after sheet 265 of original DT1078 plan set
13. | Right-of-Way Plat updated to include: - Additional triangular parcel of land purchased west of I-43 and north of Green Tree Road - New right-of-way line for Parcel 80 moved 4' east toward I-43 ~ Replaces sheets 287 and 292 in the 1229-04-22 Right-of-Way Plat
14. | Indian Creek structures B-40-1026, B-40-1027,and B-40-1028 updated to include: - Removal of the entire existing box culvert. - Constructing stream bed from coarse aggregate mix and add additional temporary shoring for construction staging. ~ Replaces sheets 409-426 in Structure Plans of original DT1078 plan set
15. | Revised alignment of noise wall N-40-102. Plan set to be swapped out. 1 extra page is included in plan set. ~ Replaces sheets 456-465 in Structure Plans of original DT1078 plan set
16. | IH-43 cross sections updated from STA 1271+00 to STA 1282+50 to show proposed noise wall on the east side of IH-43 ~ Replaces sheets 788-796 in Cross Sections of original DT1078 plan set