## Sheet1
WISDOT / FOXCONN / PUBLIC UTILITIES COORDINATION MEETING
LOCAL ROADS - RACINE COUNTY
2018-11-28
ACTION ITEMS
Item | Action | Date Initiated | Ball-in-Court | Due Date | Next Step / Dependent On
1 | CTH KR Lift Station - Foth to discuss the existing & proposed lift stations with Mt. Pleasant to determine if existing lift station can be discontinued. | 2018-09-26 | Mt. Pleasant (T. Beyer), Foth (D. Snyder) | 2018-11-30
2 | WVW and STH 11 Real Estate & Utilities - DOA & WisDOT will schedule a meeting to discuss the status of real estate at WVW and STH 11, and impact on utility schedules. Plat will be revised. Sign-off by Village in mid/late November. Acquire by February 1. | 2018-10-03 | DOA (R. Berry), WisDOT (S. Hoff) | 2018-11-28
3 | WVW storm sewer - HNTB to send revised storm sewer files to utilities when available. | 2018-10-31 | Kapur (Prasad), HNTB (P. Bielefeld) | 2018-11-14 | COMPLETED
4 | UPRR Permits - Utilities to send list of outstanding (and future) permits where they cross the UPRR. HNTB to compile table. DOA to help expidite permit process. | 2018-10-31 | DOA (R. Berry), HNTB (P. Bielefeld) | 2018-11-28
5 | CTH H southbound right turn lane into UNFI - HNTB to inform Village of Sturtevant of this design change | 2018-11-14 | HNTB (TJ Dougherty) | 2018-11-28 | COMPLETED