## Summary of Changes
Braun East REV 2
CTH H to 90th Street
Project ID 2704-09-71
Summary of Changes
(5/13/2019)
1. | Driveway to Pond Q added at 173BRW+25, LT which includes: ~ Addition of eastbound left turn lane off of Braun Road. ~ Addition of median opening. ~ Changes to the drainage, including ditching, slope intercepts, storm sewer, and culverts to accommodate the addition of the driveway.
2. | Modifications to the western leg of the 90th Street intersection from 197BRE+78 to 208BRE+00 which includes: ~ Addition of eastbound left turn lane. ~ Additional pavement widening to the south. ~ Sidewalk and handicap ramp locations. ~ Updates to the drainage, including ditching, slope intercepts, and storm sewer. ~ Updates to the x-sections.
3. | Addition of temporary storm sewer for temporary pavement along the west side of 90th Street.
4. | Modifications to the eastern leg of the 90th Street intersection from 208BRE+00 to 214BRE+75 which includes: ~ Reconstuction of two new driveways at 210BRE+22, LT and 211BRE+65, LT. ~ Addition of westbound left turn lane. ~ Additional pavement widening to the south. ~ Sidewalk and handicap ramp locations. ~ Updates to the drainage, including ditching, slope intercepts, storm sewer, and culverts at the driveways. ~ Updates to the x-sections.
5. | Additional right-of-way purchased at the 90th Street intersection (refer to plat), which includes: ~ South leg of intersection - west side. ~ South leg of intersection - east side. ~ North leg of intersection - west side. ~ East leg of intersection - south side.