## Prelim
Zoo Interchange E-Submittal and Deliverable Checklist
HNTB Preliminary Submittals
|  | Target Submittal Date | Prelim Plans _pln.pdf | SSR _ssr.doc | Road Plans _rod.pdf | Maps _map.pdf | Photos _pic.pdf | Geotech _geo.pdf | Actual E-Submit Date | WisDOT Approval | PQP files done?
2013 Construction
B-40-433 | UPRR tunnel under STH 100/Bluemound | 2011-09-01 | X | X | X | X | X | X | 2011-09-02 | 2011-09-29
R-40-474 | NE corner STH 100/Watertown Plank | 2011-09-01 | X | X | X | X | X | X | 2011-09-01 | 2011-09-26
R-40-475 | Wall at tunnel extension | 2011-09-01 | X | X | X | X | X | X | 2011-09-01 | 2011-09-26
R-40-476 | Wall at tunnel extension | 2011-09-01 | X | X | X | X | X | X | 2011-09-01 | 2011-09-26
R-40-477 | Wall at tunnel extension | 2011-09-01 | X | X | X | X | X | X | 2011-09-01 | 2011-09-26
2014 Construction
B-40-770 | STH 100 SB over IH 94 | 2012-03-01 | X | X | X | X | X | X | 2012-03-01 | 2012-03-29
B-40-771 | STH 100 NB over IH 94 | 2012-03-01 | X | X | X | X | X | X | 2012-03-01 | 2012-03-29
B-40-773 | UPRR over IH 94 | 2012-03-01 | X | X | X | X | X | X | 2012-03-01 | 2012-03-28
B-40-774 | UPRR over HAST | 2012-03-01 | X | X | X | X | X | X | 2012-03-01 | 2012-03-28
B-40-868 | STH 100 U-ramp | 2012-07-16
B-40-890 | Zoo Access Tunnel South End Extension | 2012-07-16
R-40-471 | Wall at S Abut STH 100 over IH 94 | 2012-03-01 | X | X | X | X | X | X | 2012-03-01 | 2012-04-16 | X
R-40-472 | Wall at N Abut STH 100 over IH 94 | 2012-03-01 | X | X | X | X | X | X | 2012-03-01 | 2012-04-16 | X
R-40-482 | Wall at SW corner B-40-774 | 2012-03-01 | X | X | X | X | X | X | 2012-03-01 | 2012-04-04
R-40-524 | Wall along N side of Schlinger Ave | 2012-04-16 | X | X | X | X | X | X | 2012-04-16
R-40-525 | Wall along S side of Schilinger Ave | 2012-04-16 | X | X | X | X | X | X | 2012-04-16
R-40-537 | Wall at S Abut B-40-868 | 2012-07-16
R-40-538 | Wall at N Abut B-40-868 | 2012-07-16
2015-2017 Construction
B-40-850 | E-N (Core) | 2013-02-01
B-40-851 | S-E (Core) | 2012-12-01
B-40-853 | N-E Ramp (Core) | 2012-12-01
B-40-854 | E-S Ramp (Core) | 2013-02-01
B-40-869 | IH 94 WB over HAST | 2012-11-01
B-40-870 | IH 94 EB over HAST | 2012-11-01
B-40-878 | UPRR over USH 45 (North Leg) | 2013-06-01
B-40-891 | Over Zoo Access Tunnel North End | 2012-12-01
R-40-497 |  | 2012-12-01
R-40-501 | Wall attached to B-40-891 | 2012-12-01
R-40-505 |  | 2012-12-01
R-40-507 |  | 2013-02-01
R-40-509 |  | 2013-02-01
R-40-510 |  | 2012-12-01
R-40-511 |  | 2012-11-01
R-40-512 |  | 2012-11-01
R-40-514 |  | 2012-11-01
R-40-539 |  | 2012-11-01
R-40-540 |  | 2012-11-01
R-40-546 |  | 2012-11-01
R-40-547 |  | 2013-02-01
R-40-551 |  | 2012-11-01
R-40-552 |  | 2012-11-01
R-40-556 | W side of USH 45, under Bluemound Rd | 2012-09-15 | X | X | X | X | X | X | 2012-09-14 |  | X
B-40-871 | IH 94 WB over 121st St/Curtis Rd (Who?)
B-40-872 | IH 94 EB over 121st St/Curtis Rd (Who?)
B-40-873 | IH 94 WB over Underwood Creek (Who?)
B-40-874 | IH 94 EB over Underwood Creek (Who?)
B-40-882 | USH 45 over RR (South Leg) - CH2M
B-40-883 | USH 45 over RR (South Leg) - CH2M
R-40-508
R-40-532
R-40-549
R-40-560 | W side of USH 45, btwn WTP Rd and Wisconsin Ave

## BOS SSRs
Zoo Interchange E-Submittal and Deliverable Checklist
SSRs for BOS-designed Structures
|  | Target Submittal Date | SSR _ssr.doc | Road Plans _rod.pdf | Maps _map.pdf | Photos _pic.pdf | Geotech _geo.pdf | Layout Sketch _oth.pdf | Actual E-Submit Date
Watertown Plank Road 1060-33-72
B-40-777 |  | 2011-11-01 | X | X | X | X | NA | X | 2011-11-01
B-40-778 |  | 2011-11-01 | X | X | X | X | NA | X | 2011-11-01
B-40-779 |  | 2011-11-01 | X | X | X | X | NA | X | 2011-11-01
B-40-780 |  | 2011-11-01 | X | X | X | X | NA | X | 2011-11-01
B-40-781 |  | 2011-11-01 | X | X | X | X | NA | X | 2011-11-01
B-40-782 |  | 2011-11-01 | X | X | X | X | NA | X | 2011-11-01
R-40-491 |  | 2011-11-01 | X | X | X | X | NA | X | 2011-11-01
R-40-492 |  | 2011-11-01 | X | X | X | X | NA | X | 2011-11-01
76th St 1060-33-78
B-40-799 | Ramp GE over Schlinger Ave. | 2012-01-25 | X | X | X | X | NA | X | 2012-01-26
2015-2018 Construction
B-40-795 | 45 SB/Ramp ES over Schlinger | 2012-05-01 | X | X | X | X | NA | X | 2012-05-08
B-40-796 | WS/CS Ramp over Schlinger | 2012-05-01 | X | X | X | X | NA | X | 2012-05-08
B-40-797 | 45 SB over Schlinger | 2012-05-01 | X | X | X | X | NA | X | 2012-05-08
B-40-798 | 45 NB over Schlinger | 2012-05-01 | X | X | X | X | NA | X | 2012-05-09
B-40-849 | SW/SE Gore over Schlinger | 2012-05-01 | X | X | X | X | NA | X | 2012-05-08
B-40-852 | N-W Ramp | 2012-05-01 | X | X | X | X | NA | X | 2012-05-10
B-40-861 | S-E Ramp | 2012-05-01 | X | X | X | X | NA | X | 2012-05-03
B-40-862 | 92nd St. over IH 94 | 2012-05-01 | X | X | X | X | NA | X | 2012-05-03
B-40-863 | IH 94 WB over 84th St. | 2012-05-01 | X | X | X | X | NA | X | 2012-05-01
B-40-864 | IH 94 EB over 84th St. | 2012-05-01 | X | X | X | X | NA | X | 2012-05-01
2015-2018 Construction -- North Leg
B-40-792
B-40-793
B-40-794
B-40-875
B-40-876
B-40-877
B-40-879
B-40-880
B-40-881
R-40-561
R-40-562
R-40-563
R-40-565
R-40-567
R-40-568
R-40-569
R-40-570
R-40-576
R-40-578
2018 Construction
R-40-563
R-40-566
R-40-571
R-40-572
R-40-573
R-40-574
R-40-575
R-40-577

## Final 2013
Zoo Interchange E-Submittal and Deliverable Checklist
HNTB Final Submittals -- 2013 Construction
|  | Target Submittal Date (2 mo. before Final PS&E) | Final Plans _pln.pdf | Geotech _geo.pdf | Quantities _qty.pdf | Special Provisions _spe.pdf/doc | Inventory Form _inv.pdf/doc | Computations _com.pdf | Quality Form _qc.pdf | Rating Form _rat.pdf | Rating Input Spreadsheet _rat.xls | Other _oth.xxx | Actual E-Submit Date | WisDOT Review | Quantities & Estimate for Transport
STH 100 1060-33-70
2012.06.01 Final Submittal to BOS
B-40-433 | UPRR tunnel under STH 100/Bluemound | 2012-06-01 | X | X | X | X | X | X | X | X | NA | NA | 2012-06-01 | 2012-07-07 | X
R-40-475 | Wall at tunnel extension | 2012-06-01 | X | X | X | X | X | X | X | NA | NA | NA | 2012-06-01 |  | X
R-40-476 | Wall at tunnel extension | 2012-06-01 | X | X | X | X | X | X | X | NA | NA | NA | 2012-06-01 |  | X
R-40-477 | Wall at tunnel extension | 2012-06-01 | X | X | X | X | X | X | X | NA | NA | NA | 2012-06-01 |  | X
2012.08.01 Final PSE
B-40-433 | UPRR tunnel under STH 100/Bluemound | 2012-08-01 | X | X | X | X | NA | X | NA | NA | NA | X | 2012-08-01 |  | X
R-40-475 | Wall at tunnel extension | 2012-08-01 | X | X | NA | X | NA | NA | NA | NA | NA | NA | 2012-08-01 |  | X
R-40-476 | Wall at tunnel extension | 2012-08-01 | X | X | X | X | NA | NA | NA | NA | NA | NA | 2012-08-01 |  | X
R-40-477 | Wall at tunnel extension | 2012-08-01 | X | X | X | X | NA | NA | NA | NA | NA | NA | 2012-08-01 |  | X

## Final 2014
Zoo Interchange E-Submittal and Deliverable Checklist
HNTB Final Submittals -- 2014 Construction
|  | Target Submittal Date (2 mo. before Final PS&E) | Final Plans _pln.pdf | Geotech _geo.pdf | Quantities _qty.pdf | Special Provisions _spe.pdf/doc | Inventory Form _inv.pdf/doc | Computations _com.pdf | Quality Form _qc.pdf | Rating Form _rat.pdf | Rating Input Spreadsheet _rat.xls | Other _oth.xxx | Actual E-Submit Date | WisDOT Review | Quantities & Estimate for Transport
RR1 1060-33-75
2013.03.01 Final Submittal to BOS
B-40-770 | STH 100 SB over IH 94 | 2013-03-01 | X | X | X | X | X | X | X | X | X | NA | 2013-03-01
B-40-771 | STH 100 NB over IH 94 | 2013-03-01 | X | X | X | X | X | X | X | X | X | NA | 2013-03-01
B-40-773 | UPRR over IH 94 | 2013-03-01 | X | X | X | X | X | X | X | NA | NA | NA | 2013-04-01 | 2013-04-22
B-40-774 | UPRR over HAST | 2013-03-01 | X | X | X | X | X | X | X | NA | NA | NA | 2013-03-29
B-40-868 | STH 100 U-Ramp | 2013-03-01 | X | X | X | X | X | X | X | X | NA | NA | 2013-03-15
B-40-890 | Zoo Access Tunnel South End Extension | 2013-03-01 | X | X | X | X | X | X | X | X | NA | NA | 2013-03-01
R-40-471 | Wall at S Abut STH 100 over IH 94 | 2013-03-01 | X | X | X | X | X | X | X | NA | NA | NA | 2013-03-01
R-40-472 | Wall at N Abut STH 100 over IH 94 | 2013-03-01 | X | X | X | X | X | X | X | NA | NA | NA | 2013-03-01
R-40-482 | Wall at SW corner B-40-774 | 2013-03-01 | X | X | X | X | X | X | X | NA | NA | NA | 2013-04-01
2013.05.01 Final PSE
B-40-770 | STH 100 SB over IH 94 | 2013-05-01 |  |  |  |  | NA |  | NA |  |  | NA
B-40-771 | STH 100 NB over IH 94 | 2013-05-01 |  |  |  |  | NA |  | NA |  |  | NA
B-40-773 | UPRR over IH 94 | 2013-05-01 |  |  |  |  | NA |  | NA |  | NA
B-40-774 | UPRR over HAST | 2013-05-01 |  |  |  |  | NA |  | NA |  | NA | NA
B-40-868 | STH 100 U-Ramp | 2013-05-01 |  |  |  |  | NA |  | NA |  | NA | NA
B-40-890 | Zoo Access Tunnel South End Extension | 2013-05-01 |  |  |  |  | NA |  | NA |  | NA | NA
R-40-471 | Wall at S Abut STH 100 over IH 94 | 2013-05-01 |  |  |  |  | NA |  | NA | NA | NA | NA
R-40-472 | Wall at N Abut STH 100 over IH 94 | 2013-05-01 |  |  |  |  | NA | NA | NA | NA | NA | NA
R-40-482 | Wall at SW corner B-40-774 | 2013-05-01 |  |  | NA |  | NA | NA | NA | NA | NA | NA
TL 1060-33-78
2013.03.01 Final Submittal to BOS
R-40-482 | Wall at SW corner B-40-774 | 2013-03-01 | X | X | X | X | X | X | X | NA | NA | NA | 2013-03-01
2013.05.01 Final PSE
R-40-482 | Wall at SW corner B-40-774 | 2013-05-01 |  |  |  |  | NA | NA | NA | NA | NA | NA

## Final 2015
Zoo Interchange E-Submittal and Deliverable Checklist
HNTB Final Submittals --Core 1
|  | Target Submittal Date (2 mo. before Final PS&E) | Final Plans _pln.pdf | Geotech _geo.pdf | Quantities _qty.pdf | Special Provisions _spe.pdf/doc | Inventory Form _inv.pdf/doc | Computations _com.pdf | Quality Form _qc.pdf | Rating Form _rat.pdf | Rating Input Spreadsheet _rat.xls | Controlling Rating Analyis File (ConSpan etc.) | Other _oth.xxx | Actual E-Submit Date | WisDOT Review | Quantities & Estimate for Transport
Z1 1060-33-80
2014.03.01 Final Submittal to BOS | [12 empty] | MDX
B-40-891 | I94 EB/Ramp SA over Zoo Access Tunnel Entry | 2014-02-28
R-40-504 | Wall along Zoo IC Ramp NW | 2014-02-28 | [7 empty] | NA | NA | NA | NA
R-40-511 | Wall along Zoo IC Ramp NW | 2014-02-28 | [7 empty] | NA | NA | NA | NA
R-40-525 | Wall along South Side of Schlinger Ave. | 2014-02-28 | [7 empty] | NA | NA | NA | NA
2014.05.01 Final PSE
B-40-891 | I94 EB/Ramp SA over Zoo Access Tunnel Entry | 2014-05-01 | [8 empty] | NA | NA
R-40-504 | Wall along Zoo IC Ramp NW | 2014-05-01 | [7 empty] | NA | NA | NA | NA
R-40-511 | Wall along Zoo IC Ramp NW | 2014-05-01 | [7 empty] | NA | NA | NA | NA
R-40-525 | Wall along South Side of Schlinger Ave. | 2014-05-01 | [7 empty] | NA | NA | NA | NA

## Final 2018
Zoo Interchange E-Submittal and Deliverable Checklist
HNTB Final Submittals -- 2014 Construction
|  | Target Submittal Date (2 mo. before Final PS&E) | Final Plans _pln.pdf | Geotech _geo.pdf | Quantities _qty.pdf | Special Provisions _spe.pdf/doc | Inventory Form _inv.pdf/doc | Computations _com.pdf | Quality Form _qc.pdf | Rating Form _rat.pdf | Rating Input Spreadsheet _rat.xls | Other _oth.xxx | Actual E-Submit Date | WisDOT Review | Quantities & Estimate for Transport
ZN 1060-33-84
2017.08.01 Final PSE and Submittal to BOS
B-40-878 | UPRR over USH 45 | 2017-08-01 | [7 empty] | NA | NA |  |  |  |  | oth: Prelim, UPRR and SER-Const Comments
R-40-622 | Wall at SE corner B-40-878 | 2017-08-01 | [7 empty] | NA | NA |  |  |  |  | oth: Prelim, UPRR and SER-Const Comments

## UPRR 4th 60% Submittal
Zoo Interchange UPRR Deliverable Checklist
HNTB Final Submittal -- Construction (Plans on Shelf)
Complete?
ZN 1060-33-84
2017.12.22 UPRR 4th 60% Submittal
| 60percentUPRR_STRUCTURE-PLANS_MP-91.86_2017-12-22.pdf | X
60percentUPRR_TRACK-PLANS_MP-91.86_2017-12-22.pdf **
| 60percentUPRR_STRUCTURE-CALCULATIONS_MP-91.86_2017-12-22.pdf | X
| 60percentUPRR_SPECS_SPECIALS-THEN-STDS_MP-91.86_2017-12-22.pdf | X
| 60percentUPRR_GEOT-REPORT_MP-91.86_2016-06-20.pdf | X
| 60percentUPRR_HYDRO-REPORT_MP-91.86_2017-12-22.pdf | X
| F45Response_17-08-08 UPRR Track Design Comments.xlsx | X
| F45Response_17-08-07_RAIL_UPRR_BR_91.84_60%25 Submittal_OA.docm | X
** (includes separate sheet giving UPRR-installed material)

## Sheet1
Preliminary Structure Submittals: 2015-2017 Construction
|  | Target Submittal Date | Lead for PE (up to now)
B-40-850 | E-N (Core) | 2013-02-01 | Colin
B-40-851 | S-E (Core) | 2012-12-01 | Heather
B-40-853 | N-E Ramp (Core) | 2012-12-01 | Josh
B-40-854 | E-S Ramp (Core) | 2013-02-01 | Eric
B-40-869 | IH 94 WB over HAST | 2012-11-01 | Colin
B-40-870 | IH 94 EB over HAST | 2012-11-01 | Colin/Eric
B-40-878 | UPRR over USH 45 (North Leg) | 2013-06-01
B-40-891 | Over Zoo Access Tunnel North End | 2012-12-01
R-40-497 |  | 2012-12-01 | Eric
R-40-501 | Wall attached to B-40-891 | 2012-12-01
R-40-505 |  | 2012-12-01 | Matt
R-40-507 |  | 2013-02-01 | Matt
R-40-509 |  | 2013-02-01 | Kerry
R-40-510 |  | 2012-12-01 | Josh
R-40-511 |  | 2012-11-01 | Mark
R-40-512 |  | 2012-11-01 | Eric
R-40-514 |  | 2012-11-01 | Matt
R-40-539 |  | 2012-11-01 | Matt
R-40-540 |  | 2012-11-01 | Matt
R-40-546 |  | 2012-11-01 | Mark
R-40-547 |  | 2013-02-01 | Kerry
R-40-551 |  | 2012-11-01 | Kerry
R-40-552 |  | 2012-11-01 | Kerry
Final Design for Hwy 100 Structures
Beth - Lead and superstructure
Eric - Abutments
Colin - Piers