## Project Comments
|  |  | Project Name: Bridge Replacement - UPRR over I-41/US 45 |  | Submittal: 25% (No Plans - Response to WisDOT Comments) | UPRR Milepost: 91.86 | Subdivision: Milwaukee
|  |  | City: Wauwatosa | State: WI | Track Territory: 136# ISHH, Wood | TTS: 40mph | Reviewer: Chris Napierala
|  |  | Special Notes: Please respond to comments below and then forward this document with updated copies of the plans for the next submittal. |  |  |  | Designer/ Company: WIDOT
Public Project Guidelines and checklist are available online. Go here: http://www.up.com/customers/ind-dev/operations/specs/public_projects/index.htm
Item No. | Sheet No. | Status (Open or Closed | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response | Reviewer Comment | Designer's Response
|  |  | Date: 10/28/2013 | Date: 11/26/2013 | Date: 12/20/2013 | Date: 02/14/2014 | Date: 06/02/2014 | Date: 09/26/2014 | Date: 10/07/2014 | Date: 09/01/2015 | E. Keiner 8/25/2016 | Name/Date: JWCIII 12/22/2016 | ESK/CAN 1/19/2017 | Name/Date: JWCIII 7/20/2017 | Name/Date: ChrisN 08/07/2017 | Name/Date: CAZ 07/30/2019 | Name/Date: | Name/Date: | Name/Date: | Name/Date: | Name/Date: | Name/Date: | Name/Date: | Name/Date: | Name/Date: | Name/Date: | Name/Date: | Name/Date: | Name/Date: | Name/Date:
1 |  | Closed | Minimum track center requirement is 15' for both shoofly and final alignment. | We will provide.
2 |  | Closed | Std. 7"x9"x9' ties required | We will provide.
3 |  | Closed | 300' min. tangent between reverse curves required. | We will provide. However, in order to get the reverse curves to fit between this crossing and the crossing over North Avenue (MP 92.21) that is ~1000 feet north, as well as avoid the existing fill retaining wall just west of the west temporary mainline track, we are using 2" unbalanced superelevation, which allows 50' spirals per UPRR Std. Dwg. 0019A. | Unbalance needs to be 1", Spirals need to be sized appropriately per UPRR STD drawings based on 1" unbalance. All Bridges (Ex. And Prop.) need to be labeled in plan view and profile. (See below). Min. 50' clearance can be used for Shoofly from the North backwall to the beginning point of the spiral if needed. South end should maintain 100'. Design standards need to be met on the south side of the bridge. | We will provide.
4 |  | Closed | Maximum V/L for vertical curves, sag = 0.06, summit = 0.10 | Both the new alignment and the temporary alignment are in a sag curve. We can provide a maximum r-value of 0.06 for the new permanent alignment. However for the temporary alignment, we are unable to provide the 0.06 maximum r-value for 3 of the 4 curves, (although these 3 curves do meet AREMA requirements for 40 mph). For the temporary west ML alignment north of the crossing, we would need to either add ballast under the track north of the tie-in to over the existing North Avenue structure (MP 92.21), or drop the vertical alignment over USH 45 to meet the subject criteria; both activities we presume that UPRR would not approve for a temporary condition. For the temporary east and west ML alignments south of the crossing, we would either need to add ballast under the track 100' south of the tie-in (which would have to be removed when cutting the track back onto the permanent alignment), or drop the vertical alignment over USH 45; both activities we presume that UPRR would not approve for a temporary condition.
5 |  | Closed | Sheet PRE_13 shows vertical curve between station 16 and 17 where there is no change in annotated grade. | We will revise.
6 |  | Closed | Existing T/R surface and elevations at 100' stations to be shown in profile, not existing ground surface. | We will provide.
7 |  | Closed | All construction requires 136 # ISHH, transition rails to existing 115#. | We will reference this in our 60% submittal, along with specifications for constructing 136# ISHH. |  |  | Will verify on 60% plans. | We will provide at 60%.
8 |  | Closed | Reference UPRR Engineering Track Standards, UPRR Track Material and Construction specifications, and UP Railroad Track Construction Specifications in track plans. | We will reference these in our contract special provisions that will be submitted for review at 60% stage, (which under WisDOT contract document hierarchy, the special provisions hold greater weight than the plans). |  |  | Please add note to plans in addition to special provisions. | We will provide. | Will verify once it has been added.
9 |  | Closed | Track geometry must be approved before progressing the plan set. | In conformance with this comment, we resubmit the track geometry for your review. |  |  | Shoofly geometry is acceptable. Need to add horizontal curves to final alignment per comment 22. | Please see response to comment #22. | See continuation of comment #22
10 |  | Closed |  |  | UPRR line styles and symbology needs to be used on plans. Plans should be printed in color. | We will provide consistent with the UPRR example plan & profile labeling, and UPRR line styles and symbology sent back with these comments. (See last page.)
11 |  | Closed |  |  | Curves need to be concentric. | We will provide.
12 |  | Closed |  |  | Grades on shoofly and proposed profiles at the beginning and ends of the profile are inconsistent. Are you tying into an existing curve? Why is there a variance? | It is because we are tying into an existing vertical curve. The proposed vertical is matching both the instantaneous slope and elevation of the temporary vertical alignment. This is the reason for the variance shown in the plans.
13 |  | Closed |  |  | Existing Top of Rail should be shown and labeled 1000' on each side of structure or 200' past the end of the proposed project. - Whichever is greater. | We will provide.
14 |  | Closed |  |  | Show North Ave Bridge on plan and profile. | We will provide.
15 |  | Closed |  |  | 9' Clearance is not sufficient to maintain our typical section. 12' min. is needed (depending on wall elevation). | We will provide. Span lengths, north abutment for temporary shoofly bridge, and roadway traffic staging have been shifted south to accommodate.
16 |  | Closed |  |  | Show top of retaining wall elevations on profile. | We will provide.
17 |  | Closed |  |  |  |  | Please provide sheet numbers. | We will provide.
18 |  | Closed |  |  |  |  | Label abutment stationing on each track on both sides of the bridge. | We will provide.
19 |  | Closed |  |  |  |  | Need to provide details on the structures to be abandoned. | We will provide. Both structures to be abandoned (at Temp. East Track Sta. 10+05.64 and Sta. 16+91.18) will be filled with CLSM and plugged at the ends. |  | Provided in this 60% submission. (Detail in 09/26/14 response previously shown on plan and profile sheets. See SPV's for complete instructions and payment.)
20 |  | Closed |  |  |  |  | Need to label existing tie type/ rail weight. | We will provide.
21 |  | Closed |  |  |  |  | Show transition rail locations | We will provide.
22 |  | Closed |  |  |  |  | Horizontal curves with spirals are needed on the final alignment. Plans currently just show PI's. Curve length should be 100' min. End of curve to bridge also needs to be 100' | We used PI's because our curves would be very small. In order to get as large a curve as possible, we are holding the east track at a tangent and widening the west track with curves to 15' track centers (not centered crossing the bridge). This gives us four 00°06'00" curves for the west track. Since these slight curves are below the limits of UPRR ES #0021E (min. deg. curve is 00°30'00"), we ran the calculation for 1" unbalanced, which gave us a negative superelevation (a superelevation tipped away from the center of the curve). We therefore ran the calculation at equilibrium, (since these curves are also below the limits of UPRR ES #0020D), and came up with a superelevation of ¼". It therefore appears reasonable to use no superelevation, which is between equilibrium and 1" unbalanced. We used the maximum superelevation calculated at equilibrium and used the preferred runout rate in UPRR ES #0019A for 60 MPH to obtain 20' spirals. This spiral length allows us to fit these curves between this subject crossing and the North Avenue crossing as discussed in comment #3. | Transition needs to be to 20' across the bridge. Move the PI's away from the bridge. To allow for greater track centers throughout the project. Up to a 1.5 degree curve could be used here if needed. Curves should maintain 100' length min., have 3/4" superelevation and 33' spirals min. | Per verbal conversation between John Venice of UPRR and Greg Baer of WisDOT as to whether we use 20' track centers as in this comment #22, or 15' track centers as in comment #1, UPRR has confirmed using 15' track centers in conformance with comment #1.
23 |  | Closed | [6 empty] | Need to use UPRR linestyles to show extents of track shifts, removal etc. Tracks can be shifted to the 13' clearance point. See Exhibit 1 (Exhibits Tab) | Provided in this 60% submission.
24 | PRE_5 | Closed | [6 empty] | What is the temp at-grade crossing for? Will need to identify more details (Length, type etc). | To access the east side of the tracks north and south of the crossing, see plans for details.
25 | PRE_5 | Closed | [6 empty] | Please provide more details on the temp access gate. | Provided in this 60% submission, (as a standard detail sheet that's been used on all UPRR projects).
26 | PRE_5 | Closed | [6 empty] | What is the blue line on the bottom right corner of sheet PRE_5 reperesenting? | It is "temporary shoring railroad" to construct wall R-40-622. We will note to SEE STRUCTURE PLANS in this 60% submission, (it will be discussed and paid for on the R-40-622 plan set).
27 | All P&P sheets | Closed | [6 empty] | The shoofly will impact several utilities. Plans should indicate how this will be handeled. | Utilties will be relocated where impacted by shoofly before start of construction.
28 |  | Closed | [6 empty] | Please submit title sheet. Title sheet needs to display UPRR Subdivision, MP limits, City, State, project description & submittal % | Provided in this 60% submission. | Title sheet included. Some information should be moved to General Sheets. See Comment #33.
29 |  | Open | [6 empty] | Please incorperate UPRR General Notes into plans. Notes can be found within the reference files available on our FTP site (See tab in this workbook for more information) | Provided in this 60% submission. (UPRR general notes added as a 2nd sheet to amplify project-wide general notes). | UPRR General Notes not found in the track plan submittal. See Comment #33. | We will provide. FTP site is password protected please provide a contact person and/or password for access. | User name and password for FTP site is provided "FTP Site Information" tab below. | OK. | -
30 | 8-10 | Closed | [6 empty] | Show retaining wall removal on final plan sheets. | Provided in this 60% submission.
31 | All P&P sheets | Closed | [6 empty] | Please dimension UPRR ROW on each sheet and wherever the ROW changes from Mainline track 1. | Provided in this 60% submission.
32 | 5-10 | Closed | [6 empty] | Please show drainage structures on profiles | Provided in this 60% submission. | exist. drainage structures shown.
33 | General Sheets | Open | [8 empty] | Incorporate UPRR's General sheets, including Abbreviations & Legends, General Notes/Project Contacts, etc. Sheet files & sample plans are available at UPRR's ftp site (see tab below for instructions). John Venice can provide UPRR contact information for this project. | We will provide. (UPRR general notes added as a 2nd sheet to amplify project-wide general notes). FTP site is password protected please provide a contact person and/or password for access. | User name and password for FTP site is provided "FTP Site Information" tab below. | OK. | - | Complete in this submittal. Please confirm this is shown correctly.
34 | General Sheets | Open | [8 empty] | Include note: "UPRR General Conditions and Specifications will be followed except where "xxxx" Conditions and Specifications exceed." | We will provide ("xxxx" will read "Wisconsin Department of Transportation"). |  |  | - | Complete in this submittal. Please confirm this is shown correctly.
35 | General Sheets | Open | [8 empty] | Include a quantity summary table separated by UPRR and Contractor. Table is to summarize work responsibility for each item. | Disagree: This information is redundant; it is shown clearly on the construction phasing sheets and details. It could also be confusing since all materials (except for the planks and geofabric at the temporary grade crossing) will be provided by the contractor, with the UPRR performing the track shifts only. | No summary is currently provided. Quantity summary is required for review on next submittal. UPRR will use this information to eventually produce a Materials and Force Estimate. | We will notate the quantity of material to be installed by UPRR (contractor will purchase and deliver to site) in a separate document for the forcework estimate if needed. | Ok | --
36 | General Sheets | Open | [8 empty] | Plans need to indicate who will be providing materials for shoofly and mainline construction (UPRR vs. Contractor/Agency). | The specifications indicate that all materials (except for the planks and geofabric at the temporary grade crossing) will be provided by the contractor. We will add a note to the UPRR general notes to that effect. | UPRR will discuss materials during 25% site review. | OK. | - | --
37 | All Sheets | Open | [8 empty] | Modify Title Block to include UPRR Subdivision, MP Limits, City, State and Project Description - all sheets. | We will add on top of our regular title block, a block that states "MP 91, MILWAUKEE SUBDIVISION, WAUWATOSA, MILWAUKEE COUNTY, WISCONSIN, IH41/USH 45 CROSSING" to all UPRR-related sheets. | Verify proper UPRR Mile Post limits as MP 91 falls outside the project limits (J. Venice can assist). | We will amend our added title block noted in 12/22/2016 response to indicate MP 92 in the next plan submittal. | Ok | Complete in this submittal. Please confirm this is shown correctly.
38 | All Sheets | Open | [8 empty] | Label proposed shoofly tracks as "Shoofly 1" and "Shoofly 2". Label proposed ML tracks as "ML1" and "ML2" | Disagree: Consistent with previous UPRR comments on both track and structure plans, and with a recent UPRR approved, WisDOT-let, two UPRR bridge replacements project located 2 miles south on this line, we will label the shoofly and proposed tracks as "Temporary West Mainline Track (No. 1)", "Temporary East Mainline Track (No. 2)", and "West Mainline Track (No. 1)", "East Mainline Track (No. 2)", respectively. |  |  | Shoofly track names ok. Please label Mainline tracks as Mainline 1 (West Track) and Mainline 2 (East Track) in order to avoid confusion. | Complete in this submittal. Please confirm this is shown correctly.
39 | Plan and Profile, Phasing Plans | Open | [8 empty] | Remove the black lines labelled as "13' Clear Zone". Retain 13' clearance point callouts. | We will remove. |  |  | - | Complete in this submittal. Please confirm this is shown correctly.
40 | Plan and Profile | Open | [8 empty] | Several horizontal curve geometry point annotations (TS,SC,CS,ST) are difficult to read/cluttered. Place annotations for Shoofly 1 and ML1 west of the tracks and annotations for Shoofly 2 and ML2 east of the tracks. | We will adjust. |  |  | - | Complete in this submittal. Please confirm this is shown correctly.
41 | Plan and Profile | Open | [8 empty] | Include horizontal curve data near corresponding curve on plan/profile sheets. Include degree of curve, length of curve, superelevation and spiral length. See sample plan/profile sheet in "Exhibits" tab. | We will provide. |  |  | - | Curve data shown on alignment plan. Will show on plan & profile sheets in future submittal.
42 | Plan and Profile | Open | [8 empty] | Include construction notes for each item per UPRR's "Public Project Guidelines" (available at web site shown at top of this sheet). Also refer to sample plan/profile sheet in "Exhibits" tab. Use box/leader format with text boxes shaded gray for Contractor items and no shading for UPRR items. | We will include construction notes as requested, but we will not shade boxes since it is outside WisDOT CADD standards. | If shading cannot be provided, construction notes must indicate "By Contractor" or "By UPRR". | OK. | - | Complete in this submittal. Please confirm this is shown correctly.
43 | Plan and Profile | Open | [8 empty] | Provide construction notes and Sta.'s for proposed transition rail installations. Reference the appropriate UPRR Std. Dwg. (0947B for 136# to 115#) | We will provide the construction notes and stations. The appropriate UPRR Std. Dwg. is referenced in the "Construct 136lb ISHH CWR on Wood Ties" special provision pay item included in the previous submittal. |  |  | - | --
44 | Plan and Profile | Open | [8 empty] | Show cut/fill lines per UPRR standard Abbreviations and Legend. | Disagree. We will not provide cut and fill lines as this is outside WisDOT CADD Standards. Cut and fill limits can be seen on the cross sections. | Cut/ fill lines on plan view helps determine grading impacts. This is a requirement for UPRR projects. Linestyle is available within the cad files on the UPRR FTP site. | OK. | - | Complete in this submittal. Please confirm this is shown correctly.
45 | Plan and Profile | Open | [8 empty] | Include timetable direction with timetable stations on sides of plan/profile sheets. | We will provide. |  |  | - | Complete in this submittal. Please confirm this is shown correctly.
46 | Profiles | Open | [8 empty] | Show existing/proposed drainage structures and utility crossings on all profile sheets. | Partially agree. Per WisDOT CADD Standards, proposed and existing crossings will be shown on the plan view only. | Per UPRR's "Public Project Guidelines", this information is required on the profiles. | OK. | - | Shown on plan view. We will collect further existing data and add to the profiles
47 | PRE_20 | Open | [8 empty] | Per grades shown, V/L value for Shoofly 1 vertical curve is 0.14. Max V/L for sag curves is 0.6. | Per closed comment #4, this condition was previously approved by UPRR at the 30% submittal phase. (The actual V/L curve value is 0.10 and will be added to the plans.) | Exception for temporary condition approved. Per Arema, proposed V/L is adequate for current timetable speeds. | OK. | - | <This comment appears to be closed.>
48 | PRE_20, PRE_21 | Open | [8 empty] | Temporary crossings - Graphically show the crossings at the tracks and include construction notes indicating quantity, material, etc. Timber crossing should conform to UPRR Std. Dwg. 0301H. Note this on sheet PRE_8 also. | We will add the note "Construct 30 TF of Cross Panels per UPRR Std. Dwg. 0301H (By UPRR)", (noted on sheets PRE_8, 20 and 21). |  |  | Refer to UPRR Standard drawings for crossing lengths. Wood crossings are available in 8' 1/4" lengths. Crossing can be called out as a "32' Timber crossing". Also note that crossing type will need to be reviewed at 25% walk through by service unit and construction personell. | We will provide in submittal after walkthrough.
49 | PRE_21 | Open | [8 empty] | Max V/L for sag curves is 0.6. | Per closed comment #4, this condition was previously approved by UPRR at the 30% submittal phase. | Exception for temporary condition approved. Per Arema, proposed V/L is adequate for current timetable speeds. | OK. | - | <This comment appears to be closed.>
50 | PRE_22 | Open | [8 empty] | Verify T/R grades shown on profile for ML1 near STA. 24+00 and 25+00. Revise vertical geometry to transition into existing T/R grade, removing the PI shown at Sta. 24+44.62. | The proposed vertical geometry as shown does tie-in to the existing T/R grade of 0.40%. The PVI is shown correctly and begins at the end of the tie-in grade. No change required to the proposed vertical geometry. | A vertical curve is needed to transition from the existing T/R grade (0.51%) to the proposed T/R grade (0.40%). | The tie-in is at 0.40%. | Please explain. The label shows .51%. Are you tying into a curve? If so we will need to show the revised vertical curve and ensure that it meets UPRR Standards. This comment applies to all tie in locations. | We are not tying into a curve. The 0.51% is extraneous data beyond the project from localized and inconsistent survey readings. The label will be revised 0.40% to better reflect the proposed condition, which is a smooth transition to existing grade.
51 | PRE_20, PRE_23 | Open | [8 empty] | Remove reference to UPRR's Industrial Track Specifications. References to UPRR Industrial Track Specifications need to be removed from all project documents and specifications. | We will provide. |  |  | - | Complete in this submittal. Please confirm this is shown correctly.
52 | PRE_23 | Open | [8 empty] | Curve "RDW1" - Provide minimum 100' horizontal curve length | With the removal of the previously directed spirals in comment #22, as directed in comment #53, 100' minimum horizontal curve length will be provided. |  |  | - | Complete in this submittal. Please confirm this is shown correctly.
53 | PRE_23 - PRE_25 | Open | [8 empty] | Spirals not needed on proposed ML1 horizontal curves. | We will provide. |  |  | Please note that this only applies to curves that are 10 minutes or less. | Complete in this submittal. Please confirm this is shown correctly.
54 | PRE_24 | Open | [8 empty] | Verify a minimum of 100 ft. tangent will be provided on the proposed ML tracks beyond each abutment. | We have verified that 100' minimum tangents are provided for the ML tracks beyond each abutment. |  |  | - | Complete in this submittal. Please confirm this is shown correctly.
55 | PRE_23, PRE_24 | Open | [8 empty] | UPRR does not want to own or maintain new retaining walls. Suggest using 2:1 slopes to tie into existing slopes and keeping proposed T/R profile as close to existing as possible. | The retaining wall is necessary due to the extreme close proximity of the adjacent business buildings, access roads, and parking lots. Purchasing this land would negatively affect the social and economic value of the community. The retaining wall is required to bring existing steep slopes and track spacing up to current standards - the changes in profile resulting from the new construction do not affect the decision to add a retaining wall. | Retaining walls are not required for the existing conditions. UPRR does not agree to assume ownership and maintainence of walls as part of this project. Walls may be located outside of UPRR ROW and maintained by an agency other than UPRR if they are required. | See separate request for variance letter. | It is understood that a wall may need to be constructed. However if the wall must be located on UPRR property we ask for the following: See comments 67-71 for individual comments. | See responses to comments 67-71 below.
56 | PRE_24 | Open | [8 empty] | Proposed ML: T/R profile indicates the track will be raised up to 1.37 ft. Track raises are not acceptable by UPRR. If a raise in the track profile is required due to the proposed structure depth, roadway profile, etc. additional information and justification for the track raise must be submitted to UPRR for review. | The existing mainline tracks will be removed and the track beds will be reconstructed by the contractor with standard 12” ballast & subballast depth per the typical sections. Since the proposed track raise occurs through an existing sag curve, any raise of existing track required by surfacing will be done at the tie-in’s where the raise is minimized. The current proposed track design has already been investigated and designed to minimize the proposed UPRR profile raise. The interstate below restricts the lowering of the proposed UPRR profile closer to existing conditions. The interstate profile is in a sag at this location. The interstate sag vertical curve is designed to minimum standards to achieve the lowest possible track profile. Additionally, the interstate profile is restricted by the close proximity of the interstate bridge located 550-ft to the east, which spans over Mayfair Road. This interstate bridge over Mayfair Road has been designed to a minimum girder size and minimum vertical clearance, which again translates into the lowest possible track profile at the UPRR bridge. Once the temporary tracks are in service, the existing mainline tracks will be removed to allow the subgrade & subballast to be reconstructed per the provided design. | Comment 55 needs to be addressed before UPRR can further discuss a grade raise. | See separate request for variance letter. | Please share documentation regarding the interstate design restrictions for UPRR review so that we can understand the constraints. | Variance letter documentation will be shared with UPRR reviewers for further review and discussion
57 | PRE_25 | Open | [8 empty] | Verify T/R grades shown on profile for ML1 and ML2 near STA. 24+00 and 25+00. Revise vertical geometry to transition into existing T/R grade, removing the PI's. | The proposed vertical geometry as shown does tie-in to the existing T/R instantaneous grades. No change is required to the proposed vertical geometry. | A vertical curve is needed to transition from the existing T/R grade to the proposed T/R grade. | The tie-in is at 0.40%. | Please explain. The label shows .51%. Are you tying into a curve? If so we will need to show the revised vertical curve and ensure that it meets UPRR Standards. This comment applies to all tie in locations. | We are not tying into a curve. The 0.51% is extraneous data beyond the project from localized and inconsistent survey readings. The label will be revised 0.40% to better reflect the proposed condition, which is a smooth transition to existing grade.
58 | Cross Sections | Open | [8 empty] | Cross sections need to be formatted per UPRR's "Public Project Guidelines". See sample cross sections in "Exhibits" tab. Cross Sections must include existing/proposed T/R, grade breaks and ditch flowline elevations. Cross sections were not reviewed with this submittal. Will review when the requested information has been added. | Disagree. Formatting will remain per WisDOT CADD standards. | Format can remain, however line styles/colors need to be consistent with UPRR's "Public Project Guidelines". Cross sections must include existing/proposed T/R elevations, grade breaks and ditch flowline elevations. | We will provide in the next plan submittal. | Ok | Complete in this submittal. Please confirm this is shown correctly.
59 | Cross Sections | Open | [8 empty] | Consider reducing width of cross section windows to include more cross sections per sheet. | Cross section width conforms to WisDOT plan standards. | see Comment #58 | OK. | - | <This comment appears to be closed.>
60 | Phasing Plans | Open | [8 empty] | Format Phasing Plan consistent with the example included in the "Exhibits" tab. Much of the background information can be removed from the current phasing plans to simplify the drawings and reduce the number of sheets. | We will provide. |  |  | - | Complete in this submittal. Please confirm this is shown correctly.
61 | Phasing Plans | Open | [8 empty] | Format phasing notes per example in "Exhibits" tab, using shaded boxes for Contractor items and no shading for UPRR items (similar to construction note format to be used on plan/profile sheets). | Disagree. Formatting will remain per WisDOT CADD standards. | If shading cannot be provided, phasing notes must indicate "By Contractor" or "By UPRR". | OK. | - | Complete in this submittal. Please confirm this is shown correctly.
62 | Phasing Plans | Open | [8 empty] | Show proposed structure in green and removed structure in blue in phases where this work takes place. | We will provide |  |  | - | Complete in this submittal. Please confirm this is shown correctly.
63 | Phasing Plans | Open | [8 empty] | Show track to be shifted in orange-dashed linestyle and proposed alignment in green, similar to plan/profile. | We will provide. |  |  | - | Complete in this submittal. Please confirm this is shown correctly.
64 | Phasing Plans | Open | [8 empty] | Provide additional details in phasing notes, specifically the track shift/cutover steps. See sample phasing plan. | We will provide. |  |  | - | Complete in this submittal. Please confirm this is shown correctly.
65 |  | Open | [10 empty] | Please review UPRR's "Public Projects Guidelines" and "Public Projects Checklist", available at the web address above. Provide a completed checklist with next plan submittal. | We will provide in the next plan submittal. | - | Public Project Checklist will be submitted with 25% submittal
66 |  | Open | [10 empty] | Per UPRR design criteria, the plan are being reviewed at a 25% level. Please refer to the "Public Project Checklist" for items that need to be included/approved at each level of design. Please re-submit the plans, labelled as "25%". | Disagree. Project is submitted for 60% approval and has been acknowledged by both UPRR and WisDOT as such at the OCR hearing. | Union Pacific Engineering has a defined process for progressing all engineering projects. This is explained in the guidelines document and the checklist both available on our website. When plans are submitted indicating a percentage other than that defined by our documentation it causes confusion for UPRR employees especially those in other departments. The intention of this comment is to ensure a smooth progression through the design and approval process at UPRR. | Plans labeled as 25%
67 | Retaining Wall | Open | [12 empty] | Reduce the shoulder on the East side of the tracks to 13.5’. As we mentioned in a previous correspondence it is not likely that UPRR would shift Mainline 2 further to the East. Based on the proposed track geometry we would want to shift Mainline 1 further to the West in order to minimize the number of curves in the mainline tracks. Could the subgrade and bridge be extended to the West instead? | The subgrade and bridge cannot be moved to the west due to design restricitons including shoofly structure and track design limitations.
68 | Retaining Wall | Open | [12 empty] | Once the shoulder is reduced from 18.5’ to 13.5’ the height and length of the wall required will be reduced. There is a stretch of property where the proposed 2:1 (or greater) slope could daylight to the existing toe of slope. UPRR proposes that a slope easement be granted at these locations instead of a wall therefore reducing construction and maintenance costs. | The wall was redesigned and moved 1-FT off the right of way line, accomodated 13.5' shoulder width and 2:1 slopes. This reduced the wall length by 200-FT and reduced the wall height to the extend possible.
69 | Retaining Wall | Open | [12 empty] | Please see the provided cross sections to depict the proposed changes to the East side of the tracks. | Changes made as noted in comment 68.
70 | Retaining Wall | Open | [12 empty] | Move the wall to the furthest extents of the UPRR ROW. Typically when retaining walls are required they are located .5’ to 1’ from the ROW line. Generally it appears that this will again reduce the height of the retain wall, improve the conditions for the adjacent land owner and eliminate a potentially unsightly wall from public view. | Complete in this submittal. Please confirm this is shown correctly.
71 | Retaining Wall | Open | [12 empty] | UPRR requests that the DOT pay UPRR up front for maintenance and inspection of the proposed retaining wall. This should be discussed with John Venice and Chris Keckeisen. | Discussions and agreements are still ongoing between UPRR and WisDOT's Rails & Harbors Section.
72 |  | Open
73 |  | Open
74 |  | Open
75 |  | Open
76 |  | Open
77 |  | Open
78 |  | Open
79 |  | Open
80 |  | Open
81 |  | Open
82 |  | Open
83 |  | Open
84 |  | Open
85 |  | Open
86 |  | Open
87 |  | Open
88 |  | Open
89 |  | Open
90 |  | Open
91 |  | Open
92 |  | Open
93 |  | Open
94 |  | Open
95 |  | Open
96 |  | Open
97 |  | Open
98 |  | Open
99 |  | Open
100 |  | Open
101 |  | Open
102 |  | Open
103 |  | Open
104 |  | Open
105 |  | Open
106 |  | Open
107 |  | Open
108 |  | Open
109 |  | Open
110 |  | Open
111 |  | Open
112 |  | Open
113 |  | Open
114 |  | Open
115 |  | Open
116 |  | Open
117 |  | Open
118 |  | Open
119 |  | Open
120 |  | Open
121 |  | Open
122 |  | Open
123 |  | Open
124 |  | Open
125 |  | Open
126 |  | Open
127 |  | Open
128 |  | Open
129 |  | Open
130 |  | Open
131 |  | Open
132 |  | Open
133 |  | Open
134 |  | Open
135 |  | Open
136 |  | Open
137 |  | Open
138 |  | Open
139 |  | Open
140 |  | Open
141 |  | Open
142 |  | Open
143 |  | Open
144 |  | Open
145 |  | Open
146 |  | Open
147 |  | Open
148 |  | Open
149 |  | Open
150 |  | Open
151 |  | Open
152 |  | Open
153 |  | Open
154 |  | Open
155 |  | Open
156 |  | Open
157 |  | Open
158 |  | Open
159 |  | Open
160 |  | Open
161 |  | Open
162 |  | Open
163 |  | Open
164 |  | Open
165 |  | Open
166 |  | Open
167 |  | Open
168 |  | Open
169 |  | Open
170 |  | Open
171 |  | Open
172 |  | Open
173 |  | Open
174 |  | Open
175 |  | Open
176 |  | Open
177 |  | Open
178 |  | Open
179 |  | Open
180 |  | Open
181 |  | Open
182 |  | Open
183 |  | Open
184 |  | Open
185 |  | Open
186 |  | Open
187 |  | Open
188 |  | Open
189 |  | Open
190 |  | Open
191 |  | Open
192 |  | Open
193 |  | Open
194 |  | Open
195 |  | Open
196 |  | Open
197 |  | Open
198 |  | Open
199 |  | Open
200 |  | Open
201 |  | Open
202 |  | Open
203 |  | Open
204 |  | Open
205 |  | Open
206 |  | Open
207 |  | Open
208 |  | Open
209 |  | Open
210 |  | Open
211 |  | Open
212 |  | Open
213 |  | Open
214 |  | Open

## Exhibits
UPRR Abbreviations and Legend Sheet
Sample Plan/Profile
Sample Cross Sections
Sample Phasing Plan

## FTP Site Information
The login information:
ftp://ftp.uprr.com/
username: dftp013
password: w7m4v6x3
1. Connect to website using windows explorer.
2. Right click in windows explorer you can "Login as". Then use the username and password.
3. Browse to the “ENGR” -> “Cad Configuration Files” directory and download the “UPRR Standards.zip” file.