## Slide 1
AASHTO COBS T-19 Annual Meeting
Montgomery, Alabama
June 24, 2019
Building Information Modeling (BIM) for Bridges and Structures: Iowa DOT Demonstration Project
Ahmad Abu-Hawash
Chief Structural Engineer

## Slide 2
OUTLINES
Iowa DOT I-80 / I-380 Pilot Project
  Project Overview
  Lessons Learned
Notes: I will give an overview the I-80/I-380 demonstration project and go over Lessons Learned
  Highlight the demonstration project
  Talk about the software used and
  Show how we incorporated the BIM model into the construction contract

## Slide 3
1
2
3
INITIAL GOALS
DEVELOP BIM MODEL
As complete as possible
EVALUATE BENTLEY SOFTWARE
OpenBridge Modeler
ProStructures
Navigator Connect
ENCOURAGE CONTRACTOR USE
PROJECT OVERVIEW
Notes: We worked with the Design Team at HDR to:
Develop BIM model as complete as possible with the given software
2. Evaluate three Bentley products: OBM, PS, and Navigator CONNECT
  We wanted to identify advantages and disadvantages of each
3. Encourage contractor use
  Wanted them to become more familiar with the software
  We also wanted them to provide feedback for future model improvements

## Slide 4
PROJECT OVERVIEW
3 Complex Curved Steel Plate Girder Bridges
Total length = 4,200 ft.
Diverging gore
Discontinuous girders
Complex superelevation at gore
Inspection walkways
Aesthetic piers & abutments
Notes: The project is located at the I-380/I-80 interchange in Eastern Iowa
It includes three curved steel plate girder bridges with a total length of 4200 ft
  The first is a 5 span bridge with a diverging gore
  The second is a short 3 span bridge
  And the last bridge is a 13 span, 3 unit curved bridge

## Slide 5
Defines primary bridge elements using horizontal & vertical geometry.
BENTLEY SOFTWARE
Bentley’s BIM Bridge Solution
Used to add elements not created by OBM and improve LOD.
Multi-platform viewing tool. Not used for element creation.
Notes: Early on in the process Bentley recommended that we use these pieces of software
The first is OpenBridge modeler:
  It was used to define the primary elements using horizontal and vertical geometry.
  It includes elements such as the bridge deck, barriers, girders, cross-frames, and some substructure elements
Because the level of detail in OBM is fairly low, ProStructures was used to add more detailed elements to the model
  All of the modeling was completed using these two pieces of software
The last piece of software is Navigator CONNECT It was not actually used to create any elements, but for multi-platform viewing on laptops and tablets in the field

## Slide 6
Combined OBM
& ProStructures
ProStructures
(PS)
OpenBridge
Modeler
(OBM)
MODEL DEVELOPMENT
Notes: The intent of this slide is to graphically show what each piece of the software produces.

## Slide 7
I-MODEL TRANSFORMER
Filter out unwanted info
Modify descriptions
Adjust software-generated data
MICROSTATION CONNECT
Add custom element info
Organize data into different categories
Link data to spreadsheets through Item Types Plus
MODEL DEVELOPMENT
Element Information
Notes: A couple of additional tools used in model development are I-Model Transformer and MicroStation Connect.
I-Model Transformer is used as a clean-up to …
MicroStation Connect is used as a customization tool to …

## Slide 8
PDF
Details not definable in BIM
Maintained traditional sheet format
SPREADSHEETS
Top of deck elevations
Camber & deflection
WORD DOCUMENTS & WEBSITE LINKS
Specifications
Special provisions
MODEL DEVELOPMENT
Linked Information
Notes: Because the model could not provide all the information, we needed a way to supplement the model.
The solution was element information dialog box with links.
This brings the model up to par with the traditional 2D plan sets.
The supplemental information were provided in the form of PDFs, Spreadsheets, Word documents and website links.

## Slide 9
Geotechnical
Roadway
Drainage
Utilities
Lighting
Mechanical
MODEL DEVELOPMENT
Interdisciplinary Coordination
Notes: One of the major benefits of BIM is the ability to incorporate other disciplines, which allows us to address conflicts during design.

## Slide 10
MODEL DEVELOPMENT
Process
Notes: This is a summary of the process used to create the model.

## Slide 11
BIM Deliverable
Provide BIM Model for Information
Hybrid Model
  Reduce Contractor Risk
  Promote BIM usage
Gather Information on BIM Usage During construction
Design, Bid, Build Contract
Notes: Being this was our first BIM project we had many discussions on how we deploy the model.
Initially, we thought about providing BIM models for information only. And include traditional 2D plan sets.
After talking with our local contractors (AGC), they suggested we require the use of the model and not provide 2D plan sets , if provided for information only, would be very limited.
AS a compromise we decided on a hybrid approach …..

## Slide 12
SPECIAL PROVISION DEVELOPED FOR DIGITAL CONTRACT FILES
BIM Deliverable
Special Provision
  List of files and access instruction
  Recommended software
  Information hierarchy
  LOD table for each element type
  List of known deficiencies
  Appendix with seal and list of covered digital files
  Referenced files
Notes: The use of the BIM model was covered in an SP that included:
A list of files and instruction to access
Recommended software
Information hierarchy
LOD table for each element type
List of known deficiencies within the model
Appendix with seal and list of covered digital files
Referenced files, such as borings and ground surfaces

## Slide 13
Used by contractors for bidding
Project Letting
Bentley View
ADVANTAGES
Free download
All info required for bidding is accessible
Visualization tools similar to MicroStation & ProStructures
Read-only i-model
ISSUES
Limited functionality during construction
No mobile application
Notes: Bentley View was made available to all bidders during the advertisement period.
The advantages and issues are listed to the left.
With this being a pilot project, we did not want to require the contractors to purchase expensive software licenses, and this product was free and allowed multiple contractor to bid on the project.

## Slide 14
Contractors & subs unfamiliar with software
HDR provided multiple training sessions to:
  Office of Bridges & Structures
  District
Contractors
Recorded hour-long training video
using the Ramp B model
Free
Bentley support
Project Letting
Training
Notes: With the contractors and subs being unfamiliar with the software we focused on providing training before and after the letting.
We did not want any contractors or sub being prevented from bidding
HDR provided training to both DOT staff and contractors.
Recorded an hour-long training video and posted it online
Also, Bentley agreed to provide free support.

## Slide 15
PROJECT AWARDED
APPARENT LOW BID
UNDER ENGINEERS ESTIMATE
CONTRACTOR ATTENDED ALL AGC MEETINGS
Project Letting

## Slide 16
OpenBridge Modeler OBM
Elements cannot be customized
Simple native elements (i.e. piers & abutments)
Limited quantities & no parts list
ProStructures PS
No civil geometry
Buildings-based program
Needs more bridge-specific tools
Time consuming
LESSONS LEARNED
ISSUES
Model Development
Notes: Early on in my presentation I stated that one of the objectives of this demonstration project was to evaluate the capabilities of available software.
So in the next three slides I will list the issues encountered by the designers but I will not have enough time to discuss.
Please keep in mind, these were issues at that point in time and may have been addressed by now.
OBM: it cannot be customized, limited to simple native elements, and with limited quantities and parts list.
PS: it is a building-based program, with no civil geometry, and it needs more bridge-specific tools.

## Slide 17
Native Element Information
Significant amount of software generated element information is irrelevant
  Difficult to locate specific items
  Repetitive information
  Increases checking process
Need for customized element information
  Bid item numbers
  Embedment depths
  Batter angles
  Etc.
LESSONS LEARNED
ISSUES
Model Development
Notes: The issues listed on this slide was the reason to use I-Model Transformer and MicroStation Connect tools to cleanup and customize the model, respectively.

## Slide 18
Current software capabilities do not allow all information to be obtained from the model
Software lacks features to allow easy access to available information such as:
  Shear connector spacing
  Horizontal dimensions
  Span Lengths
  Girder layout
Details needed to help define:
  Welding Details
  Vendor supplied items (i.e. bearings, expansion joints)
Additional details needed:
  Specifications
  Notes
LESSONS LEARNED
ISSUES
Notes: I mentioned earlier that the software used to create the model did not provide all the information needed.
The solution was to embed links to data files to supplement the model.

## Slide 19
Post Letting Feedback from contractors
  Have to invest in software in order to take full advantage of the model
  Having difficulties with generating prints for specific views
  Lack of dimensions in the model
  Helping suppliers obtain information from the model
  Getting buy-in from senior field staff
LESSONS LEARNED
ISSUES
Notes: Another objective of the demonstration project was to get feedback from contractors.
Here is some of their concerns:
The free software (Bentley View) will give you access to the model but you have to buy additional software in order to take full advantage of the model
They are having difficulties with generating prints for specific views
There is lack of dimensions in the model
The prime contractor is helping suppliers obtain information from the model
It is tough getting buy-in from senior field staff
Construction is just getting started so we expect much more feedback.

## Slide 20
CONTACT INFORMATION
Ahmad Abu-Hawash,
Chief Structural Engineer, Iowa DOT
Email: Ahmad.Abu-Hawash@iowadot.us Phone: 515-239-1393
THANK YOU FOR YOUR TIME AND ATTENTION