Date:  March 18th, 2016

Project Information: 	 ID 8221-01/8110-02-70/71/72/75/73

St Croix Crossing Bridge and Wisconsin Approach

Contract Dates Superstructure:

Open to Traffic – Fall 2017

Substantial Complete Date – TBD

Construction Completion Date – TBD

Milestones:

Mooring Cell Removals (except northern most) – TBD

Falsework and surface finishes – TBD

Dock wall & northern most mooring cell (camera) removal – TBD

Construction Dates WI Approach:

8110-02-71 – Grading, aggregate base, B-55-225 - COMPLETE

8110-02-72 – Grading from the STH 35 IC to the Eastern Limits - COMPLETE

8110-02-75 – Final paving from the Main River Bridge to the Eastern Limits

Construction start date-late spring 2016, 	Substantial Completion Date-October 3rd, 2016

(Includes requirement for contractor to complete paving next to bridge in 2017.)

8110-02-73 – Wisconsin Loop Trail Construction

Likely construction start date-Spring 2018, 	Likely substantial Completion Date-Fall 2018

Work completed to date:

- Pier Work

13W

13E

13E

  - Columns – COMPLETE

- Abutment Work

  - 82045:

    - West:  idle (backwalls to be poured soon?)

    - East:  footing and body complete (idle until December 2016)

  - 82047:  footing and body complete (idle until May 2017)

  - 82048:  complete

- Crossbeams – COMPLETE

- Pier Table – River – COMPLETE

- Towers – COMPLETE

- CIP Falsework

  - WB gore area:  COMPLETE

Span 7 decking & forming

Span 5 walls & bottom slab

3/7/2016

  - EB gore area (spans 5 thru 7):

    - Slab pour: 5A of 8 complete

    - Diaphragms:

      - Pier 4E & 5E:  complete

      - Pier 6E:  installing reinforcement

    - Web Walls:  3 of 11 complete

  - 82048 Spans 3&4:  Piling installation to begin? (CMP indicates March 23rd, but activity is not shown in most recent 3-week look ahead schedule)

3/7/2016

82047 – Span 1

  - 82047 Span 1:  falsework and decking complete, installing end diaphragm reinforcement

- Precast yards

  - Onsite:

    - Segments cast:  258 of 342  (4 more since last status report)

    - Completed cantilevers: 1E, 1W, 2E, 2W, 3E, 47-2, 47-3 (188 segments)

    - Back-spans complete:  AE, AW, 47-1 (32 segments)

    - Cantilevers/back-spans in-progress:

      - 3W-U1:2

      - 47-4

    - 3 of 4 precast diaphragms complete

  - Grey Cloud:

    - Segments cast:  490 of 650 (38 more since last status report)

    - Completed cantilevers: 8 & 9 (232 segments)

    - Back-spans complete:  7, W13-U (35 segments)

    - Cantilevers/back-spans in-progress:

      - E10-1D:16, E10-1U:16, W10-1D:15, W10-1U:14

      - E11-1D:16, E11-1U:20, W11-1D:15, W11-1U:7

      - E12-1D:16, E12-1U:24, W12-1D:24, W12-1U:24

      - E13-1U:15, W13-1D

- Precast Approach : Unit 1E & 1W

47-4

3W

4W

4W

3/7/2016

  - Pier tables

    - Stage III pour:  3W  (complete)

    - Stage II pour:  4W

    - Stage I pour: 47-Pier 4

  - Segments

    - Erected:  146 of 341

    - Completed cantilevers:  1E, 1W, 2E, 2W (68 segments)

    - Back-spans complete:  AE, AW (64 segments)

    - Cantilevers in-progress:

      - 47 Bridge Pier 2: 2-U1:4, 2-D1:4

      - 47 Bridge Pier 3: 3-U1, 3-D1

      - Pier 3E:  3E-U1, 3E-D1

- River Segments

  - Erected:  140 of 650

  - Cantilevers in-progress:

    - Pier 8: E8-1D:17, E8-1U:17, W8-1D:17, W8-1U:17

    - Pier 9:  E9-1D:16, E9-1U:16, W9-1D:16, W9-1U:16

    - Pier 12:  E12-1D:2, E12-1U:2, W12-1D:2, W12-1U:2

Work scheduled for next few months (March thru end of May):

- Pier Footing/Column Work – COMPLETE

3/7/2016

Abutment Work

  - 82045 West – EB & WB: complete backwalls

- Trestle

  - Phase 2 complete

  - Rails for span 14 installed

  - Crane Pad complete

- Crossbeam – COMPLETE

- Segments – River (220 of 650 total)

  - Erect up to…

    - Pier 8:  21st segment

    - Pier 9:  19th segment

    - Pier 12:  13th segment

  - Wet cast 1U/1D joint

    - Piers 10 & 11

  - Start erecting:

    - Week of March 28th:  Piers 8, 9, 11, 12

    - Week of April 4th:  Pier 10

- Towers – COMPLETE

- Cast-In-Place:

  - 82045 EB Spans 5-7:

    - 7 of 8 bottom slab pours complete

    - 3 of 11 web wall pours complete

    - 2 of 6 top slab pours complete

  - 82048 Spans 3 & 4:  Span 3 falsework complete (per CPM work to start late-March)

  - 82047 Span 1:  bottom slab & end diaphragm complete

- Precast yards

  - Approach Casting Yard (298 of 342 total)

    - Assumes casting rate of about 4 segments per week.

  - Grey Cloud Casting Yard (570 of 650 total)

    - Pier 10:  cast additional 25 segments

    - Pier 11  cast additional 25 segments

    - Pier 12:  cast additional 11 segments

    - Pier 13:  cast 19 additional segments

    - Assumes casting rate of about 8 segments per week.

- Precast Approach : Unit 1E & 1W

  - Pier Table

    - Complete:

      - 4W

      - 47 Bridge Pier 4

  - Segments erected  (236 of 338)

    - Complete

      - 47  Bridge Pier 2: 14 segments

      - 47 Bridge Pier 3:  18 segments

      - Pier 3E:  32 segments

      - Pier 3W:  26 segments

RFI Status:

374 RFIs have been submitted to date.

Percent Contract Complete:  74.26%

Budget Status:

Original Contract Value		$332,455,810.90

Funds Encumbered to Date		$336,212,531.92

WisDOT portion of Superstructure		$143,894,235.69

Value of Work Certified to Date		$249,686,174.51

WisDOT portion		$106,680,176.79

Schedule Status:

- The Contractor submitted a schedule (LA-26BSU-1) on February 26th.

- The substantial completion date is shown as October 4th, 2017. (Negative 308 days float)

- The construction completion date is shown as April 18th, 2018.

- 26BSU-1 is a mitigated schedule.

8110-02-75:

3/7/2016

3/7/2016

Trierweiler Construction & Supply was awarded the project. Construction to begin in May or June, with tree clearing in April.