Date:  April 15th, 2016

Project Information: 	 ID 8221-01/8110-02-70/71/72/75/73

St Croix Crossing Bridge and Wisconsin Approach

Contract Dates Superstructure:

Open to Traffic – Fall 2017

Substantial Complete Date – TBD

Construction Completion Date – TBD

Milestones:

Mooring Cell Removals (except northern most) – TBD

Falsework and surface finishes – TBD

Dock wall & northern most mooring cell (camera) removal – TBD

Construction Dates WI Approach:

8110-02-71 – Grading, aggregate base, B-55-225 - COMPLETE

8110-02-72 – Grading from the STH 35 IC to the Eastern Limits - COMPLETE

8110-02-75 – Final paving from the Main River Bridge to the Eastern Limits

Construction start date-May 16th, Interim Completion Date-September 16th, 2016

(Includes requirement for contractor to complete paving next to bridge in 2017.)

8110-02-73 – Wisconsin Loop Trail Construction

Likely construction start date-Spring 2018, 	Likely substantial Completion Date-Fall 2018

Work completed to date:

- Pier Work – COMPLETE

- Abutment Work

  - 82045:

    - West:  idle (backwalls to be poured soon?)

    - East:  footing and body complete (idle until November 2016)

  - 82047:  footing and body complete (idle until May 2017)

  - 82048:  complete

- Crossbeams – COMPLETE

- Pier Table – River – COMPLETE

- Towers – COMPLETE

- CIP Falsework

Span 5 top slab forming

Diaphragm 6E

WB gore area – COMPLETE

82048 –

Phase 2

falsework

Span 7 rebar installation

4/9/2016

  - EB gore area (spans 5 thru 7):

    - Slab pour: 6B of 8 complete

    - Diaphragms:

      - Pier 4E & 5E:  complete

      - Pier 6E:  pour next week

      - Pier 7E:  installing reinforcement

      - Web Walls:  5 of 11 complete

  - 82048 Spans 3&4:  Falsework installation of span 3 is ongoing

82047 – Span 1

4/9/2016

  - 82047 Span 1:

    - Slab pour: 1 of 2 complete

    - Diaphragms:  Rebar installation at abutment is ongoing

- Precast yards

  - Onsite:

    - Segments cast:  268 of 342  (10 more since last status report)

    - Completed cantilevers: 1E, 1W, 2E, 2W, 3E, 47-2, 47-3 (188 segments)

    - Back-spans complete:  AE, AW, 47-1 (32 segments)

    - Cantilevers/back-spans in-progress:

      - 3W

      - 47-4

      - 4W

    - 3 of 4 precast diaphragms complete

  - Grey Cloud:

    - Segments cast:  525 of 650 (35 more since last status report)

    - Completed cantilevers: 8 & 9 (232 segments)

    - Back-spans complete:  7, W13-U/D (39 segments)

    - Cantilevers/back-spans in-progress:

      - E10-1D:16, E10-1U:19, W10-1D:16, W10-1U:15

      - E11-1D:16, E11-1U:24, W11-1D:17, W11-1U:13

      - E12-1D:24, E12-1U:24, W12-1D:24, W12-1U:24

      - E13-1U:22

- Precast Approach : Unit 1E & 1W

47-4

3W

4W

47-2

47-3

3W

47-4

3E

4W

4/9/2016

  - Pier tables

    - Stage III pour:  4W  (complete)

    - Stage II pour: 47-Pier 4

  - Segments

    - Erected:  150 of 341 (4 more since last status report)

    - Completed cantilevers:  1E, 1W, 2E, 2W (68 segments)

    - Back-spans complete:  AE, AW (64 segments)

    - Cantilevers in-progress:

      - 47 Bridge Pier 2: 2-U1:5, 2-D1:5

      - 47 Bridge Pier 3: 3-U1, 3-D1

      - Pier 3E:  3E-U1, 3E-D1

      - Pier 3W: 3W-U1, 3W-D1

- River Segments

Pier 8

Erected:  160 of 650 (20 more since last status report)

Pier 11

Pier 10

Pier 9

Pier 12

  - Cantilevers in-progress:

    - Pier 8: E8-1D:17, E8-1U:17, W8-1D:18, W8-1U:18

    - Pier 9:  E9-1D:18, E9-1U:18, W9-1D:17, W9-1U:17

    - Pier 10:  W10-1D, W10-1U

    - Pier 11:  W11-1D, W11-1U

    - Pier 12:  E12-1D:4, E12-1U:4, W12-1D:4, W12-1U:4

  - WI Crane Pad Installation – COMPLETE

Work scheduled for next few months (April thru end of June):

- Abutment Work

  - 82045 West – EB & WB: complete backwalls

- Trestle

  - Phase 2 complete

  - Rails for span 14 installed

- Segments – River (346 of 650 total)

  - There are 29 segments per cantilever

  - Erect up to…

    - Pier 8:  25th segment

Pier 10&11

Pier 10&11

Pier 9

Pier 9

    - Pier 9:  23rd segment

    - Pier 10:  8th segment

    - Pier 11:  8th segment

    - Pier 12:  17th segment

    - Pier 13:  (22 of 62 segments)

- Cast-In-Place:

  - 82045 EB Spans 5-7:

    - All bottom slab pours complete

    - 7 of 11 web wall pours complete

    - 4 of 6 top slab pours complete

  - 82048 Spans 3 & 4:  Span 3 falsework complete

  - 82047 Span 1:

    - All bottom slab pours complete

    - 2 of 3 diaphragms complete

- Precast yards

  - Approach Casting Yard (308 of 342 total)

    - Assumes casting rate of about 4 segments per week.

  - Grey Cloud Casting Yard (605 of 650 total)

    - Pier 10:  cast additional 30 segments

    - Pier 11  cast additional 30 segments

    - Pier 12:  cast additional 11 segments

    - Pier 13:  cast 9 additional segments

    - Assumes casting rate of about 8 segments per week.

- Precast Approach : Unit 1E & 1W

  - Pier Table Complete:  47 Bridge Pier 4

  - Segments erected  (244 of 342)

    - Complete

      - 47  Bridge Pier 2: 12 segments

      - 47 Bridge Pier 3:  18 segments

      - Pier 3E:  32 segments

      - Pier 3W:  32 segments

RFI Status:

382 RFIs have been submitted to date.

Percent Contract Complete:  76%

Budget Status:

Original Contract Value		$332,455,810.90

Funds Encumbered to Date		$336,212,531.92

WisDOT portion of Superstructure		$143,894,235.69

Value of Work Certified to Date		$256,813,531.94

WisDOT portion		$110,109,480.30

Schedule Status:

- The Contractor submitted a schedule (LA-27BSU-1) on April 4th.

- The substantial completion date is shown as September 20th, 2017. (Negative 294 days float)

- The construction completion date is shown as April 4th, 2018.

- 27BSU-1 is a mitigated schedule.

8110-02-75:

4/9/2016

4/9/2016

Tree Clearing Completed in March, Precon was Monday, April 11th, Construction to Start May 16th with Interim completion date of September 16th.