{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["STH 16"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"STH 16","index":0,"n_rows":7,"n_cols":7,"rows_kept":7,"cut":false,"hidden":false,"merged":[[0,0,0,6]]}
["Potential Utility Conflicts"]
["Station","Offset","Utility Company","Utility Type","Utility Location Description","WisDOT Construction Activity","Resolution"]
["Column1","Column2","Column3","Column4","Column5","Column6","Column7"]
["STA 797+39","40' RT","Alliant Energy ","Overhead Electric (Pole)","Running parallel with STH 16 EB","Adding fill adjacent to pole for guardrail grading"]
["STA 802+76","43' RT","Alliant Energy","Underground Gas","Running parallel with STH 16 EB","Replacing guardrail around Ostsego Road intersection at SW quandrant (new posts and rail)"]
["STA 1157+26 to STA 1157+65","33' LT to 46' RT","Alliant Energy/AT&T ","Overhead Electric/Overhead Communications","Crosses STH 16","Bridge replacement over the Crawfish River; reconstruct roadway with minor roadway profile raise at that location"]
["STA 1159+40 to STA 1159+43","27' LT to 33' LT","Alliant Energy","Underground Gas","Crosses STH 16","Reconstruct roadway"]