TC-180625023 MAN Hwy 61 Madison St Rebuild (2019)

PRJ00045490

Red comments are review comments on TDS facilities

Bold Red comments are from conference call with Brett Peterson of OTIE 01-23-18

Bold black text is field verification notes.

July 2018 Revision 02 Updates

Phase 1 is April-June, TDS items 1-9 April to May 1st time frame

Phase 2 is July, No TDS items

Phase 3A is August-November, TDS items 10-20 May to August time frame

Phase 3B is August-November, TDS items 21-34 May to August time frame

All work items by TDS carry a 1 week notice and 1 day completion.

Item 34 has been added, the poles identified prior as TDS from STA 41+60 L to STA 46+80 L, Sheet 79 and 80.  TDS has no attachment, with Charter still attached, pole removal falls to Charter as last utility on the poles.

POTENTIAL UTILITY CONFLICTS: Construction ID 1650-07-71,81 TDS Telecom – Communication Line

The utility conflicts listed below may not be all inclusive. It is the responsibility of each utility to verify these conflicts and identify any other potential conflicts that fall within the scope and physical limits of this project. Laterals not marked when surveyed, but potential conflicts may exist.

Roadway  Station  ­ Station  Location  Sheet No.  Nature of Conflict

- Jefferson Street  21+25’J’  ­ 22+30’J’  RT  86  Underground utility within grading limits – Utility not marked when surveyed, but shown on facility map. Other conflicts may exist in this area.

Abandoned pay station and cable …………reviewed

(aband. No need to retain)NO TDS work

- Jefferson Street  22+25’J’  ­ 22+35’J’  RT  36  Potential conflict with proposed storm sewer

TDS road crossing facilities, unknown depth, 100-24 copper, 2 UO(12)(MM),  DW 12-22.  These facilities feed the Grant Cty Annex.  Existing staking sheets show a 4” conduit containing these facilities…….storm sewer issue…….see 2’to top of storm and 24” pipe…..new storm sewer..narrative on conflict required. Request depth on existing!!

(annex crossing, 23” deep at east curb and 43” at c/l of Jefferson st)

TDS will retain existing facilities in place.  Caution for compaction on select fill for TDS facilities. TDS will raise Ex cables.

- Jefferson Street  22+25’J’  ­ 22+35’J’  LT & RT  55,86  Underground utility within grading limits

Same as above comment… TDS road crossing facilities, unknown depth, 100-24 copper, 2 UO(12)(MM), DW 12-22, all within a 4” conduit.  These facilities feed the Grant Cty Annex……………..within grading limits…….8.5” concrete plus 6” base plus 12” select crush…no change to final grade

(23” on east side , 43” c/l , 47” on west side.)

TDS to keep facility in place and work with road contractor.  Should be ok.  TDS will keep facilities.  Caution for compaction on select fill for TDS facilities. Adjust TDS facilities towards R/W if required.

- Jefferson Street  22+25’J’  ­ 22+35’J’  RT  55,86  Potential conflict with proposed lighting system and post

Same as above comment… TDS facilities, unknown depth, 200-24 copper, One UO(12), spare 1.25” duct, all within a 4” conduit.  These facilities feed the Grant Cty Annex…..light post shown next to sidewalk…could light post be moved 1’ South to help avoid

( 8’ south of sidewalk to court hse.  8’6” north of decorative light post 33” deep) TDS will retain facilities, field adjustment if required during construction. Adjust TDS facilities towards R/W if required.

- Jefferson Street  23+15’J’  ­ 24+35’J’  RT  86  Underground utility within grading limits

Same as above comment… TDS facilities, unknown depth, 200-24 copper, One UO(12), spare 1.25” duct, all within a 4” conduit.  These facilities feed the Grant Cty Annex……….no storm…….paving dimensions issues as above, 8.5”and 6” and 12” select

(37” deep at north curb, 53” at c/l maple st ,44” at south curb of maple st.  10’8” from Jefferson st. curb) TDS will retain facilities, field adjustment if required during construction. Adjust TDS facilities towards R/W if required.

- Jefferson Street  23+30’J’  ­ 23+50’J’  RT  55,86  Potential conflict with proposed lighting system

Same as above comment… TDS facilities, unknown depth, 200-24 copper, One UO(12), spare 1.25” duct, all within a 4” conduit.  These facilities feed the Grant Cty Annex………..lighting decorative base is 20” diam and 6’ depth!

(32” east of ex.light base. 46” deep)

TDS will retain facilities, field adjustment if required during construction. Adjust TDS facilities towards R/W if required.

- Jefferson Street  24+12’J’  ­ 24+12’J’  RT  36  Potential conflict with proposed inlet

Same as above comment… TDS facilities, unknown depth, 200-24 copper, One UO(12), spare 1.25” duct, all within a 4” conduit.  These facilities feed the Grant Cty Annex………..Inlet for new storm….

(Same as #6)

TDS will retain facilities, field adjustment if required during construction. Adjust TDS facilities towards R/W if required.

- Jefferson Street  24+17’J’  ­ 24+17’J’  RT  55,86  Potential conflict with proposed lighting post

Same as above comment… TDS facilities, unknown depth, 200-24 copper, One UO(12), spare 1.25” duct, all within a 4” conduit.  These facilities feed the Grant Cty Annex………..should be ok. Adjust TDS facilities towards R/W if required.

- Hickory Street  9+20’H’  ­ 11+00’H’  LT & RT  87 40 41 Underground utility within grading limits – Utility not marked when surveyed, but shown on facility map. Other conflicts may exist in this area.

TDS conduit system, MH1W to MH2W, Aerial 3 copper cables, Pole #2 and Pole #3 adjacent to intersection.  These are Alliant poles, coordination with Alliant on outcome…TDS needs to locate the duct package……See page 40 for storm…. Prior locates indicate no TDS work required on Duct Package.

Top south duct.  Duct pack 3 wide x 2 high

(east side of Madison st 43”deep  at 18” from boc of hickory st .      44” c/l of Madisonst.

West side of Madison st. 30” deep at 48” from boc of hickory st.

TDS needs to survey the exact location of the duct package, it is marginal if depth of duct package is ok with new storm sewer. Storm 2.7 to 2.1 is issue area.  Storm 2.15 to 2.16 is replacement, should be ok.  Survey required for actual location of existing duct.

Final conclusion is duct pact is ok at present location.

- Elm Street  7+80’E’  ­ 11+95’E’  LT  88  Underground utility within grading limits – Not shown on facility map. Limits of utility may extend beyond area that was marked to be surveyed. Other conflicts may exist in this area.

TDS has no facilities on this section.  Wisconsin Independent network, LLC is a separate company from Farmers. The other fiber shown is owned by the Lancaster Schools….Discussed

- Elm Street  9+85’E’  ­ 9+90’E’  LT  88  Not shown on facility map. Potential conflict with proposed lighting system and post

TDS has no facilities on this section.  Wisconsin Independent network, LLC is a separate company from Farmers. The other fiber shown is owned by the Lancaster Schools.Discussed.

- Pine Street  9+65’P’  ­ 10+65’P’  RT  89  Underground utility within grading limits

BFO 144 in 1.25” conduit, spare 1.25” conduit, buried BFC 25-24. Only 1 existing facility shown.  ….TDS needs to field locate missing facility with coorndinates

Copper cable w. curb 35” deep               fiber w.curb 30” deep

“””   “””  c/l  31”                            c/l     38”  deep

“”     “”  e. curb34” deep                     e.curb  50” deep

TDS facilities to remain, TDS will adjust during construction if required. Adjust TDS facilities towards R/W if required.

- Pine Street  9+68’P’  ­ 9+68’P’  RT  59,89  Potential conflict with proposed lighting pull box

BFO 144 in 1.25” conduit, spare 1.25” conduit, buried BFC 25-24. Only 1 existing facility shown… TDS needs to field locate missing facility with coorndinates

Copper 22”deep 6’3” north of ex decorative light post and 5’ south of ex

Electric pole.

Fiber 33”deep 28” from ex decorative light post and 9’9” south of ex electic pole

TDS facilities to remain, TDS will adjust during construction if required. Adjust TDS facilities towards R/W if required.

- Pine Street  9+77’P’  ­ 9+77’P’  RT  59,89  Potential conflict with proposed lighting system

BFO 144 in 1.25” conduit, spare 1.25” conduit, buried BFC 25-24. Only 1 existing facility shown… TDS needs to field locate missing facility with coorndinates

Same as #13

TDS facilities to remain, TDS will adjust during construction if required. Adjust TDS facilities towards R/W if required.

- USH 61  34+50  ­ 34+50  RT  44  Potential conflict with proposed storm sewer

This is Pine St cables crossing.

BFO 144 in 1.25” conduit, spare 1.25” conduit, buried BFC 25-24. Only 1 existing facility shown…… TDS needs to field locate missing facility with coorndinates and depth measurement for storm issue

(same as #12)

TDS facilities to remain, TDS will adjust during construction if required. Adjust TDS facilities by raising in place if required.

- Linden Street  9+50’L’  ­ 10+50’L’  LT  90  Underground utility within grading limits

Buried 25-24 AT route Sheet 2…..discussed. Adjust TDS facilities by raising in place if required.

Aband 25pr copper   29” deep east curb  35”c/l  42” west curb

- Linden Street  9+77’L’  ­ 9+77’L’  LT  59,90  Potential conflict with proposed lighting system

Buried 25-24 AT route Sheet 2….discussed…should be ok. Adjust TDS facilities by raising in place if required.

Aband 25pr cable   25”deep 5’north of ex electric pole

- USH 61  38+55  ­ 38+55  RT  44  Potential conflict with proposed storm sewer

Linden St crossing.  Buried 25-24 AT route Sheet 2.  Structure 3.15 and 3.18….verify TDS depth

Same as #16  6’ back of linden st. curb east side and west side.

TDS facilities to remain, TDS will adjust during construction if required. Adjust TDS facilities by raising in place if required.

- USH 61  50+82  ­ 57+85  LT  81  Underground utility within grading limits

TDS cable in Foremost Easment.  BFC400-24, BFO(144), BFO(96) along this entire distance.  Copper peds A1A4 and A1A5.  Feed & distribution for DSA AB625….most match grading…should be ok. No TDS work anticipated

- USH 61  50+82  ­ 50+82  LT  81  Pedestal in conflict with proposed sidewalk

A1A4 pedestal.

TDS cable in Foremost Easment.  BFC400-24, BFO(144), BFO(96) along this entire distance.  Copper peds A1A4 and A1A5.  Feed & distribution for DSA AB625….TDS will move pedestal back from sidewalk, about 3’

Plenty of slack to move peds back. Copper cable 11’9” boc

- Ash Street  9+65’A’  ­ 9+65’A’  LT  48  Potential conflict with proposed storm sewer

Crosses facilities in easement.

TDS cable in Foremost Easment.  BFC400-24, BFO(144), BFO(96) along this entire distance.  Copper peds A1A4 and A1A5.  Feed & distribution for DSA AB625….existing storm but replacing…verify depth on TDS facilities 4.9 to 4.10…some flexibility on new storm

(comment next page)

Fiber 10’3” boc Madison st             copper 12’11” boc Madison st

North curb 57”deep                      north curb 58”deep

c/l of ash st 63”deep                    c/l of ash st 59”deep

south curb 40”deep                       south curb 49”deep

TDS facilities to remain, adjustment on Storm or TDS facilities can be done during construction. Adjust TDS facilities by raising in place if required.

- USH 61  53+81  ­ 53+81  LT  81  Pedestal in potential conflict with proposed sidewalk or curb

Pedestal A1A5

TDS cable in Foremost Easment.  BFC400-24, BFO(144), BFO(96) along this entire distance.  Copper peds A1A4 and A1A5.  Feed & distribution for DSA AB625… TDS will move pedestal back from sidewalk, about 5’

Same as #20 plenty of slack.  Plenty of slack to move peds back.

- USH 61  57+83  ­ 57+83  LT  82  Pedestal in potential conflict with proposed sidewalk

PA1B1 and power riser pole for aerial going East to DSA625AB.

TDS cable in Foremost Easment.  BFC400-24, BFO(144), BFO(96) along this entire distance.  TDS will move pedestal back from sidewalk, about 3’….this may be a ped with abandoned cable….TDS to check

This pedestal houses abandon cables that could be removed.

The pole by ped has 2 fiber risers on it. They will have to be dug up and  relashed for for slack when pole is moved.TDS to abandon pedestal. Alliant does not plan to move pole per their plan.

- USH 61  59+64  ­ 59+64  RT  62,82  Potential conflict with proposed lighting system

Service line to Car Wash at the intersection of Hwy 61 and City Limit Rd..should not be an issue….crossing with power cable

No sub. Services from this location No TDS line as indicated on Plan

- USH 61  59+70  ­ 59+70  LT & RT  82  Potential conflict with proposed culvert pipe

Service line to Car Wash at the intersection of Hwy 61 and City Limit Rd

24” culvert….will be close to apron end wall…should be ok…this is the 200 pair?? Not service to car wash…to be replaced. Where is car wash service.

No TDS line as indicated on Plan

200 pr cable under old “k” and hwy 61

W edge of k 45’ s of ped   43” deep

C/l of k 50”

e. edge of k  59”

between k  and 61

66” from old k to w edge of 61 rd ditch

42” in bottom of ditch

90” w edge of 61

106” c/l of 61

107” e edge of 61

57” bottom of e rd ditch of 61

32” from top of rd ditch to ped on city limits st

TDS facilities to remain, adjustment made during construction if required.

- Old CTH K  10+00’K’  ­ 11+42’K’  LT  93  Underground utility within grading limits

BFC400-24 and 1.25” vacant duct reworking ditch line….possible lower existing facilities….slight lowering of ditch line, 6” cut

32” n end by ped to 50” 45’ s of ped

9’6” from fence on n end by ped to 8’ from fence 45’ s of ped

TDS facility to remain, adjustment during construction if required, STA 11+00 is fill, slight cut in ditch line.TDS to lower and/or move towards R/W with existing cable.

- Old CTH K  11+00’K’  ­ 12+00’K’  RT  93  Underground utility within grading limits

From PA1B1 going East on the North side of City Limits Road BFC200-24 and 2 vacant ducts, ….possible lower existing facilities….slight lowering of ditch line, 6” cut

TDS to lower and/or move towards R/W with existing cable.

Same as 25 and 26

- Old CTH K  11+55’K’  ­ 11+55’K’  LT  93  Pedestals will likely need to be raised, lowered, or moved

BFC400-24 and 1.25” vacant duct, PA1B1, 4 distribution cables feed North along K, 25, 100, 50 and 18  ….possible lower existing facilities….slight lowering of ditch line, 6” cut

It will be hard to move ped. but should be able to lower

TDS facilities to remain. TDS to lower and/or move towards R/W with existing cable.

- City Limits Street  10+00’CL’  ­ 12+35’CL’  LT  94  Underground utility within grading limits

From PA1B1 going East on the North side of City Limits Road BFC200-24 and 2 vacant ducts, road expands over existing cables.See map 41…TDS will replace ped to ped…PA1B1 to PA1M1

This cable will be exposed and moved to the north along R/W

- City Limits Street  10+57’CL’  ­ 10+57’CL’  LT  62,94  Potential conflict with proposed lighting system

From PA1B1 going East on the North side of City Limits Road BFC200-24 and 2 vacant ducts, road expands over existing cables. See map 41…TDS will expose and move cab ped to ped…PA1B1 to PA1M1

Same as 29 This cable will be exposed and moved to the north along R/W

TDS facilities to remain, adjustment during construction if required.

- City Limits Street  10+79’CL’  ­ 10+80’CL’  LT  62,94  Potential conflict with proposed lighting system and post

From PA1B1 going East on the North side of City Limits Road BFC200-24 and 2 vacant ducts, road expands over existing cables. See map 41…TDS will replace ped to ped…PA1B1 to PA1M1

(Same as 29) This cable will be exposed and moved to the north along R/W

- City Limits Street  10+99’CL’  ­ 10+99’CL’  LT  52  Potential conflict with proposed storm sewer and inlet

From PA1B1 going East on the North side of City Limits Road BFC200-24 and 2 vacant ducts, road expands over existing cables. See map 52…TDS will replace ped to ped…PA1B1 to PA1M1

Cable could lowered or moved at this point if route was moved  see #29

TDS facilities to remain, adjustment during construction if required.  Storm sewer and light pole issue. This cable will be exposed and moved to the north along R/W

- City Limits Street  12+25’CL’  ­ 12+25’CL’  LT  94  Pedestals will likely need to be raised, lowered, or moved

PA1M1, 200-24 and vacant duct.

From PA1B1 going East on the North side of City Limits Road BFC200-24 and 2 vacant ducts, road expands over existing cables. See map 52…TDS will replace ped to ped…PA1B1 to PA1M1 Cable/Pedestal move towards R/W

Same as 29

Cable could lowered or moved at this point if route was moved  see #29

TDS facilities to remain, adjustment during construction if required.  Storm sewer and light pole issue.

- 6 poles from STA 41+60 L to STA 46+80 L, Sheet 79 and 80 are prior listed as TDS poles.  TDS has no attachment.  Charter has aerial service along and on these poles.  As the last utility attached, Charter is responsible for pole removal.