{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":24,"n_cols":7,"rows_kept":24,"cut":false,"hidden":false,"merged":[[3,0,3,6]]}
["5290-02-70, Mazomanie- Sun Prairie, STH 113(S) Intersection, STH 19, Dane Co. "]
[]
["See Utility Conflict PDF for details illustrating issue"]
["Anticipated Potential Direct Conflicts"]
["Conflict","STA","Offset","Utility Company","Utility","Location","WisDOT Construction Activity"]
[1,"STA. 100+40 \"EB\"","N/A","MG&E","Gas","Gas line buried perpendicular  to roadway","Reconstruct Roadway - Same elevation "]
[2,"STA. 101+00 \"EB\" - STA. 107+00 \"EB\"","45' RT","MG&E","Gas","Gas line buried along ditch","Sliver fill in ditch"]
[3,"STA. 117+50 \"EB\"","N/A","MG&E","Gas","Gas line buried perpendicular  to roadway","Remove topsoil and poor soil underneath; fill to approximately 6 feet above current grade"]
[4,"STA. 117+50 \"EB\"","N/A","AT&T","Fiber","Fiber line buried perpendicular  to roadway","Remove topsoil and poor soil underneath; fill to approximately 6 feet above current grade"]
[5,"STA. 120+50 \"WB\" - STA. 136+50 \"WB\"           STA. 724+50 \"TWWB\" - STA. 735+50 \"TWWB\"","40'-90' LT","TDS","Telecom","Underground telephone buried along ditch","Regrade ditch in Stage 1 and 4"]
[6,"STA. 120+50 \"WB\" - STA. 132+00 \"WB\"","50'-90' LT","Waunakee Utilities","Electric","Overhead electric along ditch","Regrade ditch in Stage 1 and 4"]
[7,"STA. 206+00 \"NB\" - STA. 213+50 \"NB\"","66'-90' RT","MG&E","Gas","Gas line buried along toe of slope","Remove topsoil and poor soil underneath; fill to approximately 0-6 feet above current grade"]
[8,"STA. 209+50 \"NB\" - STA. 213+50 \"NB\"","66'-90' RT","AT&T","Fiber","Fiber line buried along toe of slope","Remove topsoil and poor soil underneath; fill to approximately 0-6 feet above current grade"]
[9,"STA. 216+70 \"NB\"","N/A","AT&T","Fiber","Fiber line buried perpendicular  to roadway","Reconstruct Roadway - Raise grade approximately 1.5'"]
[10,"STA. 217+30 \"NB\"","N/A","Waunakee Utilities","Electric","Overhead electric perpendicular to roadway","Reconstruct Roadway - Raise grade approximately 1.5'"]
[11,"STA. 216+75 \"NB\" - STA. 217+75 \"NB\"","N/A","TDS","Telecom","Underground telephone buried perpendicular to roadway","Reconstruct Roadway - Raise grade approximately 1.5'"]
[12,"STA. 216+75 \"SB\" - STA. 225+00 \"SB\"","30' - 60' RT","TDS","Telecom","Underground telephone buried along roadway","Reconstruct Roadway "]
[13,"STA. 217+40 \"NB\"","N/A","MG&E","Gas","Gas line buried perpendicular  to roadway","Reconstruct Roadway - Raise grade approximately 1.5'"]
[14,"STA. 217+40 \"SB\" - STA. 225+00 \"SB\"","24' LT","MG&E","Gas","Gas line buried along roadway","Reconstruct Roadway "]
[15,"STA. 219+35 \"SB\"","N/A","MG&E","Gas","Gas lateral buried perpendicular  to roadway","Reconstruct Roadway - Raise grade approximately 2'"]
[16,"STA. 220+35 \"SB\"","N/A","MG&E","Gas","Gas lateral buried perpendicular  to roadway","Reconstruct Roadway - Raise grade approximately 2'"]
[17,"STA. 222+50 \"SB\"","N/A","MG&E","Gas","Gas lateral buried perpendicular  to roadway","Reconstruct Roadway - Lower  grade approximately .25'"]
[18,"STA. 217+00 \"NB\"","25' RT","Waunakee Utilities","Electric","Underground electical to lighting","Remove lighting pedestal and provide connection to new lighting"]
[19,"STA. 703+00 \"TWSB\" - STA. 708+00 \"TWSB\"","20' LT","MG&E","Gas","Gas line buried along ditch","Sliver fill in ditch for temporary widening in stage 1"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}