## 59260560_tim
CONTRACT TIME FOR COMPLETION
Wisconsin Department of Transportation DT1923 04/2021
Project ID | 5926-05-60 |  |  | Highway | STH 92 |  |  |  | Project Title | Mount Horeb - Brooklyn | [13 empty] | Date of Letting | 2022-11-08
Work Type | Short Term Overlay |  |  | County | Dane |  |  |  | Project Limits | E JCT CTH G to STH 69 | [13 empty] | Probable Date of Beginning | 2023-03-20
ITEM ANALYSIS
Item |  | Contract Quantity per Stage |  |  |  |  | Total Quantity | Unit | Production Rate |  | Working Days (per Stage) | [6 empty] | Stage 1 |  | Stage 2 |  | Stage 3 |  | Stage 4 |  | Stage 5
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | [11 empty] | Begin | End | Begin | End | Begin | End | Begin | End | Begin | End | Gap 1 | Gap 2 | Gap 3 | Gap 4 | Gap 5
Traffic Control |  | 1 |  |  |  |  | 1 | Day | 1 |  | 1 | / |  | / | / | / |  | 1 | 2 | [8 empty] | 1 | 0 | 0 | 0 | 0
Culvert Replacement (Temp Close) |  | 92 |  |  |  |  | 92 | LF | 32 |  | 3 | / |  | / | / | / |  | 2 | 5 | [8 empty] | 2 | 0 | 0 | 0 | 0
Ashaltic Surface (Temp Close) |  | 56 |  |  |  |  | 56 | Ton | 200 |  | 1 | / |  | / | / | / |  | 5 | 6 | [8 empty] | 5 | 0 | 0 | 0 | 0
Traffic Control |  |  | 1 |  |  |  | 1 | Day | 1 |  |  | / | 1 | / | / | / |  |  |  | 6 | 7 | [6 empty] | 0 | 6 | 0 | 0 | 0
Culvert Replacement |  |  | 80 |  |  |  | 80 | LF | 32 |  |  | / | 3 | / | / | / |  |  |  | 7 | 10 | [6 empty] | 0 | 7 | 0 | 0 | 0
Beam Guard |  |  | 2299 |  |  |  | 2299 | LF | 200 |  |  | / | 12 | / | / | / |  |  |  | 10 | 22 | [6 empty] | 0 | 10 | 0 | 0 | 0
Milling |  |  | 129000 |  |  |  | 129000 | SY | 14000 |  |  | / | 10 | / | / | / |  |  |  | 22 | 32 | [6 empty] | 0 | 22 | 0 | 0 | 0
HMA 4 LT 58-28 S |  |  | 14450 |  |  |  | 14450 | Ton | 1276 |  |  | / | 12 | / | / | / |  |  |  | 23 | 35 | [6 empty] | 0 | 23 | 0 | 0 | 0
Base Aggregate Dense 3/4-Inch |  |  | 1930 |  |  |  | 1930 | Ton | 400 |  |  | / | 5 | / | / | / |  |  |  | 35 | 40 | [6 empty] | 0 | 35 | 0 | 0 | 0
Pavement Marking |  |  | 131765 |  |  |  | 131765 | LF | 35000 |  |  | / | 4 | / | / | / |  |  |  | 40 | 44 | [6 empty] | 0 | 40 | 0 | 0 | 0
Finishing Roadway |  |  | 1 |  |  |  | 1 | Day | 1 |  |  | / | 1 | / | / | / |  |  |  | 44 | 45 | [6 empty] | 0 | 44 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / |  | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
| Date |  | Days |  |  | Possible Work Days | Additional Work Days Modifier | Adjusted Possible Work Days |  | Probable Work Days | [6 empty] | Note: Chart is based on the assumption of work not occuring on weekends or holidays. If work is expected to occur on these days, adjust Possible Work Days by adding days to the Additional Work Days Modifier column. See FDM 19-10-30.
Month | Begin | End | Month | Total | Holiday |  |  |  |  | % | Month |  |  | Total
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | REMARKS
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | STH 92 will remain open during construction with flagging operations utilized. A temporary closure will be used for the culvert replacement near the STH 69 intersection. The closure work is to be finished by April 1st. Shoulder closures will be implemented for culvert and beam guard work.
March | 2023-03-20 | 2023-03-31 | 12 | 12 |  | 10 |  | 10 |  | 58 | 6 |  |  | 6
April | 2023-04-01 | 2023-04-30 | 30 | 42 |  | 20 |  | 20 |  | 58 | 12 |  |  | 18
May | 2023-05-01 | 2023-05-31 | 31 | 73 | 1 | 22 |  | 22 |  | 68 | 15 |  |  | 33
June | 2023-06-01 | 2023-06-30 | 30 | 103 |  | 22 |  | 22 |  | 81 | 18 |  |  | 51
July | 2023-07-01 | 2023-07-14 | 14 | 117 | 2 | 8 |  | 8 |  | 85 | 7 |  |  | 58
|  |  | 0 | 117 |  | 0 |  | 0 |  |  | 0 |  |  | 58
|  |  | 0 | 117 |  | 0 |  | 0 |  |  | 0 |  |  | 58 |  |  | Contract Work Type
|  |  | 0 | 117 |  | 0 |  | 0 |  |  | 0 |  |  | 58 |  |  |  | Calendar Day |  |  | 117
|  |  | 0 | 117 |  | 0 |  | 0 |  |  | 0 |  |  | 58 |  |  |  | Working Day |  |  | 58 |  |  |  | Prepared By
|  |  | 0 | 117 |  | 0 |  | 0 |  |  | 0 |  |  | 58 |  |  |  | Completion Date |  |  | 2023-07-14 |  |  |  | Kody Kaiser
[8 empty] | Page 1 of 1 |  | CONSTRUCTION YEAR: | [7 empty] | 2023
Formulas:
Possible Work Days = NETWORKDAYS([Short Term Overlay],[Contract Quantity per Stage])-[STH 92]