## 5967-01-70
CONTRACT TIME FOR COMPLETION
Wisconsin Department of Transportation DT1923 04/2021
Project ID | 5967-01-70 |  |  | Highway | STH 126 |  |  |  | Project Title | STH 81-Belmont | [12 empty] | Date of Letting | 2022-03-08
Work Type | Resurfacing |  |  | County | Lafayette |  |  |  | Project Limits | STH 81 to CTH G | [12 empty] | Probable Date of Beginning | 2022-05-02
ITEM ANALYSIS
Item |  | Contract Quantity per Stage |  |  |  |  | Total Quantity | Unit | Production Rate |  | Working Days (per Stage) | [5 empty] | Stage 1 |  | Stage 2 |  | Stage 3 |  | Stage 4 |  | Stage 5
|  | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | [10 empty] | Begin | End | Begin | End | Begin | End | Begin | End | Begin | End | Gap 1 | Gap 2 | Gap 3 | Gap 4 | Gap 5
Traffic Control |  | 1 |  |  |  |  | 1 | DAY | 1 |  | 1 | / | / | / | / |  | 0 | 1 | [8 empty] | 0 | 0 | 0 | 0 | 0
Remove Asphaltic Surface Milling |  | 73000 |  |  |  |  | 73000 | SY | 12000 |  | 7 | / | / | / | / |  | 1 | 8 | [8 empty] | 1 | 0 | 0 | 0 | 0
HMA Pavement |  | 16500 |  |  |  |  | 16500 | TON | 1200 |  | 14 | / | / | / | / |  | 1 | 15 | [8 empty] | 1 | 0 | 0 | 0 | 0
Base Aggregate Dense 3/4 Inch |  | 2750 |  |  |  |  | 2750 | TON | 1300 |  | 3 | / | / | / | / |  | 15 | 18 | [8 empty] | 15 | 0 | 0 | 0 | 0
Centerline Rumble Strips |  | 22500 |  |  |  |  | 22500 | LF | 39000 |  | 1 | / | / | / | / |  | 18 | 19 | [8 empty] | 18 | 0 | 0 | 0 | 0
Grooved Epoxy-Grinding |  | 49100 |  |  |  |  | 49100 | LF | 41000 |  | 2 | / | / | / | / |  | 19 | 21 | [8 empty] | 19 | 0 | 0 | 0 | 0
Pavement Marking |  | 87300 |  |  |  |  | 87300 | LF | 60000 |  | 2 | / | / | / | / |  | 21 | 23 | [8 empty] | 21 | 0 | 0 | 0 | 0
Finishing |  | 3 |  |  |  |  | 3 | DAY | 1 |  | 3 | / | / | / | / |  | 23 | 26 | [8 empty] | 23 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | / | / | / | / | [11 empty] | 0 | 0 | 0 | 0 | 0
| Date |  | Days |  |  | Possible Work Days | Additional Work Days Modifier | Adjusted Possible Work Days |  | Probable Work Days | [5 empty] | Note: Chart is based on the assumption of work not occuring on weekends or holidays. If work is expected to occur on these days, adjust Possible Work Days by adding days to the Additional Work Days Modifier column. See FDM 19-10-30.
Month | Begin | End | Month | Total | Holiday |  |  |  |  | % | Month |  | Total
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | REMARKS
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | Project will be completed in a single stage with a flagging operation.
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
May | 2022-05-02 | 2022-05-31 | 30 | 30 | 1 | 22 |  | 22 |  | 68 | 15 |  | 15
June | 2022-06-01 | 2022-06-30 | 30 | 60 |  | 23 |  | 23 |  | 81 | 19 |  | 34
|  |  | 0 | 60 |  | 0 |  | 0 |  |  | 0 |  | 34
|  |  | 0 | 60 |  | 0 |  | 0 |  |  | 0 |  | 34
|  |  | 0 | 60 |  | 0 |  | 0 |  |  | 0 |  | 34 |  |  | Contract Work Type
|  |  | 0 | 60 |  | 0 |  | 0 |  |  | 0 |  | 34 |  |  |  | Calendar Day
|  |  | 0 | 60 |  | 0 |  | 0 |  |  | 0 |  | 34 |  |  |  | Working Day |  |  | 30 |  |  |  | Prepared By
|  |  | 0 | 60 |  | 0 |  | 0 |  |  | 0 |  | 34 |  |  |  | Completion Date | [6 empty] | Don Carpenter, WisDOT
[8 empty] | Page 1 of 1 |  | CONSTRUCTION YEAR: | [6 empty] | 2022
Formulas:
Possible Work Days = NETWORKDAYS([Resurfacing],[Contract Quantity per Stage])-[STH 126]
Possible Work Days = NETWORKDAYS([Resurfacing],[Contract Quantity per Stage]-[STH 126]+1)