Appendix B

Revised Responses to WisDOT Comments on original letter work plan proposal

- Overall, more answers are needed before a comfort level can be established.  This seems to be a proposal of work, not a plan this needed.

  - The proposal is our work plan, but we are happy to provide this more detailed formatted work plan address the additional information WisDOT requested.

- Figure 3 is missing several Subsidence Feature Locations as compared to WisDOT documentation.  Plan discuss five reported subsidence areas, but the provided Figure 3 indicates six locations.  This needs to be clarified.

  - {Figures 3-5} We hereby amend the plan to include 6 locations shown on Figure 3. Our plan is to address all known subsidence features and complete a geophysical investigation to discover and remediate any additional subsurface areas of concern within the project footprint.  If there are other features we are not aware of please note them on the map and they will be incorporated into the scope of work.

- There are several areas of the provided plan that need further explanation and discussion

  - We assume that this comment refers to the following content below.

- Is the overburden mitigation supposed to happen before joints are fixed?

  - {Section 4 & Section 5, assumption 5} No. It is not necessary to conduct mitigation before the joint repairs occur.  Backfill mitigation will likely occur in conjunction with joint sealing.

- Frozen ground?  How does this affect what is being proposed?

  - {Section 5, Assumption 7} Significant frost depths may favor use of an auger drill rig equipment rather than a Geoprobe to place grout for mitigation. The MASW geophysical investigation can be conducted over frozen ground.  We have been told that the road surface above the subsidence features has been excavated and recompacted.  Therefore, the important stiffness anomalies should be below the frost penetration. Frost will change strength but the important layers should be frost free for accurate stiffness analysis.  To the extent that frozen soils exhibit a need to be mitigated, that work would happen when frost conditions do not exist.

- Will the 500 lb. hammer ruin the temporary asphalt driveway for the residents?

  - {Section 5, Assumption 18} No. The hammer should not damage pavement. Patching or repair will be needed where borings are advanced through asphalt for ground truth or mitigation.

- Will this equipment get between the sides of the pipe and the haunches?  It seems like the pipe would prevent information in this area.

  - {Section 5, Assumption 3} The equipment is placed on the surface above the pipe.   It is possible that MASW will provide useful information about conditions adjacent to the sides and below the spring line of the pipe. This information will be shared with the Pipe Mitigation team.  However, it is possible but not certain that we will be able to detect loose conditions in the backfill below the pipe by doing this type of survey.  We assume that loose areas below the pipe will be addressed during the joint sealing effort.

- More information about what the results could look like and what fix would happen for each result.  That needs to be understood upfront.

  - {Section 2.4.1 and Appendix B} In general MASW is very straightforward for use in this situation.  It will show a profile of the backfill that will vary by showing intervals of higher or lower shear wave velocity.  Because the rate at which sound waves travel through these materials is a function of the shear strength of those soils, high shear strength is correlated to higher velocity and lower soil shear strength indicates lower velocities. The fix for shallow areas will most likely be excavation and recompaction. For deeper areas below about 5-7 feet, the presumptive remedy will be compaction grouting consisting of pressure grouting through a drill casing.

  - {Sections 3.6, 3.7} Areas of both high and low shear wave velocities will be included in the ground truth step to provide a correlation between wave velocity and soil stiffness.  Areas that are correlated with low strength/velocity will be mitigated.  The mitigation selected will depend on the factors at the depth/location where the apparent weak soils are discovered.  The mitigation is intended to increase soil shear strength in the backfill regardless of whether a distinct void is observed.

- The plan is not consistent with nomenclature.  Several areas only highlight ‘voids’.  The Department is interested in mitigating both voids, and loosely backfilled zones.  These zones may extend from the ground surface, to the haunch areas of the pipe. {Section 5, assumption 3}. We are assuming the pipe grouting will correct any loose/voided support areas below the pipe, and within the haunch areas

  - {Section 2.4.1} Our plan is intended to identify and mitigate areas of low velocity shear wave features which we were referring to generically as voids. The work plan has been updated to refer to loose soils as low density features. The wave velocity contrast identified as low surface wave velocity may represent a continuum of soil conditions ranging from dry loose sand, wet soft clay, loose backfill, and/or air filled voids.

  - We concur with the assumption that the Pipe Mitigation team is addressing low density soils below the spring line of the pipe (we avoided the term haunches as there seems to be some confusion as to what this term means.

- The proposal indicates that only 1000’ of the pipe trench has been compromised.  What is the fix in this 1000’ area that has been compromised?  The Department feels the complete 3000’ may be compromised, but distress may not have been exhibited in the upper 2000’ of pipe yet, because it is buried deeper (has more cover).  The contractor needs to prove to us that this area has no issues.  This may require multiple MASW lines in the 2000’ length.

  - {Section 2.1} The plan is amended so that MASW will be conducted in 3 passes (transects) along the entire 3,000 foot centerline length of pipe as well as either side of the pipe.

3.0 General - More explanation is needed in several areas, as detailed below.

- 3.0 Bullet 5.  Proposal proposes a ‘geophysical survey’ for 2000’ of the pipe.  We assume this means MASW, but this is not specified.

  - Correct; we propose MASW as the geophysical method of investigation.

- 3.0 Bullet 6.  More definition/explanation of potential mitigation actions need to be provided. (Discussed further in later comments.)

  - Described below as noted.

- 3.0 Last bullet.  Some uncertainty of possible future issues is raised.  We feel part of this proposal should include some type of monitoring program over time.

  - {Section 3.7.4} Our final report will include recommendations for additional monitoring based on the results of the final verification resurvey.  After the investigation and mitigation provides a thorough understanding of subsurface conditions informed decisions can be made when determining if a monitoring program is necessary. We have added a follow up MASW scan conducted approximately 4 months after the mitigation has been completed would provide adequate data to determine if any additional issues develop in addition to a 1 year follow up survey.

- 4.0 As previously stated, MASW should be used to identify both voids and loose zones.  Some parts of this section discuss voids only.

  - {Section 2.4.1} Both terms can be interpreted to mean low velocity zones.  We expect that both conditions are likely to coexist in areas below subsidence features and both are planned to be mitigated if observed.

- 4.3 Will the MASW lines located at the outer pipe edges adequately provide coverage for the complete trench excavation width?

  - {Section 3.4} Yes.  We believe that the outside MASW lines alone are likely adequate to identify potential mitigation areas above the pipe both along its centerline as well as the edges. We have added the extra line along the pipe center as a quality control effort.

- 4.3 Will MASW lines/data adequately delineate the material characteristics located in the zone from the top of the ‘repaired’ haunches, to the top of the pipe?  Will the results from this area be ‘masked’ by the pipe?

  - {Section 3.4} The MASW survey lines outside the centerline are intended to address the backfill conditions along the outermost edge (spring line) of the pipe and the overlying backfill.  The pipe is a rigid 8 inch thick concrete material but at the same time, MASW may not resolve thin layers because the surface waves penetrating deeper areas are generally longer wavelengths. The longer wave lengths have lower resolution so they will not be blocked by the pipe.  We propose conducting CPT Borings to profile the deeper locations of the backfill to aid in interpretation of the deeper fill material from the MASW.

- 4.4 Ground truth methods in this section include “direct push percussion rig”, i.e. Geoprobe.  We do not feel this is an appropriate device to effectively measure density/stiffness, as there is no quantitative test performed.  This method was not included in the ground truth methods listed in Section 3.0.

  - {Section 3.5} Our apology for any confusion, although Geoprobe has a CPT direct push tool that can be used with a percussion rig, it is still a CPT direct push method. We have not yet identified a Geoprobe contractor with this capability so we have deleted references to Geoprobe from the current work plan..

- 4.5 More detail needs to be provided on the conceptual mitigative alternatives.  CPT or Direct Push grouting is only for smaller, localized areas like voids.  Is pressure grouting being proposed to address larger loose zones?

  - {Section 3.7} These mitigation alternatives are conceptual at this stage because the MASW survey and ground truth step is needed to define the scope of the mitigation.  The plan indicates that in general, deeper and larger wide spread areas would be more effectively mitigated via grout injection.

- The proposal does not address how existing facilities will be affected/addressed (i.e. curbs, utilities, storm/sanitary sewers, water lines, etc.).  Vibratory compaction needs more explanation, as there are various methods, and some may not be applicable for this site.  Vibratory compaction may not be possible/effective for larger, deeper zones.

  - {Section 5, assumption 18} Vibratory compaction was dropped from the final work plan based on comments for WisDOT and concerns about damaging the pipe. We are not intending to mitigate any other utilities than the backfill above the storm sewer. However, any curbs or features that need to be removed will be replaced to their required conditions by IGE.

- MASW, SPT, and CPT data used to locate areas with issues all need clarification on what values are acceptable before remediation is necessary.  Each of these devices measure spectrums of stiffness/density, and there is no information provided on what ‘acceptable limits’ are.  For instance, are SPT values of 8 acceptable, or are minimum values of 14 required?  These criteria may also vary by soil type.

  - {Section 1.1, 2.3, and 3.6}} We have clarified our purpose and conceptual site model to more clearly define the objective of the investigation is mitigate areas of loose soils potentially associated with future subsidence features; the goal is not to bring the entire backfill up to an arbitrary density or compaction threshold.  Based on our conceptual model, the subsidence features are related to downward settlement of overlying soil into the loose zones.  In shallow areas where we will have an excavation and can recompact in lifts, we will meet compaction of 90% (95% in top three feet) standard proctor density.

  - For compaction pressure grouting performed at depths below 3-7 feet, we will be injecting grout into loose zones so that deformation and downward settlement cannot occur.  In these areas, the key threshold is related to the volume of grout that the loose zone is able to take in.  This will eliminate the potential for this zone to settle because the available pore space and deformable material will be compressed and occupied by the grout mixture.  This process may require iterative trials and generally good engineering practice to evaluate field conditions and make corrections. The process will be documented in the final mitigation report along with challenges encountered and results of follow up monitoring and additional mitigation if required.

  - Performance standard.  The confirmatory MASW survey, the addition of 4 month follow-up survey, and an annual monitoring survey (with CPT data collection) should provide a high degree of confidence that potential subsidence features related to loose soils will be identified and corrected.  These added tasks obviate the need for arbitrary threshold values because the monitoring and any follow up mitigation becomes what is essentially an outcome-based performance standard.

  - We have evaluated looking at blow counts or apparent density from CPT but our previous investigations indicated that the subsidence features were not well correlated with blow count data (i.e. high blow count n-values were found under subsidence features and low n-values found in areas with no subsidence). This suggests that the backfill is likely to exhibit variability that may not be directly reflected in an arbitrary threshold value, and would not be helpful in achieving the goal of limiting the formation of future subsidence features.

- These decision points/values (required for each method) will greatly affect the amount of remediation work warranted.  These decisions are also necessary to be able to analyze the confirmatory geophysical work. These decision points/values (required for each method) will greatly affect the amount of remediation work warranted.  These decisions are also necessary to be able to analyze the confirmatory geophysical work.

  - {Section 3.6} Upon review of the procedures and the additional monitoring proposed we do not believe that the paradigm described will apply to the reclamation work.  Our proposal is to mitigate loose soils wherever they occur in the backfill above pipe.  We will have indirect and direct data to determine where these areas are and will have sufficient post-mitigation monitoring to assess the performance of the mitigation.  Because the basis for what does and does not require mitigation will be based on the geophysical data and ground-truth steps, specific quantitative thresholds may not be useful or achieve better outcomes.

- 6.0 Geoprobe use is again suggested.  This does not appear to be a useful device for this work. (Unless only used for grouting.)

  - {Section 2.4.2} CPT will be used and “direct push” alone will not be used to test soil density. As above, Geoprobe does have a CPT tool although it may be unlikely that Geoprobe will be useful when deep frozen soil conditions are present.

- 7.0 Bullet 1.  It is our understanding the pipe remediation plan also calls for haunch improvements between pipe joints.  This contradicts what is written.

  - {Section 5, assumption 3} The scope of work presented is for backfill above the storm sewer pipe; if there are apparent contradictions with other plans, we would need to understand the specific elements of those plans that are at issue in order to address this concern. After listening carefully to the proposed pipe mitigation plans, we are confident that there are no conflicts.

- 7.0 Bullet 5.  Surface frost is discussed, but there is no depth provided on what the unacceptable value is.  This may affect project remediation schedule.

  - {Section 5, assumption 7} We can work with some frost but mitigation will be slowed by more than 2 feet of frost due to difficulty in accessing the subsurface with drill rig.  Work inside pipe (joint repair) will last into the summer 2020.  If acceptable by WisDOT, we can complete the initial MASW and then complete ground truth and soil mitigation in the spring when frost is gone.  With a follow up MASW after the pipe mitigation is completed.

- 7.0 Bullet 14.  It appears that Barr may not have all the collected-to-date information.  Has everything been made available to them?

  - {Section 2.2} IGE has informed us that the relevant project files have been provided to Barr Engineering and all data will be reviewed prior to commencement of the investigation to ensure project success.

- More discussion/justification may be necessary on what remediation/investigations are performed first.  Fix pipe joints and haunches before/after/concurrently with MASW work?  MASW provides an assessment at one point in time.  If pipe experiences more flow and soil loss after testing, the results may not be accurate anymore.  This decision may also be related to the acceptable amount of surface frost during MASW testing.

  - {Section 5, assumption 5} We propose conducting MASW first, followed by ground truth which can occur in conjunction with the pipe joint sealing.  The joint sealing would be followed by backfill mitigation and then the confirmatory MASW survey.

- Are MASW results affected by soil type?

  - {Section 2.4.1} Yes. Surface wave velocity will vary somewhat by soil type but the method is most sensitive to changes in in shear strength. This is why MASW is uniquely useful for this investigation.  The ground truth will help to further refine the limits of high vs lower soil strength/velocity.

Review of 3D Geophysics (i.e. 3D) Proposal:  There appears to be several disconnects between this proposal and Barr’s proposed work. These include:

- 3D proposes 750’ of survey during ‘Phase 1’, not 1000’ as Barr proposes.  But 3D includes 5000’ in the cost estimate.  These need to be clarified/corrected.

  - The cost estimate will likely be revised to match payment terms but in all cases of apparent contradiction, the Barr scope shall prevail.

- 3D discusses voids, but does not discuss defining looser zones, which is also required.

  - They are the same condition from a geophysical standpoint regardless of terms.

- 3D discusses depth to weathered bedrock.  This has no relation to this project.

  - Agreed this is an issue for some sites and is included as example in Appendix B of a dense material, but is unlikely at this site because we have at least one deep boring that suggests bedrock is much deeper than the pipe backfill.

- 3D discusses collecting “tape measure data through the pipe”.  Further explanation on this is required.

  - Correlation of the pipe distance to above ground distance will be provided by Barr Engineering based on our previous pipe inspection work.

- 3D scope of work is confusing.  Barr states there will be 5000 linear feet of MASW work, which agrees with the 3D “Primary Geophysical Survey” scope presented.  Barr also states there will be 3000 lineal feet of post-remediation work completed, but 3D appears to indicate this is “Optional” (and it will be 5000’). 3D also appears to indicate that the “full length of the sewer line” investigation is only completed if “appropriate”, and further states that repeat survey “could” be conducted.  A definitive scope of work needs to be clarified, and coordinated between the two documents.

  - Barr’s scope of work prevails.  3DGeo will perform the work as directed. Units for payment by Barr’s subcontractor is shown only to provide detail on the technical details of the survey.